## Directions
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
Directions:
Bidder's NAME: |  | Enter Name Here
Bidder's ADDRESS: |  | enter address here
Bidder shall complete all cells highlighted in yellow.
Cells highlighted in orange will be filled/calculated automatically.
The Fixed Price for Phases 3-6 shall include ANY and ALL charges or costs for the duration of the Phases, including:
1. All direct and indirect costs, as well as overhead, fees, profit, including but not limited to:
2. Labor, parts, shipping, material and equipment costs;
3. Administrative, reporting or other requirements, overhead costs and profit;
4. Travel costs, parking fees, and any and all ancillary costs including permits, insurance, licenses etc.; and
5. Services not explicitly stated in these specifications but necessarily attendant thereto as applicable for the associated
items for which the rate is being quoted.
The Fixed Price for Phases 3-6 shall also include all costs associated with implementnig:
6. Clinic Module Customizations
7. Vendor Module Customizations
8. State-Only Module Customizations
9. Admin Module Customizations
10. Case Management Module Development
Bidder's authorized representative must print the workbook and sign below:
Print Name: |  |  | Date:
Title:
Signature:

## Pricing Summary
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
Pricing Summary
Note this worksheet will be automatically filled from the other worksheets
Bidder's NAME: |  | Enter Name Here
Fixed Price for Phase 3 |  |  | 0
Fixed Price for Phase 4 |  |  | 0
Fixed Price for Phase 5 |  |  | 0
Fixed Price for Phase 6 |  |  | 0
Fixed Price for Phase 7 |  |  | 0
Total Fixed Price for Phases 3-7 |  |  | 0
System Change Management - Maximum Budget Allocation |  |  | 0
Total Bid Price |  |  | 0

## Phase 3-6 Fixed Prices
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
Phase 3-6 Fixed Prices
Bidder shall enter Fixed Prices for each Phase 3 through 6.
Bidder's NAME: |  | Enter Name Here
Phase 3: Design & Development Phase
Phase 4: Testing & Training Phase
Phase 5: Pilot & Evaluation Phase
Phase 6: Statewide Implementation Phase
Total Fixed Price for Phases 3-6 |  |  | 0

## Phase 7 Fixed Price
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
Phase 7 Fixed Price
Bidder shall enter a Fixed Price for Year 1 and Year 2.
Bidder's NAME: |  | Enter Name Here
Post Implementation Support and Warranty Price for Year 1
Post Implementation Support and Warranty Price for Year 2
Total Post Implementation Support and Warranty Price Years 1 & 2 |  |  | 0

## System Change Management
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
System Change Management - Maximum Budget Allocation
Bidder shall complete columns: Specific Job Titles and Hourly Rates
Bidder's NAME: |  |  | Enter Name Here
Job Category |  | Specific Job Titles | Estimated Number of Hours | Hourly Rates | Estimated Cost
Engagement Manager |  |  | 200 |  | 0
Project Manager |  |  | 1000 |  | 0
Development Lead |  |  | 400 |  | 0
Database Programmer |  |  | 1000 |  | 0
Software Developer |  |  | 1000 |  | 0
Business Analyst Lead |  |  | 400 |  | 0
Business Analyst |  |  | 1000 |  | 0
QA Lead |  |  | 100 |  | 0
QA Tester |  |  | 400 |  | 0
Database Administrator |  |  | 400 |  | 0
Systems Administrator |  |  | 400 |  | 0
Training Lead |  |  | 100 |  | 0
Trainer |  |  | 200 |  | 0
Maximum Budget Allocation Total |  |  | 6600 |  | 0
Notes:
1. The estimated hours in column E are provided only for purposes of calculating a Maximum Budget Allocation for System Change Management
that will be used in evaluating the Cost proposals.
2. The Maximum Budget Allocation Total will be used to establish a budget for additional work done under the System Change Management process.
3. All work done under System Change Management will require advance review and approval by NYS.
4. The Maximum Budget Allocation Total will establish a maximum not-to-exceed cap on any additional work for NYWIC.
5. Hourly Rates are to be fully-loaded rates.

## Payment Schedule
NEW YORK STATE DEPARTMENT OF HEALTH
NYWIC T&I SERVICES
ATTACHMENT C - COST PROPOSAL WORKBOOK
Payment Schedule
Bidder's NAME: |  | Enter Name Here
Note this worksheet will be automatically filled from the other worksheets
Phase 3 – Design & Development Deliverables [October 2016 - February 2018 - 17 months]
ID # | Deliverables | Payment Milestone # | Payment % | Payment Amount ($)
NYWIC-3-01 | Design & Develpoment Initiation Meeting | 3-1 | 10 | 0
NYWIC-3-02 | Project Management Plan
NYWIC-3-03 | Deliverables Expectation Document (DED)
NYWIC-3-04 | Project Work Plan/Schedule
NYWIC-3-05 | Staffing Plan
NYWIC-3-06 | Change Management Plan
NYWIC-3-07 | Design Validation Sessions | 3-2 | 10 | 0
NYWIC-3-08 | Technical Architecture Plan
NYWIC-3-09 | Technical Architecture Documents
NYWIC-3-10 | Capacity Plan
NYWIC-3-11 | Report on Security and Disaster Recovery Procedures | 3-3 | 10 | 0
NYWIC-3-12 | System Requirements and Gap Analysis Document
NYWIC-3-13 | Implementation Plan
NYWIC-3-14 | Database Plan | 3-4 | 10 | 0
NYWIC-3-15 | Data Conversion Plan
NYWIC-3-16 | Testing Plan | 3-5 | 10 | 0
NYWIC-3-17 | Security Plan
NYWIC-3-18 | Training Plan
NYWIC-3-19 | Knowledge Transfer Plan
NYWIC-3-20 | Detailed Design Document | 3-6 | 10 | 0
NYWIC-3-21 | Database Creation
NYWIC-3-22 | Data Conversion and Clean-up; Data Migration and Validation. | 3-7 | 10 | 0
NYWIC-3-23 | MIS-EBT Interface Specifications
NYWIC-3-24 | Provide Technical Knowledge Transfer to NYS ITS Staff | 3-8 | 10 | 0
NYWIC-3-25 | Install and Test MIS Software in Development Environment
NYWIC-3-26 | Provide Baseline Test Report
NYWIC-3-27 | Clinic Module Customizations | 3-9 | 10 | 0
NYWIC-3-28 | Vendor Module Customizations
NYWIC-3-29 | State-Only Module Customizations
NYWIC-3-30 | Admin Module Customizations
NYWIC-3-31 | Case Management Module Development | 3-10 | 10 | 0
NYWIC-3-32 | Approved Work under System Change Management
NYWIC-3-33 | Code Ready for UAT
NYWIC-3-34 | Provide UAT Readiness Certification Report
NYWIC-3-35 | Monthly Project Status Reports
Subtotal Phase 3 |  |  |  | 0
Phase 4 – Testing & Training Deliverables [May 2017 - May 2018 - 13 months]
ID # | Deliverables | Payment Milestone # | Payment % | Payment Amount ($)
NYWIC-4-01 | Updated Project Work Plan/Schedule | 4-1 | 25 | 0
NYWIC-4-02 | Perform pre-UAT Key Function Walkthrough
NYWIC-4-03 | Provide Training to UAT Participants
NYWIC-4-04 | Provide Requirements for Migration to UAT Environment | 4-2 | 25 | 0
NYWIC-4-05 | Create Test Scripts and Test Data
NYWIC-4-06 | Provide Support During UAT
NYWIC-4-07 | Provide UAT Outcome Metrics Report | 4-3 | 25 | 0
NYWIC-4-08 | Develop Training Materials
NYWIC-4-09 | Provide ITS Operations Staff Training
NYWIC-4-10 | Provide State WIC Program Staff Training | 4-4 | 25 | 0
NYWIC-4-11 | Staffing Plan Updates
NYWIC-4-12 | Monthly Project Status Reports
Subtotal Phase 4 |  |  |  | 0
Phase 5 - Pilot & Evaluation Deliverables [June 2018 - September 2018 - 4 months]
ID # | Deliverables | Payment Milestone # | Payment % | Payment Amount ($)
NYWIC-5-01 | Updated Project Work Plan/Schedule | 5-1 | 50 | 0
NYWIC-5-02 | Pilot and Statewide Implementation Plan
NYWIC-5-03 | Clinic Readiness Checklist Template
NYWIC-5-04 | Convene Pilot Operations Initiation Meeting
NYWIC-5-05 | Provide Pilot User Training
NYWIC-5-06 | Provide Pilot User Training Evaluation/Competence Report
NYWIC-5-07 | Provide Pilot User Oversight and Consultation | 5-2 | 50 | 0
NYWIC-5-08 | Provide Pilot-Related Software Modifications and Testing
NYWIC-5-09 | Prepare Pilot Evaluation Report
NYWIC-5-10 | Staffing Plan Updates
NYWIC-5-11 | Monthly Project Status Reports
Subtotal Phase 5 |  |  |  | 0
Phase 6 – Statewide Implementation Deliverables [September 2018 - June 2019 - 10 months]
ID # | Deliverables | Payment Milestone # | Payment % | Payment Amount ($)
NYWIC-6-01 | Updated Project Work Plan/Schedule | 6-1 | 40 | 0
NYWIC-6-02 | Convene System Rollout Initiation Meeting
NYWIC-6-03 | Provide Statewide System Implementation Training and Materials | 6-2 | 40 | 0
NYWIC-6-04 | Provide System Rollout Oversight, Consultation, and Assistance
NYWIC-6-05 | Identification & Correction of Deficiencies
NYWIC-6-06 | Provide Comprehensive System Documentation Updated to Reflect NYS System | 6-3 | 20 | 0
NYWIC-6-07 | Staffing Plan Updates
NYWIC-6-08 | Monthly Project Status Reports
Subtotal Phase 6 |  |  |  | 0
Phase 7 – Post-Implementation Support & Warranty Deliverables [July 2019 - June 2021]
ID # | Deliverables | Payment Milestone # | Payment % | Payment Amount ($)
NYWIC-7-01 | Updated Project Work Plan/Schedule | Billing for this phase will be on a monthly basis in arrears for the twenty-four (24) month period and will be dependent upon satisfactory completion of deliverables.
NYWIC-7-02 | Follow-up Training Events
NYWIC-7-03 | System Problem Fixes and Written Reports
NYWIC-7-04 | Warranty Maintenance
NYWIC-7-05 | System Modifications
NYWIC-7-06 | Post-implementation Support and Knowledge Transfer
NYWIC-7-07 | Monthly Project Status Reports

## Sheet1 (hidden)
· Participant signature file capture and storage in the MIS | Req - 8 hr, DBA - 16
· Document scanning and file storage in the MIS with the capability to categorize for ease of retrieval
· Local Agency Auto-dialer capability
· Automated processing and file transfer for rebate and coupon programs for formula (current vendor is Mead Johnson) and other identified food products |  | Dev
· UPC/PLU download process
· Interface with NUPC database | Req 16,
· Processing the annual The Integrity Profile (TIP) report
· Case Management module
· NYS branding and terminology
· Farmers' Market Nutrition Program
· Integration of APL Central (Novo Dia) may be required
· Engagement Manager – Responsible for managing the contractual relationship with the State and oversight of the delivery of services. The Engagement Manager is accountable for the successful completion of all aspects of the resulting Contract.
· Project Manager – Responsible for T&I Contractor's overall project execution, accomplishment of all project deliverables, and the daily work of T&I Contractor personnel.
· Technical Lead – Serves as the technical architect responsible for ensuring that a solution is implemented so as at to meet all system and security requirements.
· Business Analyst Lead – Leads the team of Business Analysts who will assist in defining the business and functional requirements.
· Development Lead – Leads the team of developers who will configure the platform to meet the business requirements.
· Testing Lead – Leads the testing efforts, including T&I Contractor, NYS ITS, and NYWIC Program staff.
· Training Lead – Responsible for defining training needs, developing training curricula, and oversight of the Contractor’s delivery of training.