## Ph 4 Catch-All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 2016-04-27
7001 |  |  |  |  | Project Name: Gold STAMP Program to Reduce Pressure Ulcers Division Lead: Division of Nursing Homes and ICF/IID Surveillance, Center for Health Care Provider Services and Oversight Team Lead: Jackie Pappalardi Additional Staff: Paula Grogin, Rick Rees Description: The Gold STAMP Program to Reduce Pressure Ulcers is a coalition of organizations convened in New York State to provide resources and education across the continuum of care to improve the assessment, management and prevention of pressure ulcers. |  | Completed-Mar 2015
| 4/30/14 6/30/14 7/31/14 | P | P | P | Hire a Program Coordinator to host and manage the technical aspects of the Gold STAMP Program.
| 4/30/14 6/30/14 8/31/14 10/31/14 | P | P | P | Develop two new Collaborative targeted to New York State Veterans' Homes that are underperforming in the area of pressure ulcer prevention/treatment.
| 2014-11-14 | P | P | P | Plan and convene a one-day general meeting for Collaboratives, to include a "booster session" and focus groups to gather information to be utilized in developing a Gold STAMP "How To" Tool Kit. One-day meeting canceled (changed to webinar format to be held on 11/14).
| 2014-12-15 | P | P | P | Redirect efforts to reestablish Collaboratives that may have broken down and work toward their sustainability.
| 12/31/14 1/30/15 3/6/15 | P | P | P | Develop a "How To" Tool Kit for posting on www.goldstamp.org to promote the (autonomous) establishment of new Collaboratives.
| 12/31/14 3/31/15 | P | P | P | Continue to develop a Gold STAMP best practice model for posting on www.goldstamp.org.
| 2/28/15 3/19/15 | P | P | P | Kick off/launch the "How To" Tool Kit via a Public Health Live webcast.
| 2015-03-31 | P | P | P | Maintain and expand the universal Gold STAMP website (www.goldstamp.org) to include comprehensive information on training programs, resources and links, as well as a map showing the independent Statewide Collaborative members. Activity to continue into 2015-2016 work plan.
| 2015-03-31 | P | P | P | Continue to communicate with all independent Statewide Collaboratives to collect information regarding their maintenance and sustainability, including tracking and evaluation of their progress, identification of lessons learned, best practices and pitfalls. Activity to continue into 2015-2016.
| 2015-03-31 | P | P | P | Provide monthly "virtual coaching" via "Office Hours" webinars for independent Statewide Collaborative members.
| 2015-03-31 | P | P | P | Produce three webinars/webcasts on educational topics related to Collaborative sustainability and post to Gold STAMP website.
| 2015-03-31 | P | P | P | Begin to document a Gold STAMP model for potential application to other areas. Activity to continue into 2015-2016.
7002 |  |  |  |  | Project Name: Population Health Improvement Program (PHIP) Division Lead: OPCHSM Team Lead: Lisa Ullman, Alejandra Diaz Description: Regional PHIP contractors will convene stakeholders and provide a neutral forum for identifying, sharing, disseminating and helping implement best practices and strategies to promote population health and reduce health care disparities. |  | In Progress
| 2014-08-22 | P | P | P | Release draft RFA with established project details and parameters
| 2014-10-17 | P | P | P | Deadline for applications
| 11/1/14 11/21/14 12/5/14 | P | P | P | Awards made announced
| 2014-12-01 | 8 | 8 | 8 | Contract start date
| 1/9/15 1/23/15 | P | P | P | Orientation session for contractors
| 1/31/14 1/31/15 6/1/15 8/1/15 9/1/15 10/15/15 1/15/16 2/15/16 3/15/16 5/15/16 | 8 | 8 | 8 | Finalize contracts (effective 12/1/14 1/15/16 2/15/16 3/15/16, 5/15/16)
7003 |  |  |  |  | Project Name: Improve Fair Hearing Process Division Lead: Division of Long Term Care (for now) Team Lead: Mark Kissinger Hope Plavin and Margaret Willard Additional Staff: Maria Vidal Description: Consider the possibility of a targeted increase in resources to handle the move to mandatory enrollment in managed long term care or other care coordination models. Providers should receive notice of fair hearings requested by their clients. Ongoing training for ALJs pertaining to state law, rules, and regulations should be evaluated. Consumers and plans should have input and access to the training. The target timeframe for fair hearing resolution should be within 60 days of the request for the hearing. Regulations should be amended to require documented receipt of written notice of fair hearings to CCM administrators of record or legal counsel. |  | Completed - May 2015
| 2012-03-08 | P | P | P | Develop internal DOH/OTDA team
| 2012-03-20 | P | P | P | First meeting of State team
| 7/1/12 7/9/12 8/17/12 | P | P | P | First draft of expenditure plan for budget investment
| 8/1/12 9/5/12 9/12/12 9/26/12 11/7/12 | P | P | P | Secure approvals for Expenditure plan
| 10/1/12 10/15/12 12/15/12 3/1/13 5/1/13 7/1/13 9/1/13 12/1/13 2/1/14 | 8 | 8 | 8 | Hold internal/external stakeholders meeting on improvements
| 12/1/12 12/15/12 2/15/13 5/1/13 7/1/13 10/1/13 11/1/13 2/1/14 | 8 | 8 | 8 | Hold 2nd meeting
| 12/31/12 1/15/13 5/1/13 7/1/13 10/1/13 12/1/13 1/1/14 | 8 | 8 | 8 | Develop template for reform measurement
| 2014-09-01 | P | P | P | Revision to Standardized fair hearing notices for MLTC and MMC including conferencing with stakeholders.
| 11/1/14 1/1/15 3/1/15 | P | P | P | complete revisions to notices
| . | P | P | P | implement enhanced OTDA communication with MLTC and MMC plans regarding requests and notification
| 2014-10-15 | P | P | P | Train existing and new ALJs on MLTC and FIDA
| 11/15/14 1/15/15 3/15/15 | P | P | P | Meeting with OTDA, DOH DLA and program staff to review and discuss new standardized notices.
| 12/1/14 2/01/15 4/1/15 | P | P | P | Rollout notices and train MLTC and MMC plans on proper use of standardized notices
7004 |  |  |  |  | Project Name: Foster Care Readiness to Transition to Managed Care Division Lead: OHIP and OCFS Team Lead: Lana Earle, Anna Dean Additional Staff: Lisa Fiato, Pat Higgins, Charles Asinor, Julie Harris Description: Procure Entities to Collect FC Utilization Data, Provide Managed Care Readiness Training and Assess Infrastructure/Technology needs of Voluntary FC Agencies, Training for FC Agencies to HH Care Managers |  | In Progress
ARTICLE 7 CONTRACTING/PROCUREMENT ACTIVITIES
| July | ü | ü | ü | Set-up weekly meetings with DOH and OCFS
| July | ü | ü | ü | Explored procurement options with DOH procurement staff - Use IPRO contract via statutory approval related to transition of special populations to MC
| August | ü | ü | ü | Draft and finalize descriptions of 3 activities for IPRO
| 10/1/14 10/31/14 | ü | ü | ü | Secure contract with IPRO
ACTIVITY 1: COLLECT FOSTER CARE UTILIZATION DATA FOR MC PREMIUM AND FC PER DIEM RATE DEVELOPMENT
| 10/1/14 11/31/14 | ü | ü | ü | Rate setters meet with Vendor to review components of study
| 10/1/14 to 12/31/14 12/31/14 to 2/1/15 5/1/15 2/2/15 to 5/16/15 | ü | ü | ü | Vendor conducts study collects data
| 2/1/15 5/1/15 5/29/15 7/13/15 8/14/15 | ü | ü | ü | Review contractor's final report on data collection and time and motion study
| 2/1/15 3/1/15 5/29/15 6/12/15 7/15/15 8/21/15 10/30/15 | ü | ü | ü | Share data collection results with MC Rate setters to build premium
ACTIVITY 2: PROVIDE MC READINESS TRAINING ASSESS INFRASTRUCTURE/TECHNOLOGY NEEDS
| 10/1/14 12/31/14 10/1/14 to 1/31/14 1/1/15 to 4/27/15 3/27/15 3/1/15 | ü | ü | ü | DOH and OCFS work with IPRO to develop training materials and set dates and locations, vendor begins to assess infrastructure and technology needs
| 1/1/15 6/1/15 2/1/15 to 5/31/15 3/1/15 to 6/5/15 6/30/16 | ü | ü | ü | IPRO conducts trainings to foster care agencies CTAC (McSilver Institute) conducts trainings to foster care agencies (web-based and in person).
| 2/1/15 4/1/15 | ü | ü | ü | IPRO evaluate and submit recommendation for foster care agency technical readiness needs CTAC (McSilver Institute) evaluate provider technical assistance readiness assessments
| 2/1/15 11/1/14 to 1/1/15 3/1/15 4/1/15 5/1/15 | ü | ü | ü | DOH and OCFS develop methodology to distribute funds to agencies for assessed technical readiness needs
| 6/1/15 7/1/15 7/31/16 | 8 | 8 | 8 | DOH and OCFS collect information tracked by IPRO of training outcomes
| 2016-06-01 | 8 | 8 | 8 | Distribute VFCA MC Readiness Funds
| 2016-08-15 | 8 | 8 | 8 | Receive final spending reports from VFCAs for MC Readiness funds
ACTIVITY 3: TRAIN VOLUNTARY FOSTER CARE AGENCIES TO BE HH CARE MANAGERS FOR FOSTER CARE CHILDREN
| 10/1/14 1/1/15 2/13/15 3/1/15 3/27/15 4/27/15 | ü | ü | ü | DOH and OCFS work with IPRO to develop training materials and set dates and locations
| thru 12/31/14 thru 5/31/14 thru 8/1/15 thru 12/18/15 | ü | ü | ü | Schedule and Conduct Trainings, Evaluate Training Outcomes
7005 |  |  |  |  | Project Name: Program Integrity - FAS for SE Income Reviews Division Lead: DEMI Team Lead: Diane Farrell Additional Staff: Mary Lisa Description: Achieve savings through procurement with firm employing tax specialists, certified accountants and/or forensic accountants to evaluation whether of self employment related data and/or documentation used to obtain Medicaid coverage for information that appears questionable or suspect. | NA Note: Savings not realized until SFY 2015-16. Implementation cost to be offset by cost avoidance savings for a net estimated state savings of $1M annually beginning in SFY 2015-16. | Completed - Jan 2016
| 11/14/14 1/16/15 | P | P | P | Post procurement on website Begin Discussion with OMIG staff about development of an evaluation process.
| 2015-04-10 | 8 | 8 | 8 | Selection of contractor
| 2015-05-08 | 8 | 8 | 8 | Contract award/execution
| 6/1/15 7/31/15 11/30/15 | P | P | P | Work with contractor OMIG to develop pre-set evaluation and sampling criteria based on test criteria to ensure complete and consistent reviews
| 6/30/15 7/31/15 | P | P | P | Contractor Develop 1st universe of cases and select 1st test sample
| 9/15/15 11/30/15 | P | P | P | Contractor Complete initial reviews of 1st test sample; when needed, contact consumers to request supplementary SE data; conduct supplementary reviews after data is provided; and report results to the Department for further action.
| Ongoing until contract expires | P | P | P | Contractor Continue to conduct review activities and report results to the Department for further action.
7006 |  |  |  |  | Project Name: Basic Health Program Essential Plan Division Lead: DEMI Team Lead: Judy Arnold Additional Staff: Kathleen Johnson Description: Add the Basic Health Program as a new health insurance option. | $1B | Completed - Jan 2016
| 2014-08-30 | P | P | P | Discuss implementation plan with CMS
| 2014-12-31 | P | P | P | Decide program details (e.g., benefits, cost-sharing)
| 2015-02-28 | P | P | P | Develop NYSOH system requirements for BHP
| 2015-04-01 | P | P | P | Implement phase one - move some Medicaid enrollees into BHP
| 2015-04-15 | P | P | P | Release plan invitation for BHP plans
| 8/15/15 8/20/15 | P | P | P | Select BHP plans
| 9/1/15 10/1/15 | P | P | P | Implement system changes to add BHP to NYSOH
| 11/1/15 | P | P | P | BHP fully implemented for 2015 open enrollment
7007 |  |  |  |  | Project Name: Preschool/School Supportive Health Services (SSHSP) Cost Study and Certified Public Expenditure (CPE) Implementation - NYCDOE Division Lead: DPDM Team Lead: Constance Donohue, Cris Carter Description: Increase federal Medicaid funding by determining actual costs incurred by school districts and counties providing SSHSP services including transportation; implement certified public expenditure (CPE) reimbursement methodology. |  | In Progress
| 12/2013 | P | P | P | Federal Public Notice - preserving retroactivity to 9/1/2013 filed
| 4/06/15 | P | P | P | Kick-off meeting with NYCDOE
| 5/13/15 | P | P | P | Follow-up meeting with NYCDOE
| 5/15/15 5/22/15 | P | P | P | Pre-payment reviews (speech services) in progress - NYCDOE-school age
| 4/13/15 | P | P | P | Pre-payment reviews (all services being billed) in progress - NYCDOE-preschool (claims will be pended once NYCDOE obtains a separate MMIS provider number for preschool services)
| 5/15/15 5/22/15 7/27/15 | P | P | P | Re-submit draft SPAs to CMS
| 10/27/15 1/29/16 2/29/16 4/30/16 | 8 | 8 | 8 | Receive CMS Response to DOH

## Ph 4 Supportive Housing
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7101 |  |  |  |  | Project Name: Olmstead Subsidy Program Division Lead: Division of Long-Term Care Team Lead: Mark Kissinger, Rebecca Corso, Denard Cummings, Emily Engel, Rachel Baron-VanCleve Description: Funding will support $5 million of provide rental subsidy to high cost Medicaid enrollee's that participate in MLTC/FIDA for those who are enrolled in Medicaid, nursing home level of care as determined by the Uniform Assessment System (UAS), homeless or unstably housed, and who have spent at least one hundred and twenty (120) consecutive days in a nursing home over the most recent two year period. |  | In Progress
| 2014-07-16 | P | P | P | Develop draft RFA with establish project details and parameters
| 8/15/14 | P | P | P | Initiate B1184
| 8/25/14 10/9/14 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria
| 10/1/14 11/24/14 12/19/14 3/2/15 3/20/15 5/18/15 5/15/15 7/15/15 9/1/15 9/15/15 10/30/15 | P | P | P | RFA Posted to NYSDOH public website
| 2015-11-02 | P | P | P | Proposals due
| 12/14/15 12/31/15 | P | P | P | Complete internal review and scoring
| 1/25/16 2/15/16 3/25/16 | P | P | P | DOH internal approval
| 2016-04-15 | P | P | P | Obtain OSC approval
| 5/1/16 8/1/16 | 8 | 8 | 8 | Anticipated award release contract start date
7102 |  |  |  |  | Project Name: MRT Housing Tracking and Reporting System Division Lead: Division of Long-Term Care Team Lead: Mark Kissinger, Liz Misa, Rebecca Corso, Denard Cummings, Emily Engel Description: Funding will create a web-based tracking and reporting system for all MRT units. |  | Cancelled
| 2014-07-16 | P | P | P | Develop draft RFP with established project details and parameters
| 8/15/14 9/18/14 | P | P | P | Initiate B1184
| 8/18/14 9/16/14 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria |  | RFP is in EDCC approval process
| 2016-01-04 | 8 | 8 | 8 | Create sole source document and submit for EDC approval
| 2016-03-15 | 8 | 8 | 8 | Receive EDC and OSC approval
| 10/1/14 11/17/14 11/25/14 2/2/15 4/6/15 5/4/15 6/15/15 7/24/15 11/1/15 | 8 | 8 | 8 | RFA Posted to NYSDOH public website
Tracking will occur in exisiting software system
7103 |  |  |  |  | Project Name: MRT Evaluation Project Division Lead: Division of Long-Term Care Team Lead: Mark Kissinger, Liz Misa, Rebecca Corso, Denard Cummings, Emily Engel Description: Funding will support research and evaluation of current MRT programs |  | Complete - April 2016
| 2014-09-24 | P | P | P | Meet internally to develop project details and parameters for RFP
| 2014-10-01 | P | P | P | Develop draft RFP with establish project details and parameters
| 10/15/14 9/18/14 | P | P | P | Initiate B1184
| 10/20/14 11/3/14 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria
| 11/12/14 12/1/14 2/2/15 2/27/15 3/3/15 | P | P | P | RFA Posted to NYSDOH public website
| 2015-03-13 | P | P | P | Bidders questions due
| 3/27/15 4/10/15 4/15/15 | P | P | P | DOH responds to bidders questions
| 4/24/15 5/6/15 | P | P | P | Proposals due
| 5/8/15 6/12/15 | P | P | P | Complete internal review and evaluation of proposals
| 5/22/15 7/10/15 7/31/15 10/5/15 | P | P | P | DOH internal approval
| 10/29/15 12/18/15 2/1/16 3/25/16 | P | P | P | Obtain OSC approval
| 6/5/15 8/1/15 12/1/15 | P | P | P | Anticipated award release date
7104 |  |  |  |  | Project Name: Special-Needs Assisted Living Program (SN-APLS) Division Lead: Division of Long term Care Team Lead: Mark Kissinger, Rebecca Corso, Denard Cummings, Emily Engel Description: Funding will create a new assist in capital improvements and staff training SN-ALPS program for special populations that are high-cost Medicaid members who currently lack congregate care settings tailored to their needs. |  | In Progress
| 9/2/14 11/1/14 12/15/14 | P | P | P | Develop draft RFP with establish project details and parameters
| 9/10/14 9/18/14 | P | P | P | Initiate B1184
| 9/22/14 11/17/14 12/29/14 | P | P | P | Submit project to EDCC and BOC for approval of document and evaluation criteria
| 12/1/14 3/2/15 3/20/15 5/18/15 4/10/15 4/27/15 5/21/15 | P | P | P | RFA Posted to NYSDOH public website
| 2015-07-29 | P | P | P | Applications are due
| 8/28/15 9/18/15 10/5/15 11/30/15 | P | P | P | Complete internal review and evaluation of proposals
| 9/11/15 10/23/15 12/11/15 1/4/16 2/29/16 | P | P | P | DOH internal approval
| 12/10/15 2/1/16 4/22/16 5/13/16 | 8 | 8 | 8 | Obtain OSC approval |  | Component B has been approved by OSC
| 1/1/16 5/1/16 8/1/16 | 8 | 8 | 8 | Anticipated award release contract start date
7105 |  |  |  |  | Project Name: Access to Homes Division Lead: Liz Misa, Mark Kissinger, Rebecca Corso Team Lead: Denard Cummings, Emily Engel Description: Funding will be allocated to the HCR Access to Homes program to serve people with a disability and on Medicaid that need home modifications in order to live in the community. |  | Completed - June 2015
| 10/20/14 11/21/14 12/19/14 2/13/15 3/6/15 4/17/15 4/30/15 5/29/15 6/26/15 | P | P | P | Create a MOU with HCR |  | MOU approved, sending for signature to DHCR.
| 11/17/14 11/24/14 12/10/14 | P | P | P | HCR drafts RFP
| 2014-12-10 | P | P | P | RFP Posted on HCR's website
| 2015-02-13 | P | P | P | Applications received
| 5/4/15 5/14/15 | P | P | P | Awards made
7106 |  |  |  |  | Project Name: Expand and improve independent senior housing opportunities Division Lead: Division of Long Term Care Team Lead: Mark Kissinger Additional Staff: Paul Pfliegler Val Deetz Description: Address concerns about independent senior housing by: clearly defining independent senior housing in regulation; streamlining regulatory barriers to improve outcomes and achieve efficiencies; identifying resources to develop and preserve quality independent affordable housing for seniors that can serve as a platform for services to maximize their ability to be maintained in their homes and communities; and identifying new funding sources and new services from best practices in the supportive housing industry to support independent senior housing. |  | In Progress - Merged from #5715
| 2/1/14 | P | P | P | Create bi-monthly internal meetings
| 2/1/13 8/1/13 9/1/13 11/1/13 1/1/14 3/1/14 4/1/15 5/5/15 | P | P | P | Develop internal work plan
| 6/30/15 9/1/15 12/1/15 2/1/16 3/15/16 4/15/16 5/13/16 | P | P | P | Sending DAL letter clarifying independent senior housing regulations. (Task 1) |  | Pending OHSM. Reviewing OHSM letter is being revised Letter in signature process
| 2014-07-25 | P | P | P | Executed contracts with contractors for the following programs: Access to Homes and the two senior pilot programs, Senior Supportive Housing Services and Nursing Home to Independent Living. MRT Capital funds have and are being used to open new affordable senior housing (unregulated).
| 10/1/15 1/1/16 2/29/16 5/6/16 | 8 | 8 | 8 | Outreach to associations on barriers of senior housing.
| 10/1/12 4/1/13 8/1/13 10/1/13 12/31/13 4/1/14 9/1/15 | 8 | 8 | 8 | Coordinate, schedule and participate in stakeholder meeting

## Ph 4 Basic Benefit
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7201 |  |  |  |  | Project Name: Topical Oxygen Wound Therapy (TOWT) Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/Connie Donohue Additional Staff: Joan Sicard, Katherine Truby Description: Discontinue coverage of topical oxygen wound therapy due to lack of medical evidence | ($1.11) | Suspended - pending litigation
| 2/25/14 | P | P | P | Dossier submitted by GWR Medical
| 2/26/14 | P | P | P | Dossier sent to OHSU for review
| 3/17/14 | P | P | P | Contacted by governmental representatives regarding impact of coverage decision; referred to Office of Governmental Affairs (OGA) and DLA
| 3/25/14 | P | P | P | Dossier review completed by OHSU
| 3/28/14 | P | P | P | OHSU review shared with medical directors
| 5/1/14 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 5/1/14 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 6/9/14 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
|  | P | P | P | Provided a 30-day public comment period on MRT Dossier webpage
| 9/30/14 | P | P | P | Meet/share policy and billing guidance and applicable diagnosis and procedure codes with Managed Care Policy staff and Reimbursement staff.
| 10/1/14 | P | P | P | Received clearance to move forward from OGA
| 10/14/14 | P | P | P | Notified GWR of final decision following dossier review
| 10/15/14 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 10/16/14 | P | P | P | Meet/share policy and billing guidance and applicable diagnosis and procedure codes with Managed Care policy and planning group.
| 10/17/14 | P | P | P | Circulate Medicaid Update article for review/comments. Submit article for publication in October MA Update.
| 1/15/15 | 8 | 8 | 8 | Develop outcome metrics (Salient bookmark)
| 7/1/14 12/1/14 | 8 | 8 | 8 | Implement policy - 12/1/14 for FFS and 1/1/15 for MMC
7202 |  |  |  |  | Project Name: Eliminate Coverage of Viscosupplementation of the Knee for Osteoarthritis Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/ Connie Donohue Additional Staff: Donna Urban, Joan Sicard Description: Discontinue coverage of viscosupplementation of the knee for osteoarthritis | ($.99) | Completed - Feb 2015
| 1/7/14 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis codes and CPT/HCPCS procedure code(s) that apply.
| 1/7/14 | P | P | P | Discuss diagnosis editing needed.
| 1/7/14 | P | P | P | Identify systems impact/if changes are necessary to implement MRT.
| 1/29/14 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 2/20/14 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 3/25/14 | P | P | P | Meet/share policy and billing guidance and applicable diagnosis and procedure codes with Managed Care Policy staff and Reimbursement staff.
| 3/26/14 | P | P | P | Circulate Medicaid Update article for review/comments.
| 3/2014 | P | P | P | Publish Medicaid Update
| 2014-04-01 | P | P | P | Implement policy for both FFS and MMC.
| 11/14/14 11/28/14 2/10/15 | P | P | P | Develop outcome metrics.
7203 |  |  |  |  | Project Name: Tobacco Cessation by Dentists Division Lead: Greg Allen/Division of Program Development and Management Team Lead: Ron Bass/ Connie Donohue Additional Staff: Donna Haskin, Mark Tremblay Description: Expand the providers who can bill Medicaid for tobacco cessation counseling to include dentists | ($1.5) | Completed - Feb 2015
| 3/2014 | P | P | P | Prepare coverage guidelines to expand SCC to dental practitioners (an earlier MRT project expanded the populations covered for SCC)
| 3/2014 | P | P | P | Confer with DOH medical director(s) on coverage guidelines.
| 3/2014 | P | P | P | Meet/share policy and billing guidance and applicable diagnosis and procedure codes with Managed Care Policy staff and Reimbursement staff.
| 3/2014 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy.
| 3/2014 | P | P | P | Circulate Medicaid Update article for review/comments.
| 4/1/14 | P | P | P | Implement policy - April 1, 2014 FFS and July 1, 2014 for MMC
| 11/15/14 11/28/14 2/10/15 | P | P | P | Develop outcome metrics.

## Ph 4 Health Disparities (comp)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7301 |  |  |  |  | Project Name: Promote Hepatitis C Care and Treatment through Service Integration: Health Home Expansion Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Colleen Flannigan, Jackie Treanor, Frank Laufer, Ron Bass, Vida Wehren Description: Utilize health homes care coordination framework for eligible HCV infected Medicaid enrollees for client engagement, care coordination and peer education/support services. Expand Health home eligibility to include HCV mono infected population. |  | Cancelled Pending cancellation Keep as In progress. This project came from Ph 2. Merged from Phase 2
| 6/1/12 | P | P | P | Internal SDOH planning for steps needed to add remaining HCV population to Medicaid Health Homes for care coordination services and supports. The majority of HCV population is already on State health home assignment lists.
| 7/10/12 | P | P | P | Stakeholder meeting on HCV initiative planning.
| 9/1/12 | P | P | P | Develop recommendations to ensure newly HCV diagnosed population are also served through Health Home bottom up referrals for treatment decisions and engagement in care.
| 9/1/12-12/31/12 | P | P | P | Promote avenues for adding providers to Health Home networks experienced with providing HCV treatment and ancillary services: HCV support groups, HCV peer services, side effect management.
| 4/1/13 TBD | 8 | 8 | 8 | Develop proposal for HCV to be a single qualifying condition for Health Homes. | It is proposed HCV MRT expenditures will commence during 2013-14, in the form of a PMPM add on payment to managed care plans. This funding will be passed on to providers to incentivize HCV treatment programs in primary care setting, similar to the current PCMH initiative. Requires submission of a new SPA category of service to CMS. On hold until current HH identified population is implemented. Will not pursue Health Home for mono infected as per updated clinical guidance. The majority of HCV infected Medicaid identified populations qualify for health homes due to other morbidities.
7302 |  |  |  |  | Project Name: Social Determinants of Health: Division Lead: Office of Public Health Team Lead: Gus Birkhead Additional Staff: Barbara Dennison; Hope Plavin Description: Develop recommendations on how to best address the social determinants of health to promote health, improve wellbeing and decrease/reduce disparities due to social determinants, with a focus on issues related to employment. |  | Completed -New Work Group, Expansion Of Health Disparities Work Group from Phase 2
| 12/20/13 | P | P | P | Kick-off Meeting
| 1/10/14 | P | P | P | Identified and recruited co-chairs, Kristin Proud (ODTA) and Elizabeth Swain (CHCANYS)
| 2/15/14- 3/15/14 | P | P | P | Identified representatives for internal work group - DOL (Russell Oliver; Anthony Joseph), OMH (Gregory Miller; John Allen; Hextor Pablon); O Health Disparities (Kristen Pergolino); OCFS (Janice Molnar); OHIP, Medicaid Liz Misa);OPH, DCDP (Mycroft Sowizral)
| 3/14/14 | P | P | P | Meeting of internal work group to discuss charge; identify additional internal work group members.- OTDA (Barbara Guinn)
| 4/1/14 | P | P | P | Meeting to discuss potential topic areas for recommendations and begin to identify potential external work group members.
| 2014-04-21 | P | P | P | Meeting to discuss potential topic areas for recommendations and external work group members.
| 2014-05-01 | P | P | P | Meeting to discuss agenda for in-person meetings; Approve external work group members. Approve draft invitation. |  | Approved by OPH
| 2014-05-13 | P | P | P | Meeting to develop agenda and plan meeting; review external work group members.
| 2014-06-12 | P | P | P | Meeting to finalize agenda; review presentations; finalize external work group members.
| 2014-06-22 | P | P | P | Final planning meeting for July 7th meeting.
| 2014-07-07 | P | P | P | First Full Work Group Meeting, NYC, NY
| 2014-08-08 | P | P | P | Review progress of three sub-work groups
| 2014-08-27 | P | P | P | Review progress of three sub-work groups; Plan for September 12th meeting.
| 2014-09-12 | P | P | P | Second Full Work Group Meeting, Rensselaer, NY
| 2014-09-19 | P | P | P | Review progress of three sub-work groups
| 2014-10-03 | P | P | P | Review progress of three sub-work groups; Plan for October 10th meeting.
| 2014-10-10 | P | P | P | Third Full Work Group Meeting, NYC, NY
| 2014-10-11 | P | P | P | Summarize voting and priorities; Finalize Final Report |  | Approved by OPH
| 2014-11-05 | P | P | P | Final Recommendations (In Priority Order) |  | Posted on Website
|  | P | P | P | 1) Earned Sick Time
|  | P | P | P | 2) Advancing the Community Health Worker (CHW) Workforce to Improve Health Outcomes: |  | Communicated to DSRIP
|  | P | P | P | 3) Paid Family Leave Insurance
|  | P | P | P | 4) Advancing Community-Based Prevention
|  | P | P | P | 5) Advancing Additional Peer Specialist Positions
|  | P | P | P | 6) Strengthening Current Infrastructure |  | Referred to Employment First Commission
|  | P | P | P | 7) Development of Certified Peer Specialist – DSRIP
|  | P | P | P | 8) Disability Equity in State Contracting |  | Referred to Employment First Commission
|  | P | P | P | 9) Benefits Advisement and Web-Based Calculator: |  | Referred to Employment First Commission
|  | P | P | P | 10) Providing Transportation & Employment Opportunities |  | Referred to Employment First Commission
|  | P | P | P | 11) Regional Economic Development Councils (REDC)
|  | P | P | P | 12) Supported Employment/Education: |  | Referred to Employment First Commission

## Ph 4 Behavioral Health
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7401 |  |  |  |  | Project Name: Facilitating the Transition of BH Services for Adults and Kids into Managed Care Division Lead: OMH Team Lead: Gary Weiskopf Additional Staff: Pat Lincourt and Linda Kelly Description: Ensure adequate networks are in place prior to implementation of Managed Care by kick starting BH system readiness activities that promote Managed Care IT readiness and Managed Care Plan and Provider Technical Assistance. |  | In Progress
MANAGED CARE PROVIDER TECHNICAL ASSISTANCE
| 2014-06-01 | P | P | P | Execute contract with Managed Care Technical Assistance Center (MCTAC) to facilitate managed care technical assistance
| 2014-08-15 | P | P | P | Announce Managed Care Technical Assistance Series Kick-Off Events-- including foundational and implementation training (ongoing for 2 yrs.) |  | ongoing for 2 yrs.
| 2014-09-09 | P | P | P | Begin Managed Care Technical Assistance Series |  | ongoing for 2 yrs.
| 2016-02-17 | P | P | P | MCTAC Training for Rest of State Adult Behavioral Health Providers Schedule to Begin |  | We will insert specific training dates adults and kids
| 3/21/16-4/14/16 | P | P | P | Children's System Transformation Forums
| 2016-03-23 | P | P | P | UM and Billing Series for Rest of State and Long Island
| 2016-03-29 | P | P | P | NYS Adult Behavioral Health HCBS Authorization Webinar
| 2016-04-19 | P | P | P | Residential Redesign Learning Community
| Ongoing | 8 | 8 | 8 | Ongoing Managed Care Readiness Training and Learning Collaboratives |  | ongoing for 2 yrs
MANAGED CARE IT READINESS
| 9/1/14 11/26/14 1/15/15 2/1/15 | P | P | P | Finalize plan for allocation of IT readiness |  | Await stakeholder feedback on current HIT proposal
| 4/3/15 6/7/15 | P | P | P | Draft contract language |  | In progress
| 10/1/14 12/15/14 2/15/15 3/1/15 5/15/15 8/1/15 | P | P | P | Begin implementing IT readiness assistance in NYC | IT readiness assistance is ongoing. OSC has Approved single source contract with NYC Fund for Public Health Contract is in final negotiations with DOH and NYC Survey scoping out provider readiness has been released
REGIONAL PLANNING CONSORTIUMS
| 10/1/14 12/30/14 | P | P | P | Finalize regional RPC approach
| 1/1/15 3/1/15 5/30/15 | P | P | P | Implement RPCs in NYC
| 5/30/16-6/30/16 | 8 | 8 | 8 | ROS RPC Kick-off Meetings
| 7/1/15 8/1/15 5/1/16 8/1/16 | 8 | 8 | 8 | Implement RPCs in Rest of State
7402 |  |  |  |  | Project Name: Integration of Behavioral and Physical Health (Payment Increases for Integrated Clinic Care and Collaborative Care) Division Lead: DOH Team Lead: (OMH) Keith McCarthy, (DOH) Lana Earle, (OASAS) Trisha Schell-Guy Additional Staff: Description: To promote coordination of BH and PH services at the clinical, regulatory and financing levels. Collaborative care embeds basic behavioral health services in primary care settings. Integrated licensing allows certain providers to receive one license from either DOH, OMH, or OASAS and provide the full range of services that would have been allowed by any of the individual licenses. |  | Completed - Mar 2015 (Reflected in DSRIP WP)
[5 empty] | INTEGRATED LICENSING |  | Completed (Reflected in DSRIP Work Plan)
| 2013-03-15 | P | P | P | Begin approval of enhanced rates for year 1 integrated licenses
| 2015-04-01 | 8 | 8 | 8 | Expand access to integrated licenses
[5 empty] | COLLABORATIVE CARE |  | Complete
| 8/31/14 11/1/14 | P | P | P | Publish Federal public notice
| 9/2/14 11/1/14 | P | P | P | Finalize Medicaid Evolution Project Create rate codes to support collaborative care services to detect and treat depression
| 10/15/14 11/12/14 | P | P | P | Issue request for applications (RFA) to providers and begin issuing designations
| 2014-10-16 | 8 | 8 | 8 | Obtain DOB approval of rates
| 9/15/14 11/18/14 12/1/14 | P | P | P | Submit rate package to DOB
| 9/1/14 12/30/14 | P | P | P | DOH to submit SPA to CMS
7403 |  |  |  |  | Project Name: Targeted Vital Access Provider (VAP) program to preserve critical access to behavioral health inpatient and article 31 freestanding clinic services Division Lead: Office of Mental Health Team Lead: Bob Blaauw Additional Staff: Donna Cater, Mike Ogborn, Janet Baggetta Description: This initiative is intended to fund targeted investment areas that are critical to preserving and stabilizing needed capacity in the behavioral health service delivery system. |  | In Progress
INCREASE INPATIENT PSYCHIATRIC FEES
| 2014-07-01 | P | P | P | DOH issued notification of State's intent to expand rural status and increase psychiatric inpatient per diem base price by 10% for upstate hospitals effective July 1, 2014.
| 6/30/14 9/30/14 | P | P | P | Submit SPA to CMS for rural status expansion to upstate counties with population densities of 225 persons or fewer per square mile.
| TBD after SPA approval | 8 | 8 | 8 | DOH to submit rate package to adjust psychiatric inpatient per diem upon approval from CMS | This task is deleted because it was incorrectly placed in this section. Please see Inpatient Vital Access Provider Program tasks below for additional details.
INPATIENT VITAL ACCESS PROVIDER PROGRAM (VAP)
| on-going | P | P | P | Finalize review of Article 28 hospital VAP proposals
| 2014-09-30 | P | P | P | Submit SPA to CMS for St Joseph's Hospital-Elmira
| 2014-12-11 | P | P | P | Final TMRAA document and request for first payment to hospital submitted to DOH.
| 10/31/14 TBD | P | P | P | Submit SPA to CMS for Bassett Healthcare
| 2015-02-25 | P | P | P | Submit SPA to CMS for Oswego Hospital
| 2015-03-03 | P | P | P | Final TMRAA for first payment request to Bassett sent to DOH
| 2015-03-04 | P | P | P | Final TMRAA for first payment request to Oswego sent to DOH
| TBD After 1/27/16 | P | P | P | Submit SPA to CMS for United Health Services | Strategic Planners engaged with UHS to develop a proposal. F/U to take place with OMH 3/20/15
| 12/1/14 3/1/15 TBD Ongoing | 8 | 8 | 8 | Award VAP dollars to hospitals upon CMS approval | This is an on-going process, depending on when a provider's application is deemed acceptable. Bassett and Oswego have been receiving State-only payments since earlier this year. St. Joseph's-Elmira's SPA has been approved and has been receiving 100% payments since. Three hospitals; Basset, St. Josephs Arnot and Oswego are currently receiving the federal share of their VAP awards. CMS approved Basset's SPA on 9/1/15
CLINIC VITAL ACCESS PROVIDER (VAP)
| 9/15/14 11/1/14 | P | P | P | Develop VAP for Article 31 clinics
| 2014-11-04 | P | P | P | Emergency Regulations submitted to Department of State
| 2014-11-05 | P | P | P | Initial notice to providers sent
| 2014-11-13 | P | P | P | Mini-bid information to providers
| 2014-11-19 | P | P | P | Webinar for providers
| 2014-12-12 | P | P | P | Mini-bid applications due
| 1/9/15 1/20/15 | P | P | P | Proposals selected
| 2015-02-08 | P | P | P | Full application due from selected providers
| 2/28/15 10/1/15 1/27/16 | P | P | P | Issuance of Federal Public Notice and State Plan Amendment
| 3/1/15 10/1/15 TBD 3/1/16 | P | P | P | Initiate steps to make first payments
| 2016-05-01 | 8 | 8 | 8 | Clinics to receive payments
7404 |  |  |  |  | Project Name: OASAS Residential Restructuring Division Lead: Office of Alcohol and Substance Abuse Services Team Lead: Robert Kent Additional Staff: Pat Lincourt, Ilyana Meltzer, Henry Kurcman Description: This initiative is designed to restructure OASAS residential treatment to increase medical and clinical staff to allow for three elements of care including stabilization, rehabilitation and re-integration. |  | In Progress
| 2014-08-01 | P | P | P | Complete readiness tool to assist providers in transitioning to the new residential model
| 10/1/14-12/30/14 12/30/16 | P | P | P | Conduct Training | This is ongoing goal through 2016 March of 2015
| 9/1/14 12/15/14 4/15/15 5/1/15 | P | P | P | Finalize Rates | DOH has developed rates
| 9/1/14 12/15/14 1/15/15 | P | P | P | Finalize Billing Guidance Manual | Final managed care billing guidance has been released Final draft is under review
| 8/1/14 11/30/14 1/15/15 9/1/15 3/1/16 6/1/16 | 8 | 8 | 8 | Submit SPA | In process- pending finalizing rate methodology. Authorities will be given via 1115 waiver; state will submit corresponding SPA when children's SPA submitted Will be submitted by 3/1/16 for 1/1/16 effective date
| 1/30/15 7/1/15 10/1/15 1/1/16 Spring 2016 | 8 | 8 | 8 | Implementation of first programs | Implementation date consistent with NYC 10-1-15 begin date for BH carve-in. Implementation will be phased in based on provider readiness. State began working w NYC based programs and anticipates first program to be designated by Spring Jan 2016; and begin in rest of state by Fall 2016
7405 |  |  |  |  | Project Name: Health Home Plus for Assisted Outpatient Treatment (AOT) Division Lead: OMH Team Lead: Doug Ruderman Additional Staff: Lana Earle Description: To prepare discrete Health Home Plus operations and performance protocols for Health Homes to ensure appropriate legal and clinical accountability for enhanced Health Home care management to the highest acuity and need population. |  | Completed - Feb 2015
| 2014-04-01 | P | P | P | Submit rate package for DOB approval to fund program enhancements
| 2014-06-01 | P | P | P | Develop the standards for Health Home Plus
| 2014-08-01 | P | P | P | Obtain DOB approval of rate package
| 2014-08-01 | P | P | P | Issue guidance to Health Homes |  | posted to DOH/ OMH websites
| 2014-08-20 | P | P | P | Conduct webinar training on Health Home Plus to Health Home Care Managers and amend Administrative Services Agreement
| 2014-11-01 | P | P | P | Load HH Plus rate codes to Medicaid files |  | added new task
| 2015-01-01 | P | P | P | Expand to Criminal Justice population as part of revised BIP plan |  | added new task
7406 |  |  |  |  | Project Name: Funding New HARP HCBS Services Division Lead: OMH/OASAS Team Lead: Bob Myers Additional Staff: Robert Kent Description: To promote access to HARP HCBS benefit package offered through Health and Recovery Plans (HARPs). HARP HCBS services are designed to provide individuals with significant physical, behavioral and mental health needs, the resources and skills necessary to remain in the community. |  | Completed - April 2016 Changed 1915(i) to HARP HCBS
| 10/1/14 12/15/14 1/15/15 | P | P | P | Finalize plan to provide managed care readiness assistance to HARP HCBS providers
| 10/1/14 1/15/15 2/5/15 3/13/15 | P | P | P | Designate HARP HCBS providers in NYC
| 11/1/14 2/1/15 3/5/15 3/30/15 5/1/15 6/15/15 | P | P | P | Begin providing managed care readiness assistance to HARP HCBS providers | Letters to HCBS designated providers have been distributed notifying them of their start-up grant availability 7/18
| 4/1/15 6/30/15 10/1/15 11/1/15 12/1/15 1/15/16 | P | P | P | Designate HARP HCBS providers in rest of state
| 3/31/16 4/19/16 | P | P | P | Distribute Managed Care Readiness Assistance to Designated HCBS Providers in the rest of state

## Ph 4 Pharmacy (Complete)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014 -2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7501 |  |  |  |  | Project Name: Antiretroviral (ARV) Supplemental Rebates (SR) associated with the Ending AIDS Epidemic Initiative Division Lead: Greg Allen Team Lead: Tony Merola Additional Staff: Alan Ball, Nick Cioffi, Janet Elkind Description: Collect supplemental rebates on ARVs in order to cover 75% of the spend associated with “new” utilizing patients. | Estimated Total Spend/Cost of "new" AVR therapy = $265M. State Cost (25%) = $66.25. Supplemental Rebates (75%) = $198.75. | Merged - #8101
| 2014-03-05 | P | P | P | Present the initiative and supplemental rebate (SR) proposal to Pharmaceutical Manufacturers via conference call.
| 2014-05-01 | P | P | P | Meeting with each Pharmaceutical Manufacturer individually to discuss SR Proposal.
| 2014-04-11 | P | P | P | Overview of Ending AIDS initiative by AIDS Institute to Pharmaceutical Manufacturers.
| 2014-08-08 | P | P | P | Discuss initiative with the Medicaid Managed Care Plan (MCP) representatives.
| 2014-08-31 | P | P | P | Revise State Direct Contract (SDC) Revision to allow collection of SR on MCP data via State Direct Contract. |  | Undergoing internal review in preparation to send to DOB.
| 9/1/14 12/1/14 12/31/14 | P | P | P | Submit State Plan Amendment (SPA) to CMS.
| 9/1/14 12/15/14 12/31/14 2/28/15 3/31/15 5/15/15 | P | P | P | Reach conceptual SR agreement with Pharmaceutical Manufacturers that are willing to participate in the ARV SR program.
| 9/1/14 12/15/14 12/31/14 2/28/15 3/31/15 5/15/15 | P | P | P | Update Pharmaceutical Manufacturers regarding revisions to the SDC.
| 10/31/14 1/1/15 3/1/15 6/1/15 | P | P | P | Receive SPA approval from CMS. |  | Received CMS approval 5/8/15
| 11/15/15 1/30/15 3/15/15 6/15/15 | 8 | 8 | 8 | Convert conceptual agreement parameters for each Pharmaceutical Manufacturer into a SDC. |  | move to phase 5
| 12/1/14 4/1/15 7/1/15 8/1/15 | 8 | 8 | 8 | Receipt of SDCs from each participating Pharmaceutical Manufacturer. |  | move to phase 5
| 12/15/14 3/15/15 7/1/15 9/1/15 | 8 | 8 | 8 | Review of SDC financials and compare to conceptual agreement. |  | move to phase 5
| 1/1/15 4/1/15 7/1/15 10/1/15 | 8 | 8 | 8 | Execute SDC. |  | move to phase 5 Begin to accrue supplemental rebates on "new" utilization during 4Q15.
| 2/28/15 7/28/15 2/28/16 | 8 | 8 | 8 | Invoice Pharmaceutical Manufacturers for SRs. |  | move to phase 5 Invoice for 4Q15 identified as "new" associated with Ending AIDS initiative.
| 4/1/15 8/15/15 3/15/16 | 8 | 8 | 8 | Receipt of SRs from Pharmaceutical Manufacturers. |  | move to phase 5
PREPAID CAPITATION RATE
| 2015-10-01 | 8 | 8 | 8 | DOH/Mercer develops assumptions used to augment rates; share with plans |  | move to phase 5
| 2015-10-15 | 8 | 8 | 8 | DOH/Mercer develops draft rates; share with plans |  | move to phase 5
| 2015-11-01 | 8 | 8 | 8 | Plans provide feedback on assumptions/draft rates |  | move to phase 5
| 2015-11-15 | 8 | 8 | 8 | DOH/Mercer finalize rate adjustments |  | move to phase 5
| 2015-12-15 | 8 | 8 | 8 | Rates approved by DOB, CMS |  | move to phase 5
| 2016-01-01 | 8 | 8 | 8 | Rates loaded to the system |  | move to phase 5
POST IMPLEMENTATION
| 10/1/15 6/1/16 | 8 | 8 | 8 | Evaluate SR to determine financial impact. |  | move to phase 5
7502 |  |  |  |  | Project Name: Prior Authorization for Non-Medically Accepted Indications for Prescription Drugs Division Lead: Greg Allen Team Lead: Tony Merola Additional Staff: Alan Ball, Janet Elkind, Monica Toohey Description: Require verification of FDA or Compendia supported use for certain drugs or drug classes where there is significant "off-label" prescribing in order for coverage to be provided. | 9.9 | Completed - Oct 2014
| 2014-04-01 | P | P | P | Identify drugs/drug classes being utilized "off-label" (ongoing).
| 2014-04-01 | P | P | P | Presented the budget proposal to the managed care plans at the quarterly managed care plan (MCP) meeting held by the pharmacy department.
| 2014-06-12 | P | P | P | Presented a power point presentation outlining the project to the MCPs at the Managed Care Policy and Planning Meeting
| 2014-06-16 | P | P | P | Updated the Managed Care Plans on the Project.
| 2014-07-01 | P | P | P | Prepare reports for review by the Drug Utilization Review Board (DURB) as applicable.
| 2014-08-18 | P | P | P | Develop DURB agendas to include drugs/drug classes identified for significant "off-label" use. | September and November meetings scheduled for 2014. Next DURB meeting scheduled for November 20th; agenda posted October 20th. March 2015 DURB meeting TBD.
| 2014-09-18 | P | P | P | DURB Meeting - obtain recommendations from the DURB.
| 2014-10-01 | P | P | P | Provide utilization data (reviewed by the DURB) to Managed Care Plans.
| 2014-10-20 | P | P | P | DURB Meeting - obtain recommendations from the DURB. | Final Determinations associated with the September DURB meeting received 10/15/2014
| 11/1/14 12/11/14 | P | P | P | Implement prior authorization parameters to ensure drugs are being utilized for FDA or Compendia supported uses. | Implementation Date of December 11, 2014 - communicated via e-mail to stakeholders on November 3rd.
PREPAID CAPITATION RATE
|  | 8 | 8 | 8 | DOH/Mercer develops assumptions used to augment rates; share with plans
|  | 8 | 8 | 8 | DOH/Mercer develops draft rates; share with plans
|  | 8 | 8 | 8 | Plans provide feedback on assumptions/draft rates
|  | 8 | 8 | 8 | DOH/Mercer finalize rate adjustments
|  | 8 | 8 | 8 | Rates approved by DOB, CMS
|  | 8 | 8 | 8 | Rates loaded to the system
POST IMPLEMENTATION
| 2015-03-01 | P | P | P | Evaluate drug utilization for changes and fiscal impact.
7503 |  |  |  |  | Project Name: Align Pharmacy Copayments with Plan formularies Division Lead: Janet Zachary-Elkind Team Lead: Monica Toohey Additional Staff: Description: Enables managed care plans to align pharmacy copayments with their formularies, rather than with the Medicaid FFS preferred drug list. Will not change current pharmacy copayment structure. | N/A | Completed
ADMINISTRATIVE
| 2013-04-01 | P | P | P | Article VII legislation change/passing of executive budget
PROGRAM DEVELOPMENT
| 2014-04-01 | P | P | P | Presented the budget proposal to the managed care plans at the quarterly managed care plan meeting held by the pharmacy department.
| 2014-04-25 | P | P | P | Provided an email to the plans outlining the project and legislative language.
| 2014-05-01 | P | P | P | Managed care plans implemented the change.
7504 |  |  |  |  | Project Name: Align statewide Drug Utilization Review (DUR) programs by expanding point of sale clinical pharmacy editing in managed care plans (MCP) Division Lead: Janet Zachary-Elkind Team Lead: Monica Toohey Additional Staff: Tony Merola, Alan Ball Description: Further aligns statewide DUR programs by incorporating clinical pharmacy editing, to include consideration of non-pharmacy claims data elements such as diagnoses and/or relevant services. Customize PA criteria to target utilization concerns related to specific diagnoses, procedure codes etc. | 3.12M (State Share) | Completed - Oct 2014
PROGRAM DEVELOPMENT
| 2014-04-01 | P | P | P | Presented the budget proposal to the managed care plans at the quarterly managed care plan (MCP) meeting held by the pharmacy department.
| 2014-06-12 | P | P | P | Presented a power point presentation outlining the project to the MCPs at the Managed Care Policy and Planning Meeting
| 2014-07-01 | P | P | P | Presented the same power point presentation outlining the project at the quarterly managed care plan meeting held by the pharmacy department.
| 2014-08-15 | P | P | P | Provide the MCPs with supporting documentation on the fiscal estimate and clinical edits related to the proposal.
| 2014-10-01 | P | P | P | Implement enhanced clinical edits
PREPAID CAPITATION RATE
|  | P | P | P | DOH/Mercer develops assumptions used to augment rates; share with plans |  | Determined no change applied to the rate for this initiative.
|  | P | P | P | DOH/Mercer develops draft rates; share with plans
|  | P | P | P | Plans provide feedback on assumptions/draft rates
|  | P | P | P | DOH/Mercer finalize rate adjustments
|  | P | P | P | Rates approved by DOB, CMS
|  | P | P | P | Rates loaded to the system
POST IMPLEMENTATION
| 2015-01-01 | 8 | 8 | 8 | Monitor drug utilization data
7505 |  |  |  |  | Project Name: Tighten Early Fill Edit Division Lead: Janet Zachary-Elkind Team Lead: Monica Toohey Additional Staff: Description: Reduces stockpiling and waste that can occur based on current statute, where members may accumulate up to 90 days of medication over a one year period. The proposed claim edit will allow for accumulation of no more than ten days of medication at any given time. Prescribed changes in therapy, increased dose or changes in frequency will bypass the proposed early fill claims editing. Existing processes to “appeal” early fill edit will remain in place. | Savings in FY 2013-14 Enacted Budget | Completed - Jan 2015
ADMINISTRATIVE
| 2014-04-01 | P | P | P | Article VII legislation change/passing of executive budget
PROGRAM DEVELOPMENT
| 2014-04-29 | P | P | P | Submit Evolution project
| 2014-06-06 | P | P | P | Meeting held to detail functional requirements
| 2014-08-13 | P | P | P | Project assessment completed and approved
| 2015-01-22 | P | P | P | Project implemented
NOTIFICATIONS
|  | P | P | P | Develop and distribute Medicaid Update and communications with stakeholders
POST IMPLEMENTATION
|  | P | P | P | Monitor drug utilization data
7506 |  |  |  |  | Project Name: Eliminate ePrescribing Incentive Program Division Lead: DPDM Team Lead: Carol Lindley Additional Staff: Patty Keller Description: Discontinue payment of incentive to prescribers and pharmacies for each approved FFS Medicaid e-prescription. Pharmacy incentive of $.20 is paid at Point-of-Sale (POS) through claims processing; prescriber payment of $.80 is paid retroactively on a quarterly basis through EFT payment. |  | Completed - May 2014
| 2014-04-01 | P | P | P | Article VII legislation change/passing of executive budget
| 2014-04-08 | P | P | P | System change to end date pharmacy incentive payment of $.20 at POS effective 4/1/14
| 2014-04-09 | P | P | P | Develop and distribute Medicaid Update and communications with stakeholders
| 2014-05-05 | P | P | P | CMS Approval of SPA |  | Effective date of SPA: 4/1/14

## Ph 4 OMIG
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2014-2015 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
7601 |  |  |  |  | Project Name: Inappropriate Reserve Bed Payments Division Lead: Kevin Ryan Team Lead: Mary Kay Delgiacco Additional Staff: Daniel McAuliffe/Bede Edwards Description: HMS will review all bed reservations paid to 569 LTC facilities for a five year review period. These reviews will include a 24 month look back period. |  | In Progress
| 2014-09-29 | P | P | P | Facilities selected for Review.
| 2014-10-16 | 8 | 8 | 8 | Engagement letter and project plan to be approved by the OMIG.
| 2014-10-22 | P | P | P | Engagement letter and project plan to be approved by the OMIG.
| 2014-11-01 | P | P | P | HMS requested to extend audit period.
| 11/2/14 2/1/15 | P | P | P | Data analytics being repeated to account for the extended audit period.
| 11/1/14 12/1/14 3/1/15 | P | P | P | First engagement letters to be mailed to providers.
| 12/1/14 1/1/15 4/1/15 | P | P | P | Reviews to begin.
| 6/1/15 10/1/15 | P | P | P | Recoveries to begin.
| 2016-11-01 | 8 | 8 | 8 | Engagements to be completed.
| 2017-06-01 | 8 | 8 | 8 | Recoveries to be completed.
7602 |  |  |  |  | Project Name: OPWDD inappropriate services included in Rate Division Lead: Kevin Ryan Team Lead: Mary Kay Delgiacco Additional Staff: Bede Edwards Description: HMS will review claims inappropriately billed for OPWDD recipients for services included in their residential rates. |  | Completed
| 2014-01-30 | P | P | P | OPWDD has assumed responsibility for this initiative.
| 2014-01-30 | P | P | P | Process exists for recovery of inappropriate expenditures identified thru self-disclosure and audit process.
| 2014-11-14 | P | P | P | Recoveries are ongoing.
7603 |  |  |  |  | Project Name: Rx claims paid by Medicaid and Medicare Division Lead: Kevin Ryan Team Lead: Mary Kay Delgiacco Additional Staff: Daniel McAuliffe/Bede Edwards Description: Pharmacy claims paid by both Medicaid and Medicare will be identified and recovered. |  | Completed
| 2013-09-25 | P | P | P | File received from CMS of matched Medicaid Pharmacy claims with Medicare Part D duplicates.
| 2013-10-04 | P | P | P | CMS file sent to HMS. HMS in turn compared this file to recoveries they had undertaken prior to the receipt of the file.
| 2014-05-01 | P | P | P | HMS has issued probing mailings for those claims not previously identified by HMS as duplicates. (approximately 50)
| 2014-09-01 | P | P | P | The CMS data file is being reviewed for issues based on the lack of recoveries from the probing letters.
| 2014-04-08 | P | P | P | Recoveries are in process.
7604 |  |  |  |  | Project Name: Denied Claims Project Division Lead: Kevin Ryan Team Lead: Mary Kay Delgiacco Additional Staff: Loretta Ruperto, Bede Edwards Description: The purpose of this project is to identify partially denied Medicare claims that were crossed over from Medicare to Medicaid and were paid in full by Medicaid. |  | Completed
| 2014-09-30 | P | P | P | HMS has sent a data request to Safeguard Services (SGS).
| 2014-11-15 | P | P | P | SGS returns data request to HMS.
| 2014-11-16 | P | P | P | HMS returned data request to SGS for matching.
| 2/15/15 4/1/15 | P | P | P | HMS begins mailings on this project to providers.
| 6/1/15 8/1/15 | P | P | P | Recoveries begin on this project.
7605 |  |  |  |  | Project Name: UMASS County Demonstration Division Lead: Kevin Ryan Team Lead: Mary Kay Delgiacco Additional Staff: Karen Kruszeski, Sondra Rennick, Bede Edwards Description: The purpose of this project is to review dual Medicare/Medicaid eligibility for home health services to ensure Medicaid is the payer of last resort. | To date 4/1/14-10/16/14 UMASS has recovered $1,893,225.71. Target is $5.0 M Gross $2.5M State. | Completed
| 2014-09-30 | P | P | P | Reviews are proceeding.
| 2014-09-30 | P | P | P | Recoveries are in process.

## Boo-yah (hidden)
BOO-YAH!