## Ph 2 Program Streamlining
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 5/23/2018
5001 |  |  |  |  | Project Name: Develop and Implement Core Exchange Business Processes Division Lead: Exchange Staff Team Lead: |  | In Progress
Tasks to be implemented by Exchange Staff.
5002 |  |  |  |  | Project Name: Restructure Medicaid Financing Division Lead: Division of Health Reform and Health Insurance Exchange Integration Team Lead: Judy Arnold Additional Staff: DOB Description: Develop and implement a plan for more sustainable Medicaid financing that phases out reliance on local taxes (e.g., property taxes) and includes the examination of financing structures in other states. |  | Completed - Jan 2014
| 2012-04-01 | P | P | P | Fiscal Relief Enacted in Budget
| 2012-04-01 | P | P | P | Administrative cap enacted in budget
| 11/1/12 10/1/14 | P | P | P | Examine impact of county administrative cap
5003 |  |  |  |  | Project Name: Transition Medicaid Administration from Counties to the State Division Lead: Division of Health Reform and Health Insurance Exchange Integration Team Lead: Judy Arnold Additional Staff: Wendy Butz, Ralph Bielefeldt, Beth Osthimer Description: 5003A: Secure Legislative Authority and Resources 5003B: Identify Functions for Early State Administration and Implement 5003C: Centralize MAGI Eligibility Determinations |  | Completed - May 2018
5003A |  |  |  |  | Project Name: Transition Medicaid Administration from Counties to the State: Secure Legislative Authority and Resources Team Lead: Judy Arnold Additional Staff: Ralph Bielefeldt Description: |  | Completed - April 2013
| 2012-04-01 | P | P | P | Legislation Enacted
| 2012-04-20 | P | P | P | Develop staffing plan and contracting plan
| 2012-04-20 | P | P | P | Identify vacant items and submit waivers to fill positions
| 2012-04-30 | P | P | P | Develop process for streamlined contract amendments
| 2012-05-01 | P | P | P | Request Lists from Civil Service and canvass
| 2012-05-29 | P | P | P | Start recruiting/hiring staff
| 2012-06-30 | P | P | P | Develop new eligibility worker title and submit package to Civil Service
| 12/31/12 2/15/13 3/31/13 4/30/13 | P | P | P | Complete hiring
5003B |  |  |  |  | Project Name: Transition Medicaid Administration from Counties to the State: Identify Functions for Early State Administration and Implement Team Lead: Judy Arnold Additional Staff: Wendy Butz, Ann Volpel, Rita Zink, Peggy Williams Description: 5003B1 FPBP Applications 5003B2 Add Counties to Enrollment Center 5003B3 Resolve Death Matches 5003B4 Process Third Party Health Insurance 5003B5 Disability Determinations |  | Completed - June 2013
| 2012-03-15 | P | P | P | Identify functions the State can assume in 2012
| 2012-04-30 | P | P | P | Identify contract amendments required to implement
| 2012-05-01 | P | P | P | Develop separate work plans for each function identified
5003B1 |  |  |  |  | FPBP APPLICATIONS
| 2012-07-01 | P | P | P | Develop tool to receive and track applications from providers
| 2012-10-01 | P | P | P | Hire and train staff
| 11/1/12 12/10/12 | P | P | P | Begin processing FPBP applications
| 12/31/12 2/15/13 3/31/13 4/30/13 | P | P | P | Hire and train staff
SYSTEM UPDATES - CNS/WMS
| 2012-06-30 | P | P | P | Submit System Change Request for Central location and interfaces
| 2012-07-30 | P | P | P | Submit CNS Renewal Notice Changes
| 2012-09-01 | P | P | P | Finalize System Change Requests
| 11/1/12 12/10/12 | P | P | P | Begin processing FPBP applications
5003B2 |  |  |  |  | ADD COUNTIES TO ENROLLMENT CENTER
| 2012-08-15 | P | P | P | Confirm HEART functionality to process increased volume
| 2012-09-01 | P | P | P | Add 4700 monthly renewals for Enrollment Center processing
| 2012-10-01 | P | P | P | Hire new staff
| 2012-10-15 | P | P | P | Complete new staff training
| 2012-11-20 | P | P | P | Hire new staff
| 2012-12-01 | P | P | P | Add 4700 monthly renewals for Enrollment Center processing
| 2012-12-10 | P | P | P | Complete new staff training
| 2013-03-01 | P | P | P | Add 4700 3700 monthly renewals for Enrollment Center processing
5003B3 |  |  |  |  | RESOLVE DEATH MATCHES
| 2012-06-01 | P | P | P | Preliminary review of policy issues
| 2012-06-01 | P | P | P | Evaluate effectiveness of current automated closing process
| 2012-07-01 | P | P | P | Explore advantages / disadvantages of using NYS Vital Statistics data for automated closing process.
| 2012-08-01 | P | P | P | Explore changes to current matching process
| 10/1/12 11/15/12 12/1/12 12/31/12 2/15/13 3/31/13 4/30/13 | P | P | P | Hire new workers to close death match cases
| 11/1/12 12/1/12 12/15/12 | P | P | P | Finalize policy changes - if any
| 11/1/12 12/1/12 12/15/12 | P | P | P | Submit draft GIS for clearance
| 12/1/12 12/15/12 | P | P | P | Develop training module for new hires
| 12/1/12 12/15/12 12/28/12 1/31/13 2/28/13 4/1/13 | P | P | P | Issue GIS
| 1/2/13 2/1/13 3/1/13 4/1/13 | P | P | P | Begin resolution of death match case in some upstate counties
| 12/1/12 12/15/12 1/15/13 2/28/13 4/1/13 | P | P | P | Train new workers in correct closing process
5003B4 |  |  |  |  | PROCESS THIRD PARTY HEALTH INSURANCE
| 2012-04-30 | P | P | P | Define approach for state assumption of function
| 10/1/12 12/31/12 2/15/13 3/31/13 4/30/13 | P | P | P | Hire and train staff
| 11/30/12 2/22/13 4/29/13 6/16/13 | P | P | P | Execute contract amendment
| 3/1/13 4/01/13 5/28/13 6/30/13 | P | P | P | Begin processing TPHI for NYC (Applications with TPHI-FHP Premium Assistance Program)
DOWNSTATE SYSTEM UPDATES - CNS, WMS
| 2012-08-15 | P | P | P | Submit System Change Request - Central location ID/Issue Interfaces
| 10/31/12 11/30/12 1/7/13 1/15/13 2/15/13 | P | P | P | Submit CNS Notice Changes
| 10/31/12 11/30/12 1/15/13 1/21/13 3/1/13 | P | P | P | Finalize System Change Requests
5003B5 |  |  |  |  | DISABILITY DETERMINATIONS: STAGED TRANSITION OF DISABILITY DETERMINATIONS TO THE STATE DISABILITY REVIEW TEAM (SDRT)
| 6/30/12 | P | P | P | Submit amendment to increase physician T contracts to $49,000 for life of contract (currently at $39,000)
| 6/30/12 | P | P | P | Hire 2 new state staff
| 9/30/12 | P | P | P | First half of training complete
| 11/30/12 | P | P | P | Second half of training complete.
| 12/1/12 | P | P | P | Increase physician hours per amended T contracts
| 12/1/12 | P | P | P | Begin adding other county reviews (up to 200 additional cases/month)
5003C |  |  |  |  | Project Name: Transition Medicaid Administration from Counties to the State: Centralize MAGI Eligibility Determinations Division Lead: Team Lead: Judy Arnold Additional Staff: Beth Osthimer, Wendy Butz Description: |  | Completed - May 2018
| 2012-03-15 | P | P | P | Obtain staff and contract/hiring flexibility in enacted Executive Budget
| 10/1/12 12/15/12 7/1/13 1/1/14 | P | P | P | Obtain staff and contract/hiring flexibility in enacted Executive Budget
| 2012-11-01 | P | P | P | Complete policy decisions
| 12/30/12 7/1/13 9/1/13 9/30/13 | P | P | P | Determine local districts that will continue to process assist with MAGI applications and for how long
| 7/1/13 9/1/13 9/30/13 | P | P | P | Hire staff for central processing unit
| 7/1/13 9/1/13 9/30/13 | P | P | P | New eligibility system with MAGI rules engine is operationally ready
| 8/1/13 9/1/13 9/30/13 | P | P | P | Complete business processes for application processing, referrrals, special handling, etc
| 2013-09-30 | P | P | P | Complete staff training
| 2013-10-01 | P | P | P | Begin processing MAGI applications
| Sub Proj Index for 5003C |  |  |  | Project Name: Transition Medicaid Administration from Counties to the State: Centralize MAGI Eligbility Determinations Team Lead: Judy Arnold Additional Staff: Beth Osthimer, Wendy Butz Description:
|  | P | P | P | 5003C1 Centralize MAGI Eligibility Determinations
5003C2 Transition all new applications for MAGI groups from LDSS to Marketplace (retroactive eligibility-newborns)
5003C3 Transition all new applications for MAGI groups from LDSS to Marketplace (PE-inmates-FPBP)
|  | P | P | P | 5003C4 Administrative renewal for Marketplace enrollees through Exchange
5003C5 Renewal of MAGI Medicaid enrollees transitioned from WMS to the Marketplace
5003C6 Improve eligibility Worker interface
5003C7 Improve consumer interface
5003C8 Enhance data matching and program integrity
5003C9 Improve assistor interface
5003C10 Centralize non-MAGI eligibility determinations
|  | P | P | P | 5003C10 Spanish online Application
5003C1 |  |  |  |  | CENTRALIZE MAGI ELIGIBILITY DETERMINATIONS
| 2012-03-15 | P | P | P | Obtain staff and contract/hiring flexibility in enacted Executive Budget
| 10/1/12 12/15/12 7/1/13 1/1/14 | P | P | P | Obtain staff and contract/hiring flexibility in enacted Executive Budget
| 2012-11-01 | P | P | P | Complete policy decisions
| 12/30/12 7/1/13 9/1/13 9/30/13 | P | P | P | Determine local districts that will continue to process assist with MAGI applications and for how long
| 7/1/13 9/1/13 9/30/13 | P | P | P | Hire staff for central processing unit
| 7/1/13 9/1/13 9/30/13 | P | P | P | New eligibility system with MAGI rules engine is operationally ready
| 8/1/13 9/1/13 9/30/13 | P | P | P | Complete business processes for application processing, referrrals, special handling, etc
| 2013-09-30 | P | P | P | Complete staff training
| 2013-10-01 | P | P | P | Begin processing MAGI applications
5003C2 |  |  |  |  | TRANSITION ALL NEW APPLICATIONS FOR MAGI GROUPS FROM LDSS TO MARKETPLACE (RETROACTIVE ELIGIBILITY-NEWBORNS)
| 4/30/14 6/30/14 8/29/14 | P | P | P | Develop business requirements for system
| 4/30/14 6/30/14 8/29/14 | P | P | P | Develop business requirement for cusomer service
| 4/30/14 6/30/14 8/29/14 | P | P | P | Define system changes
| 5/1/14 7/1/14 9/1/14 | P | P | P | Finalize/submit Systems Change Request
| 7/1/14 9/30/14 | P | P | P | Systems Testing begin
| 7/1/14 9/1/14 | P | P | P | Submit draft ADM for clearance
| 6/1/14 9/1/14 | P | P | P | Submit Medicaid Update article for clearance
| 8/1/14 11/1/14 | P | P | P | M-TAG call for LDSS
| 8/15/14 12/1/14 2/1/15 4/1/15 4/23/15 7/31/15 10/1/15 1/1/16 3/31/16 5/17/16 6/27/16 | P | P | P | Systems testing completed (retroactive elig-done) newborns testing to be completed - Upstate
| 7/11/16 9/5/16 10/31/16 1/31/17 3/1/17 6/30/17 10/1/17 12/31/17 | P | P | P | Systems testing completed (retroactive elig-done) newborns testing to be completed - NYC
| 8/15/14 12/1/14 2/1/15 5/1/15 7/31/15 | 8 | 8 | 8 | Issue ADM
| 7/30/14 11/30/14 2/1/15 | 8 | 8 | 8 | Issue Medicaid Update article
| 9/1/14 1/1/15 | 8 | 8 | 8 | Implement system changes
| 7/30/14 11/30/14 8/1/15 | P | P | P | Begin development of a pilot project to transition MAGI enrollees from WMS to Marketplace
| 9/1/15 10/1/15 12/1/16 3/1/16 | P | P | P | Define system requirements
| 10/1/15 2/28/16 3/31/16 | P | P | P | Finalize/submit Systems Change Request
| 10/1/15 12/1/16 3/1/16 | 8 | 8 | 8 | Select a sample of 5,000 10,000 enrollees per month from Enrollment Center Counties
| 11/1/15 2/28/16 3/31/16 5/1/16 | P | P | P | Develop transition procedures
| 11/30/15 2/28/16 5/1/16 6/23/16 | P | P | P | Communicate to stakeholders
| 11/1/15 5/1/16 6/16/16 | P | P | P | System testing begins
| 11/30/15 6/15/16 6/16/16 | P | P | P | Systems testing complete
| 11/30/15 2/2/16 5/1/16 5/3/16 | P | P | P | M-TAG call for LDSS
| 2015-11-30 | 8 | 8 | 8 | Communicate to stakeholders
| 2016-08-31 | P | P | P | Transition 10,000 MAGI enrollees per month from Enrollment Center Counties for July and August”
| 1/31/2017 8/31/17 03/15/18 | P | P | P | Transition non-Enrollment Center Upstate MAGI enrollees
5003C3 |  |  |  |  | TRANSITION ALL NEW APPLICATIONS FOR MAGI GROUPS FROM LDSS TO MARKETPLACE (PE-INMATES-FPBP) INMATES DONE - EXCEPT RIKERS NYC |  | Suspended 5003 C5 merged with this section.
| 6/30/15 12/31/15 3/1/18 | 8 | 8 | 8 | Develop Rikers inmate interface system requirements
| 7/30/15 12/31/15 3/31/18 | 8 | 8 | 8 | Define system changes
| 8/30/15 12/16/15 4/15/18 | 8 | 8 | 8 | Finalize/submit Systems Change Request
| 9/15/15 1/15/16 6/1/18 | 8 | 8 | 8 | System development
| 10/1/15 8/1/18 | 8 | 8 | 8 | Systems Testing begin
| 11/1/15 9/15/18 | 8 | 8 | 8 | System defect resolution
| 12/31/15 10/15/18 | 8 | 8 | 8 | System implementation
| 12/15/15 8/1/18 | 8 | 8 | 8 | Communication to stakeholders
| 3/1/16 2/1/17 1/2/18 1/1/19 | 8 | 8 | 8 | Develop systems requirements for presumptive eligibilty
| 4/1/16 2/1/17 1/2/18 1/1/19 | 8 | 8 | 8 | Define system changes for presumptive eligibility
| 5/1/16 3/31/17 3/31/2018 | 8 | 8 | 8 | Finalize/submit Systems Change Request
| 6/1/16 4/1/17 4/1/18 | 8 | 8 | 8 | System development
| 7/1/16 7/15/17 7/15/18 | 8 | 8 | 8 | Systems testing begins
| 8/1/16 8/15/17 8/15/18 | 8 | 8 | 8 | System defect resolution
| 9/1/16 9/15/17 9/15/18 | 8 | 8 | 8 | System implementation
| 8/15/15 8/15/16 7/1/17 7/1/18 | 8 | 8 | 8 | Communication to stakeholders
| 8/1/14 11/1/14 2/1/15 | 8 | 8 | 8 | Develop business requirements for system
| 8/1/14 11/1/14 2/1/15 | 8 | 8 | 8 | Develop business requirement for customer service
| 8/15/14 11/15/14 3/1/15 7/30/15 | 8 | 8 | 8 | Define system changes
| 8/20/14 11/20/14 3/1/15 8/30/15 | 8 | 8 | 8 | Finalize/submit Systems Change Request
| 9/17/14 2/1/15 3/30/15 | 8 | 8 | 8 | Systems Testing begin
| 10/1/14 1/1/15 5/1/15 | 8 | 8 | 8 | Submit draft ADM for clearance
| 10/1/14 2/1/15 6/1/15 | 8 | 8 | 8 | Submit Medicaid Update article for clearance
| 10/15/14 2/15/15 6/15/15 | 8 | 8 | 8 | M-TAG call for LDSS
| 12/15/14 3/31/15 4/30/15 | 8 | 8 | 8 | Systems testing completed
| 12/15/14 2/1/15 6/1/15 | 8 | 8 | 8 | Issue ADM
| 12/31/14 3/31/15 6/1/15 | 8 | 8 | 8 | Implement system changes
| 1/15/15 3/1/15 6/1/15 | 8 | 8 | 8 | Issue Medicaid Update article
5003C4 |  |  |  |  | ADMINISTRATIVE RENEWAL FOR MARKETPLACE ENROLLEES THROUGH EXCHANGE
| 2014-06-01 | P | P | P | Complete review of policy issues around implementation in health exchange
| 2014-06-08 | P | P | P | Develop policies and procedures for implementation on HX.
| 2014-06-15 | P | P | P | Define system changes
| 6/17/14 7/1/14 9/1/14 | P | P | P | Finalize/submit Systems Change Request
| 7/14/14 9/15/14 | P | P | P | Development and coding of system changes completed
| 7/19/14 9/13/14 | P | P | P | Systems Testing begin
| 9/19/14 11/14/14 | P | P | P | Systems testing completed
| 2014-11-17 | P | P | P | Implement system changes
5003C5 |  |  |  |  | RENEWAL OF MAGI MEDICAID ENROLLEES TRANSITIONED FROM WMS TO THE MARKETPLACE |  | Merged with 5003 C2
| 6/1/14 12/1/14 | P | P | P | Complete review of policy issues around implementation in health exchange
| 6/8/14 1/1/15 3/1/15 5/31/15 8/1/15 | P | P | P | Develop policies and procedures for implementation on HX.
| 6/15/14 1/17/15 6/1/15 8/1/15 3/1/16 4/1/16 | 8 | 8 | 8 | Define system changes
| 6/17/14 2/1/15 8/1/15 3/1/16 4/30/16 | 8 | 8 | 8 | Finalize/submit Systems Change Request
| 7/1/14 2/1/15 8/1/15 3/1/16 6/15/16 | 8 | 8 | 8 | Submit draft ADM for clearance
| 7/1/14 2/1/15 8/1/15 5/1/16 8/15/16 | 8 | 8 | 8 | Submit Medicaid Update article for clearance
| 7/14/14 3/1/15 11/1/15 5/1/16 6/15/16 | 8 | 8 | 8 | Development and coding of system changes completed
| 7/19/14 11/1/15 5/1/16 8/1/16 | 8 | 8 | 8 | Systems Testing begin
| 8/1/14 11/1/15 5/1/16 7/31/16 | 8 | 8 | 8 | M-TAG call for LDSS
| 9/15/14 2/1/15 10/1/15 5/1/16 8/31/16 | 8 | 8 | 8 | Issue ADM
| 9/19/14 2/1/15 9/1/15 5/1/16 9/15/16 | 8 | 8 | 8 | Systems testing completed
| 10/1/15 2/8/15 10/1/15 6/1/16 10/15/16 | 8 | 8 | 8 | Implement system changes
| 10/15/14 2/1/15 11/1/15 6/1/16 9/15/16 | 8 | 8 | 8 | Issue Medicaid Update article
5003C6 |  |  |  |  | IMPROVE ELIGIBILITY WORKER INTERFACE
| 2014-04-22 | P | P | P | Complete requirement
| 5/1/14 | P | P | P | Finalize/submit Systems Change Request
| 5/30/14 12/1/14 3/1/15 1/1/17 1/1/18 7/1/18 | 8 | 8 | 8 | Development and coding of system changes completed
| 5/30/14 12/1/14 3/1/15 1/1/17 1/1/18 7/1/18 | 8 | 8 | 8 | Systems Testing begin
| 6/15/14 12/31/14 4/30/15 1/1/17 1/1/18 7/1/18 | 8 | 8 | 8 | Systems testing completed
| 6/30/14 1/15/15 5/15/15 1/1/17 1/1/18 7/1/18 | 8 | 8 | 8 | Implement system changes
5003C7 |  |  |  |  | IMPROVE CONSUMER INTERFACE
| 7/21/14 1/1/15 4/1/15 | P | P | P | Develop requirements for implementation on HX.
| 7/21/14 3/1/15 6/1/16 | P | P | P | Develop notices in alternative formats for visually impaired
| 7/28/14 12/31/15 6/30/15 | P | P | P | Solicit stakeholder feedback
| 8/11/14 12/31/15 6/30/15 | P | P | P | Define system changes and submit Systems Change Request
| 9/16/14 1/15/15 7/31/15 10/1/15 1/1/18 7/1/18 | 8 | 8 | 8 | Development and coding of system changes completed
| 9/16/14 1/15/15 8/15/15 11/1/15 1/1/18 7/1/18 | 8 | 8 | 8 | Systems Testing begin
| 12/20/14 2/1/15 3/30/15 8/15/15 12/1/15 1/1/18 7/1/18 | 8 | 8 | 8 | Systems testing completed
| 12/31/14 3/1/15 8/15/15 2/1/16 1/1/18 7/1/18 | 8 | 8 | 8 | Implement system changes
5003C8 |  |  |  |  | ENHANCE DATA MATCHING AND PROGRAM INTEGRITY
| 5/1/14 8/1/14 3/1/15 | P | P | P | Develop policies and procedures for implementation on HX. Death Match
| 5/16/14 8/16/14 6/1/15 8/1/15 8/1/16 4/1/16 | P | P | P | Define system changes
| 5/23/14 8/23/14 8/23/15 8/23/16 | P | P | P | Finalize/submit Systems Change Request
| 7/11/14 10/11/14 8/1/15 8/1/16 5/1/16 | P | P | P | Development and coding of system changes completed
| 7/11/14 10/11/14 9/1/15 9/1/16 6/1/16 | P | P | P | Systems Testing begin
| 9/19/14 9/28/15 9/28/16 8/1/16 | P | P | P | Systems testing completed
| 10/1/14 10/1/15 10/1/16 1/1/16 | P | P | P | Implement system changes
5003C9 |  |  |  |  | IMPROVE ASSISTOR INTERFACE
| 2014-10-08 | P | P | P | Define system changes and Systems Change Request
| 11/14/14 11/20/14 3/1/15 1/1/17 7/1/2017 | P | P | P | Development and coding of system changes completed
| 11/14/14 11/20/14 3/1/15 1/1/17 7/1/17 | P | P | P | Systems Testing begin
| 12/22/14 4/30/15 1/1/17 7/1/17 | P | P | P | Systems testing completed
| 12/30/14 6/30/15 1/1/17 7/1/17 7/28/17 | P | P | P | Implement system changes
5003C10 |  |  |  |  | CENTRALIZE NON-MAGI ELIGIBILITY DETERMINATIONS |  | Suspended
| 12/1/14 6/1/15 8/B213:B226/1/16 12/31/16 12/31/17 | 8 | 8 | 8 | Complete review of policy issues around implementation in health exchange
| 12/30/14 7/30/15 7/30/16 1/31/17 1/31/18 | 8 | 8 | 8 | Prioritize non-Magi rules for implementation
| 1/15/15 1/15/16 1/15/17 1/15/18 | 8 | 8 | 8 | Develop policies and procedures for implementation on HX.
| 2/15/15 2/15/16 2/15/17 2/15/18 | 8 | 8 | 8 | Define system changes
| 3/15/15 3/15/16 3/15/17 3/15/18 | 8 | 8 | 8 | Fianlize/submit Systems Change Request
| 8/15/15 8/15/16 8/15/17 8/15/18 | 8 | 8 | 8 | Development and coding of system changes completed
| 10/1/15 10/1/16 10/1/17 10/1/18 | 8 | 8 | 8 | Submit draft ADM for clearance
| 10/1/15 10/1/16 10/1/17 10/1/18 | 8 | 8 | 8 | Submit Medicaid Update article for clearance
| 11/1/15 11/1/16 11/1/17 11/1/18 | 8 | 8 | 8 | M-TAG call for LDSS
| 10/15/15 10/15/16 10/15/17 10/15/18 | 8 | 8 | 8 | Systems Testing begin
| 11/15/15 11/15/16 11/15/17 11/15/18 | 8 | 8 | 8 | Systems testing completed
| 11/15/15 11/15/16 11/15/17 11/15/18 | 8 | 8 | 8 | Issue ADM
| 12/1/15 12/1/17 12/1/18 | 8 | 8 | 8 | Implement system changes
| 12/15/15 12/15/16 11/15/17 12/15/18 | 8 | 8 | 8 | Issue Medicaid Update article
5003C11 |  |  |  |  | SPANISH ONLINE APPLICATION
| 6/1/14 8/1/14 10/1/14 | P | P | P | Obtain reference files for translation
| 7/1/14 9/1/14 10/15/14 | P | P | P | Translate application questions and static content from reference files
| 7/1/14 9/1/14 | P | P | P | Translate notices (Work in progress)
| 8/1/14 10/31/14 | P | P | P | Build translation into system
| 9/5/14 11/10/14 | P | P | P | Test System
| 9/15/14 3/1/15 1/31/15 7/31/15 | P | P | P | Test notices
| 9/30/14 12/1/14 | P | P | P | Deploy Spanish Application and notices
5004 |  |  |  |  | Project Name: Long Term Care Recommendations Division Lead: Division of Coverage and Enrollment Team Lead: Judy Arnold Additional Staff: Description: 5004A: Centralize and automate eligibility and enrollment processes for the Medicare Savings Programs. Rita Z 5004B: Expand Aged, Blind, and Disabled Automated Renewals 5004C: Asset Verification System (AVS) 5004D: Automate Spend Down 5004E: Address Vulnerable Population Consumer Assistance Needs 5004F: Long Term Care Work Group |  | Completed - April 2018
5004A |  |  |  |  | Project Name: Centralize and automate eligibility and enrollment processes for the Medicare Savings Programs. Division Lead: Division of Health Reform and Health Insurance Exchange Integration Team Lead: Wendy Butz Judy Arnold Additional Staff: Rita Zink, Margaret Williams, Wendy Butz Description: Centralize and automate eligibility and enrollment processes for the Medicare Savings Programs by January 2014. |  | Suspended
Phase 1 |  |  |  |  | PHASE I - EXPAND MSP RENEWALS AND UPSTATE AGED, BLIND AND DISABLED RENEWALS TO INCLUDE PENSION INCOME
POLICY AND PROCEDURE
| 5/31/12 | P | P | P | Meet with contractor - exceptions to MSP Auto renewal
Step |  |  |  |  | DOWNSTATE - SYSTEMS UPDATES - CNS, WMS, MBL, LOCAL DISTRICT INTERFACE FOR MSP AUTO RENEWALS
| 4/11/12 | P | P | P | Submit System Change Request for Mass rebudgeting
| 6/1/12 | P | P | P | Submit Systems Change Request for Auto Renewal Process
| 11/17/12 2/28/13 | P | P | P | Finalize SA for Mass Rebudgeting
| 6/1/15 | P | P | P | Complete review of policy issues around implementation in health exchange.
| 3/15/13 5/15/13 6/30/15 1/31/16 | 8 | 8 | 8 | Finalize SA Systems request for Auto Renewal Process
| 2/13/13 6/15/13 8/1/15 3/1/16 | 8 | 8 | 8 | Finalize testing complete WMS, MBL, and CNS
| 1/30/13 5/1/13 7/1/13 8/1/15 3/1/16 | 8 | 8 | 8 | CNS - Development/coding changes
| 2/1/13 5/1/13 7/1/13 8/15/15 3/15/16 | 8 | 8 | 8 | Finalize systems change requirements WMS, MBL
| 2/25/13 6/15/13 8/15/13 9/15/15 4/15/16 | 8 | 8 | 8 | User acceptance
| 6/1/13 7/1/13 8/31/13 10/1/15 5/1/16 | 8 | 8 | 8 | Implementation - / Auto Renewals QMB/SLIMB
| 6/1/13 7/1/13 8/31/13 10/1/15 5/1/16 | 8 | 8 | 8 | Implementation Contractor process exceptions to auto renewal
| 6/1/13 7/1/13 8/31/13 10/1/15 5/1/16 | 8 | 8 | 8 | Implementation - Auto renewals Ql 1
Step |  |  |  |  | DOWNSTATE - SYSTEMS UPDATES - CNS, WMS, MBL, LOCAL DISTRICT INTERFACE FOR ABD AND MSP AUTO RENEWALS WITH PENSIONS
| 06/01/16 | 8 | 8 | 8 | Complete review of policy issues
| 03/31/16 | 8 | 8 | 8 | Finalize SA request for Auto Renewal Process
| 05/01/16 | 8 | 8 | 8 | Finalize testing complete WMS, MBL, and CNS
| 05/01/16 | 8 | 8 | 8 | CNS - Development/coding changes
| 05/15/16 | 8 | 8 | 8 | Finalize systems change requirements WMS, MBL
| 06/15/16 | 8 | 8 | 8 | User acceptance
| 07/01/16 | 8 | 8 | 8 | Implementation - / Auto Renewals QMB/SLIMB
| 07/01/16 | 8 | 8 | 8 | Implementation - Auto renewals Ql 1
Step |  |  |  |  | UPSTATE SYSTEMS UPDATES - CNS, WMS, MBL, LOCAL DISTRICT INTERFACE
| 4/11/12 | P | P | P | Submit System Change Request for Mass rebudgeting
| 6/1/12 | P | P | P | Submit Systems Change Request for Auto Renewal Process
| 2/15/13 | P | P | P | Finalize SA for Auto Process Renewal
| 3/31/13 | P | P | P | CNS - Development/coding changes
| 3/31/13 | P | P | P | Finalize systems changes WMS, MBL
| 5/20/13 | P | P | P | Finalize testing complete WMS, MBL CNS
| 5/25/13 | P | P | P | User acceptance
| 6/1/13 | P | P | P | Implementation - Auto Renewals QMB/SLIMB with pensions and Aged, Blind and Disabled with pensions
| 6/8/13 | P | P | P | Implementation - Auto renewals Ql 1 with pensions and ABD with pensions
Phase 1A |  |  |  |  | PHASE IA - EXPAND MSP RENEWALS TO INCLUDE THOSE WITH A SPENDDOWN
POLICY AND PROCEDURE
| 9/01/13 12/1/15 12/1/16 1/1/18 | 8 | 8 | 8 | GIS Released
Step |  |  |  |  | SYSTEM UPDATES
| 4/11/12 | P | P | P | Submit System Change Request for Mass rebudgeting
| 6/1/12 | P | P | P | Submit Systems Change Request for Auto Renewal Process
| 6/30/12 | P | P | P | Submit CNS Mass Redbudgeting Notice Changes
| 8/1/15 8/1/16 1/1/18 | 8 | 8 | 8 | Complete review of policy issues around implementation in health exchange.
| 4/30/13 8/15/15 8/15/16 1/1/18 | 8 | 8 | 8 | Finalize/Submit System changes for Auto Re-budgeting/renewal process
| 4/30/13 8/15/15 8/15/16 1/1/18 | 8 | 8 | 8 | Finalize/Submit System changes for CNS renewal notice changes
| 4/1/13 9/1/13 8/30/15 8/30/16 1/1/18 | 8 | 8 | 8 | Submit System changes for CNS - Development/coding changes
| 5/1/13 10/1/13 9/15/15 9/15/16 1/1/18 | 8 | 8 | 8 | Finalize systems changes for Auto Renewal requirements
| 2/10/14 11/1/15 11/1/16 1/1/18 | 8 | 8 | 8 | Complete Testing for CNS renewal notices
| 2/10/14 11/1/15 11/1/16 1/1/18 | 8 | 8 | 8 | Complete Testing for Mass Rebudgeting
| 2/10/14 11/1/15 11/1/16 1/1/18 | 8 | 8 | 8 | Complete Testing for Auto Renewal process
| 5/25/13 2/15/14 11/15/15 11/15/16 1/1/18 | 8 | 8 | 8 | User acceptance
| 10/5/13 3/1/14 12/1/16 1/1/18 | 8 | 8 | 8 | Implementation - / Auto Renewals QMB/SLIMB
| 6/8/14 3/1/14 12/1/15 12/1/16 1/1/18 | 8 | 8 | 8 | Implementation - Auto renewals Ql 1
Phase 1B |  |  |  |  | IMPLEMENT MSP AUTOMATED RENEWAL ON THE HIX
| 6/1/15 6/1/16 1/1/18 | 8 | 8 | 8 | Define changes to existing renewal interfaces with HIX for implementation through HIX (i.e. EDITS, MRT, CHEM)
| 8/1/15 8/1/16 1/1/18 | 8 | 8 | 8 | Development/coding changes completed
| 11/1/15 11/1/16 1/1/18 | 8 | 8 | 8 | Unit Testing begin
| 12/1/15 12/1/16 1/1/18 | 8 | 8 | 8 | Unit testing completed
| 4/1/16 4/1/17 1/1/18 | 8 | 8 | 8 | Implementation - MSP automated renewal on the HIX
Phase 2 |  |  |  |  | PHASE II - AUTOMATE MSP MIPPA APPLICATIONS
Step |  |  |  |  | POLICY AND PROCEDURE
| 5/15/13 12/1/15 1/1/18 | 8 | 8 | 8 | ADM Issued
Step |  |  |  |  | SYSTEM UPDATES
| 7/31/12 | P | P | P | Submit Systems Change Request
| 9/30/12 12/31/12 8/1/15 8/1/16 1/1/18 | 8 | 8 | 8 | Submit Evolution Project Request (eMedNY)
| 2/8/13 9/1/15 10/1/15 10/1/16 1/1/18 | 8 | 8 | 8 | Identify & resolve outstanding application issues (LIS app info)
| 12/31/12 2/15/13 9/15/15 10/1/15 10/1/16 1/1/18 | 8 | 8 | 8 | Finalize/Submit System changes
| 10/30/12 12/31/12 2/28/13 9/15/15 10/1/15 10/1/16 1/1/18 | 8 | 8 | 8 | Finalize/Submit System changes for CNS renewal notice changes
| 4/30/13 10/1/15 10/1/16 1/1/18 | 8 | 8 | 8 | CNS - Development/coding changes
| 5/20/13 10/15/15 1/1/18 | 8 | 8 | 8 | Complete testing for CNS renewal notices
| 5/20/13 11/1/15 11/1/16 1/1/18 | 8 | 8 | 8 | Complete testing for System Changes
| 5/30/13 11/15/15 11/15/16 1/1/18 | 8 | 8 | 8 | User Acceptance
| 6/2/13 12/1/15 1/1/18 | 8 | 8 | 8 | Implementation
| 6/1/13 12/1/15 12/1/16 1/1/18 | 8 | 8 | 8 | Implementation Contractor process exceptions to auto renewal
Phase 3 |  |  |  |  | PHASE 3 - CENTRALIZE MSP ELIGIBILITY DETERMINATIONS
Step |  |  |  |  | ADMINISTRATIVE
| 5/14/12 | P | P | P | Meet with Contractor
| 8/1/12 | P | P | P | Execute Contract Amendment
| 10/1/12 | P | P | P | Identify/hire staff for oversight of Contractor process
| 2/15/13 7/30/15 7/1/16 1/1/18 | 8 | 8 | 8 | Hire and train staff for oversight process
POLICY AND PROCEDURES
| 1/1/13 3/1/13 10/1/15 1/1/18 | 8 | 8 | 8 | Policy and Procedures for staff completed
| 1/1/13 3/1/13 10/30/15 1/1/18 | 8 | 8 | 8 | Staff training complete
SYSTEM UPDATES
| 7/30/12 | P | P | P | Submit Systems Change Request
| 10/1/15 1/1/18 | 8 | 8 | 8 | Complete review of policy issues around implementation in health exchange
| 9/30/12 2/1/13 8/1/13 10/15/15 | 8 | 8 | 8 | Finalize/Submit System Changes for CNS notice changes
| 11/1/12 2/1/13 8/1/13 10/15/15 1/1/18 | 8 | 8 | 8 | Finalize/Submit System Changes
| 3/30/13 1/30/14 12/1/15 | 8 | 8 | 8 | Complete coding of CNS notice changes
| 4/30/13 4/30/14 1/15/16 1/1/18 | 8 | 8 | 8 | Complete coding of System changes
| 4/15/13 4/15/14 1/15/16 | 8 | 8 | 8 | Complete testing of CNS notice changes
| 5/15/13 5/15/14 1/15/16 1/1/18 | 8 | 8 | 8 | Complete testing of WMS/MBL System changes
| 3/1/13 5/30/13 12/01/13 5/30/14 2/1/16 1/1/18 | 8 | 8 | 8 | Implementation MSP Applications NYC
| 6/1/13 6/1/14 4/1/16 1/1/18 | 8 | 8 | 8 | MIPPA Exceptions Report goes to Contractor for manual processing
Phase 3A |  |  |  |  | EXPAND MSP RENEWALS - EXCEPTIONS TO AUTO RENEWALS
| 12/31/12 10/1/12 4/1/16 1/1/18 | 8 | 8 | 8 | Identify/hire staff for oversight of contractor process (Kalin Hold deleted here)
| 2/15/13 4/1/16 1/1/18 | 8 | 8 | 8 | ADM issued
5004B |  |  |  |  | Project Name: Expand Aged, Blind, and Disabled Automated Renewals Division Lead: Division of Health Care Reform and Health Insurance Exchange Integration Team Lead: Ralph Bielefeldt Judy Arnold Additional Staff: Wendy Butz Description: Expand Aged, Blind, and Disabled Automated Renewals to Include Pension Income and Spenddown Cases Note: ABD with pensions implemented upstate in June 2013. |  | Cancelled
POLICY AND PROCEDURE
| 9/15/13 5/1/15 5/1/16 1/1/18 | 8 | 8 | 8 | ADM issued
SYSTEM UPDATES
| 3/1/13 1/1/15 1/1/16 1/1/18 | 8 | 8 | 8 | Submit Systems Change Request
| 3/15/13 1/1/15 1/1/16 1/1/18 | 8 | 8 | 8 | Submit System change request for CNS renewal notice changes
| 8/15/13 3/1/15 3/1/16 1/1/18 | 8 | 8 | 8 | Complete CNS - Development/coding changes
| 9/1/13 4/30/15 5/30/16 1/1/18 | 8 | 8 | 8 | Finalize systems change
| 9/15/13 10/20/13 5/25/15 5/25/16 1/1/18 | 8 | 8 | 8 | HX testing complete
| 9/30/13 10/20/13 6/1/15 6/1/16 1/1/18 | 8 | 8 | 8 | User acceptance
| 10/6/13 10/22/13 6/1/15 6/1/16 1/1/18 | 8 | 8 | 8 | Implementation
5004C |  |  |  |  | Project Name: Asset Verification System (AVS) Division Lead: Division of Health Care Reform and Health Insurance Exchange Integration Team Lead: Ralph Bielefeldt Judy Arnold Additional Staff: Wendy Butz Description: The State should invest in an Asset Verification System (AVS) to permit the electronic verification of assets (including assets in the 5 year look back period) for determining eligibility for aged, blind, and disabled Medicaid applicants and recipients. AVS should be deployed as soon as possible in existing systems and this functionality should also exist in any new eligibility system. |  | Merged - Moved to Phase 8 #11001
| 6/1/12 | P | P | P | Analyze Requirements
| 11/1/12 12/1/12 2/15/13 5/1/13 6/15/13 6/21/13 7/12/13 8/9/13 10/1/13 10/15/13 | P | P | P | Select a contractor
| 11/15/12 12/15/12 2/15/13 5/15/13 6/15/13 6/21/13 7/12/13 8/9/13 10/1/13 | P | P | P | B1184 funding justification submitted to DOB for approval
| 12/1/12 1/1/13 3/15/13 6/1/13 7/1/13 7/15/13 8/15/13 8/23/13 10/15/13 11/1/13 12/2/13 1/15/14 3/12/14 | P | P | P | Start Negotiate negotiating contract and deliverables
| 1/1/13 2/1/13 4/1/13 7/1/13 7/31/13 8/31/13 11/15/13 11/30/13 12/31/13 2/1/14 4/16/14 7/1/14 9/1/14 10/1/14 12/1/14 | P | P | P | Contract approved (Executed, pending final processing)
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/18/16 2/8/16 | 8 | 8 | 8 | Develop programming specifications and deliverables. (System Change Request form submitted, pending approval)
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/8/16 2/8/16 3/31/16 | P | P | P | Develop LDSS training requirements
| 1/1/13 2/1/13 4/1/13 8/1/13 12/15/13 1/24/14 3/1/14 7/1/14 9/1/14 10/1/14 10/31/14 12/31/14 3/1/15 4/30/15 6/15/15 7/1/15 7/31/15 9/15/15 11/16/15 1/8/16 2/8/16 3/31/16 | P | P | P | Test programming
| 4/1/13 6/1/13 10/1/13 11/1/13 2/1/14 3/7/14 11/1/14 12/1/14 2/28/15 4/15/15 5/1/15 7/1/15 9/30/15 10/31/15 1/8/16 2/29/16 5/20/16 6/20/16 9/30/16 10/31/16 11/30/16 | P | P | P | ADM Issued for implementation statewide |  | Draft ADM was issued statewide on 11/14
| 8/1/13 10/1/13 11/1/13 12/1/13 3/1/14 4/1/14 12/1/14 1/1/15 4/1/15 6/1/15 7/1/15 8/15/15 9/30/15 12/15/15 1/29/16 2/29/16 | P | P | P | Train LDSS staff - pilot districts
| 8/1/13 10/1/13 11/1/13 12/1/13 3/1/14 4/1/14 12/1/14 1/1/15 4/1/15 6/1/15 8/15/15 9/14/15 10/19/15 1/11/16 2/1/16 3/7/16 | P | P | P | Implement AVS program - pilot districts
| 2017-03-28 | P | P | P | Train all districts - except NYC
| 2017-03-29 | P | P | P | Implement for applications - all districts except NYC
| 8/5/2017 10/17/17 11/10/17 | P | P | P | Implementation of renewals - all districts except NYC
| 2017-10-12 | P | P | P | Complete NYC Testing
| 8/1/2017 9/15/17 10/6/17 10/31/17 11/30/17 | P | P | P | Issue Final ADM
| 2017-10-23 | P | P | P | Implement NYC - Pilot phase - chronic care
| 10/30/17 10/31/17 | P | P | P | Train NYC staff
| 1/20/2018 2/28/2018 | P | P | P | NYC - Implement all non-spousal electronic nursing home applications
| 2018-03-30 | 8 | 8 | 8 | NYC - Implement all non-spousal electronic nursing home conversions
| 2018-06-29 | 8 | 8 | 8 | NYC - Implement all spousal electronic nursing home applications
| 2018-07-31 | 8 | 8 | 8 | NYC - Implement all spousal electronic nursing home conversions
| 2018-09-28 | 8 | 8 | 8 | NYC - Implement all manual nursing home applications and conversions
| 2018-11-30 | 8 | 8 | 8 | Implement all community SSI-related - NYC
| 2019-01-30 | 8 | 8 | 8 | Implement Renewals - NYC
5004D |  |  |  |  | Project Name: Automate Spend Down Division Lead: Division of Health Reform and Health Insurance Exchange Integration Team Lead: Wendy Butz Additional Staff: David Bacheldor Description: Automate spend down by linking eMedNY to WMS and using provider billing to track spend down similarly to an insurance deductible. In addition to streamlining spend down eligibility, the automation ensures that Medicaid is correctly paid. This spend down automation function should be deployed as soon as possible in existing systems and this functionality should also exist in any new eligibility system. |  | Cancelled
Step |  |  |  |  | POLICY AND PROCEDURE
| 5/31/12 | P | P | P | Complete review of policy issues
| 10/1/14 10/1/15 1/1/18 | 8 | 8 | 8 | Complete review of policy issues around implementation in health exchange
| 12/1/14 1/1/18 | 8 | 8 | 8 | Develop policies and procedures for implementation on HX.
| 3/13/13 9/30/12 1/1/15 1/1/18 | 8 | 8 | 8 | Submit draft ADM for clearance
| 12/1/12 5/1/13 1/1/15 1/1/18 | 8 | 8 | 8 | Submit Medicaid Update article for clearance
| 11/7/12 5/30/13 1/1/15 1/1/18 | 8 | 8 | 8 | M-TAG call for LDSS
| 12/10/12 6/1/13 2/1/15 1/1/18 | 8 | 8 | 8 | Issue ADM
| 2/1/13 6/1/13 2/1/15 1/1/18 | 8 | 8 | 8 | Issue Medicaid Update article
| 2/1/13 6/1/13 2/1/15 1/1/18 | 8 | 8 | 8 | Policy Manual and DOH website changes completed
| 2/1/13 6/1/13 2/1/15 1/1/18 | 8 | 8 | 8 | Information to Call Center (Qs&As) completed
Step |  |  |  |  | SYSTEM UPDATES
| 3/31/12 | P | P | P | Submit Systems Change Request
| 4/12/12 | P | P | P | Submit Evolution Project request (eMedNY)
| 12/1/14 12/1/15 1/1/18 | 8 | 8 | 8 | Submit project request to implement on health exchange
| 9/28/12 2/28/13 12/30/14 | 8 | 8 | 8 | DOH sign off Evolution Project Request
| 9/28/12 3/28/13 12/30/14 1/1/18 | 8 | 8 | 8 | Submit CNS notice changes
| 2/17/13 6/17/13 1/15/15 1/1/18 | 8 | 8 | 8 | Migrate system changes to production
| 3/1/13 7/1/13 2/1/15 1/1/18 | 8 | 8 | 8 | Roll out system changes to eMedNY
| 3/1/13 7/1/13 3/1/15 1/1/18 | 8 | 8 | 8 | Implementation Revised date pending eMed NY assessment
5004E |  |  |  |  | Project Name: Address Vulnerable Population Consumer Assistance Needs Division Lead: Division of Health Reform and Health Insurance Exchange Integration Team Lead: Gabrielle Armenia Additional Staff: Wendy Butz Description: Disabled and elderly New Yorkers in need of long term care services should have the same access to enrollment and eligibility assistance as other applicants for Medicaid. |  | Completed -April 2015
| 6/1/12 | P | P | P | Submit B1184 for Approval
| 9/20/12 12/28/12 | P | P | P | Receive approval for B1184
| 10/29/12 | P | P | P | Draft RFP
| 10/29/12 | P | P | P | Develop selection criteria for RFP
| 12/28/12 1/31/13 2/15/13 4/22/13 5/31/13 7/15/13 9/15/13 11/8/13 12/9/13 12/31/13 1/21/14 | P | P | P | Obtain InternalExecutive clearance for release of RFP
| 3/5/14 | P | P | P | Obtain approval of internet posting form
| 1/7/13 2/15/13 2/20/13 4/29/13 5/31/13 7/15/13 9/15/13 11/15/13 12/6/13 1/8/14 1/28/14 3/7/14 | P | P | P | Post RFP on DOH website
| 3/21/14 | P | P | P | RFA questions due
| 2/11/13 3/6/13 6/3/13 7/3/13 8/15/13 10/15/13 12/20/13 1/13/14 2/28/14 4/4/14 | P | P | P | Post responses to questions
| 3/18/13 4/1/13 6/21/13 7/21/13 9/1/13 11/1/13 1/27/13 2/7/14 4/25/1 5/19/14 | P | P | P | Proposal due date
| 4/29/13 7/17/13 8/17/13 10/1/13 12/1/13 2/28/14 3/7/14 3/19/14 4/9/14 5/16/14 6/6/07 | P | P | P | Review and score proposals
| 6/3/13 8/5/13 9/5/13 10/15/13 12/15/13 3/17/14 3/28/14 5/1/14 6/23/14 7/25/14 10/1/14 | P | P | P | Select successful contractor and obtain Executive Deputy Clearance approval
| 6/7/13 8/12/13 9/12/13 11/1/13 1/1/14 3/21/14 6/27/14 8/8/14 10/8/14 12/15/14 | P | P | P | Notify successful and unsuccessful bidders
| 6/28/13 8/26/13 9/26/13 11/15/13 1/15/14 7/14/14 8/8/14 10/31/14 1/31/15 3/31/15 | P | P | P | Negotiate contract with successful bidder
| 7/1/13 9/1/13 10/1/13 12/1/13 2/1/14 4/1/14 7/14/14 9/1/14 11/1/14 12/1/14 2/28/15 4/1/15 | P | P | P | Effective date for contract with successful bidder
5005 |  |  |  |  | Project Name: Improve Access to Emergency Medicaid Division Lead: DCE Team Lead: Kathleen Johnson Description: Improve Access to Emergency Medicaid |  | Completed - Feb 2016
PART 1
CLARIFY EMERGENCY MEDICAID APPLICATION PROCEDURES
POLICY AND PROCEDURE
| 2012-04-02 | P | P | P | Complete preliminary review of policy issues
| 2012-11-30 | P | P | P | Update Training Materials
| 2012-11-30 | P | P | P | Draft Medicaid Update Article for clearance
| 2012-11-30 | P | P | P | Draft Fact Sheet for Website for clearance
| 2012-12-30 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 2/1/2013 2/15/13 3/1/13 3/18/13 5/15/13 | P | P | P | Issue ADM GIS
| 2/15/13 3/1/13 3/18/13 5/15/13 6/30/13 8/30/13 | P | P | P | Issue Fact Sheet on Website
| 1/15/13 3/1/13 3/18/13 5/15/13 6/30/13 8/30/13 9/30/13 | 8 | 8 | 8 | Issue Medicaid Update Article
WEBSITE
| 2/15/13 3/15/13 3/18/13 5/15/13 6/30/13 8/30/13 9/30/13 | 8 | 8 | 8 | Post information about Emergency Medicaid
PART 2
PRE-QUALIFY MEDICAID FINANCIAL ELIGIBILITY
POLICY AND PROCEDURE
| 2012-04-02 | P | P | P | Complete preliminary review of policy issues
| 2012-04-03 | P | P | P | Explore the need for regulatory changes
| 2012-11-30 | P | P | P | Update Training Materials
| 2012-11-30 | P | P | P | Draft Medicaid Update Article for clearance
| 2012-11-30 | P | P | P | Draft Fact Sheet for Website for clearance
| 2012-12-30 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 1/15/13 2/15/13 3/18/13 5/15/13 6/30/13 8/30/13 9/30/13 11/30/14 11/30/15 | 8 | 8 | 8 | Issue Fact Sheet on Website
| 2/1/13 2/15/13 3/18/13 5/15/13 | P | P | P | Issue ADM GIS
| 2013-03-01 | P | P | P | Implement Changes
| 1/15/13 3/1/13 3/18/13 5/15/13 6/30/13 8/30/13 9/30/13 11/30/14 11/30/15 | 8 | 8 | 8 | Issue Medicaid Update Article
SYSTEM UPDATES
WMS/HEART
| 2012-03-01 | P | P | P | Explore necessary system changes
| 2012-04-02 | P | P | P | Submit System Change Request Form
| 2012-04-27 | P | P | P | Finalize system change requirements
| 2012-05-04 | P | P | P | Finalize System Action Request
| 2012-12-14 | P | P | P | Development/coding changes
| 2013-02-08 | P | P | P | Unit testing
| 2013-02-13 | P | P | P | User Acceptance
eMedNY
| 2012-07-01 | P | P | P | Explore need for emedNY evolution project to strengthen edits on emergency claims
| 2012-07-01 | P | P | P | Submit eMedNY evolution project (if necessary) Not necessary
| 2012-07-01 | P | P | P | Finalize eMedNY evolution project (if necessary) Not necessary
CNS
| 2012-07-01 | P | P | P | Explore CNS Notice Issues
| 2012-10-15 | P | P | P | Finalize and submit CNS notices (if necessary)
| 10/29/12 12/1/12 | P | P | P | Finalize System Action Request
| 2012-12-14 | P | P | P | Development/coding changes (if necessary)
| 2013-02-08 | P | P | P | Unit testing (if necessary)
| 2013-02-13 | P | P | P | User Acceptance (if necessary)
PART 3
IMPLEMENT 12 MONTH CERTIFICATION PERIOD FOR CERTAIN CONDITIONS
POLICY AND PROCEDURE
| 2012-04-02 | P | P | P | Complete preliminary review of policy issues
| 2012-04-03 | P | P | P | Explore the need for regulatory changes
| 2012-04-19 | P | P | P | Explore Federal requirements for statement from treating physician
| 2012-11-30 | P | P | P | Submit draft Medicaid Update article for clearance
| 2012-12-30 | P | P | P | Submit draft Administrative Directive (ADM) for clearance
| 2/1/13 2/15/13 3/18/13 5/15/13 | P | P | P | Issue ADM GIS
| 2/15/13 5/18/13 6/30/13 7/31/13 | P | P | P | Revise online Emergency Medicaid training for LDSS staff
| 1/15/13 3/1/13 3/18/13 5/15/13 6/30/13 8/30/13 9/30/13 11/30/14 11/30/15 | 8 | 8 | 8 | Issue Medicaid Update Article
SYSTEM UPDATES
WMS/HEART
| 2012-03-01 | P | P | P | Explore necessary system changes
| 2012-04-02 | P | P | P | Submit System Change Request Form
| 2012-04-27 | P | P | P | Finalize system change requirements
| 2012-05-04 | P | P | P | Finalize System Action Request
| 2012-12-14 | P | P | P | Development/coding changes
| 2013-02-08 | P | P | P | Unit testing
| 2013-02-13 | P | P | P | User Acceptance
| 2013-02-18 | P | P | P | Migrate system change
eMedNY
| 2012-07-01 | P | P | P | Explore need for emedNY evolution project to strengthen edits on emergency claims
| 2012-07-01 | P | P | P | Submit eMedNY evolution project (if necessary)
| 2012-07-01 | P | P | P | Finalize eMedNY evolution project (if necessary)

## Ph 2 Behavioral Health
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5101 |  |  |  |  | Project Name: Create Risk/Bearing Managed Care Entities for High/Need Behavioral Health Populations Division Lead: Office of Mental Health Team Lead: Bob Myers Additional Staff: Rob Kent Description: Develop managed care systems using risk/bearing Special Needs Plans (SNPs), Integrated Delivery Systems (IDSs), and/or Behavioral Health Organizations (BHOs), consistent with MRT recommendation #93 and State statutes. In New York City, based on its population and its delivery system infrastructure, develop full/benefit SNPs or IDSs that cover the full range of mental health, substance use, and physical health benefits. |  | Completed December 2016
| 2012-08-01 | P | P | P | Obtain actuarial and consulting contract resources from Mercer
| 2012-10-18 | P | P | P | Stakeholder meeting (MRT BH Workgroup)
| 2012-11-01 | P | P | P | Determine preliminary eligibility criteria for NYC HARP (also BHO as appropriate to the design of BHO) |  | Complete for adults
| 11/1/12 | P | P | P | Review preliminary HARP eligibility, service and benefit data / OMH, OASAS, DOH, NYC |  | Complete for adults
| 2013-02-28 | P | P | P | OMH/OASAS with DOH finalize behavioral health benefit package for BHOs, HARPs (pending federal approval) |  | Complete for adults
| 3/31/13 5/1/13 | P | P | P | OMH/OASAS with DOH finalize selection of managed care models and BHO/NYC SNP regions.
| 4/30/13 5/28/13 | P | P | P | DOH with OMH/OASAS submit high level overview of necessary revisions to 1115 waiver (or alternative) as necessary to CMS (BHO and SNP). |  | Initial call with CMS was May 28, 2013
| 2013-04-30 | 8 | 8 | 8 | Distribute HIT standards for BHO/SNP to stakeholders for review and comment (ongoing coordination with DOH on HIT standards and RHIO implementation).
| 2013-04-30 | P | P | P | Distribute proposed HARP/BHO regions, models to stakeholders (MRT BH workgroup) for review. |  | MRT BH workgroup meeting was May 1, 2013
| 10/30/13 11/29/13 | P | P | P | Distribute RFI for public comment
| 9/1/13 12/30/13 | P | P | P | Submit 1115 waiver and Final SPAs (includes the OASAS medically monitored programs) to CMS |  | The MRT task previously known as Medical Respite for the Homeless will be addressed as part of the OASAS SPA changes needed to implement BHO Phase II.
| 6/1/13 8/1/13 1/15/14 2/14/14 3/14/14 | P | P | P | Finalize Year 1 BHO/HARP performance metrics.
| 8/30/13 2/14/14 3/14/14 3/21/14 | P | P | P | Post RFQ on website for at least 30 days (per enacted legislation)
| 9/30/13 4/30/14 5/2/14 | P | P | P | Presentations for interested parties (bidders, stakeholders) |  | Presentations will be done between February and April
| 11/1/14 10/28/14 | P | P | P | Pilot test interRAI assessment process
| 5/31/13 8/1/13 12/30/13 4/30/14 9/15/14 11/28/14 11/14/14 | P | P | P | DOH with OMH/OASAS propose rates to CMS |  | NYC HARP and Mainstream rate package will go to DOB and CMS-Date to be updated based on revised timeline
| 12/15/13 5/30/14 7/30/14 11/1/14 11/21/14 1/23/15 | P | P | P | Select Plans in NYC (Plans will be designated between July and August) |  | Plan designation will take place throughout the summer 8/ 10 designation letters distributed
| 10/1/14 11/1/14 12/1/14 1/19/15 | P | P | P | Distribute Readiness Review Information Request
| 6/1/13 7/30/13 1/15/14 4/30/14 6/30/14 9/15/14 12/15/14 3/1/15 2/15/15 3/16/15 | P | P | P | Finalize Mainstream/HARP managed care contract requirements for DOH review |  | Model contract revisions due June Date subject to change based on discussion with DOH. Contract workgroup in process of identifying potential model contract revisions.
| 4/1/15 7/20/15 8/17/15 | P | P | P | Begin passive enrollment of HARP eligible in NYC |  | Passive enrollment timeframe pending issuance of HARP Certificate of Authority
| 6/1/15 8/1/15 | P | P | P | NYC Plan Readiness Reviews complete (30 days before "go live")
| 4/30/14 4/1/14 1/1/15 4/1/15 7/1/15 10/1/15 | P | P | P | MCOs and HARPs in NYC fully operational
| 6/15/14 11/30/14 1/15/15 3/15/15 7/30/15 10/15/15 | P | P | P | Select Plans in rest of state (ROS) (Plans will be designated between December and March) |  | On September 18th 15 Plans submitted their Rest of State RFQ Applications. All 8 Upstate Plans submitted HARP applications The State has completed reviewing applications and have awarded conditional designation.
| 2016-01-01 | P | P | P | NYC HCBS Implementation
| 3/1/16 4/8/16 | P | P | P | Onsite Readiness Review for Managed Care Plans Begin
| 10/1/15 4/1/16 5/1/16 | P | P | P | Begin passive enrollment of HARP eligibles ROS
| 12/1/15 3/1/16 6/1/16 | P | P | P | ROS Plan Readiness Reviews complete (30 days before "go live") |  | Desk Audit phase of the readiness review is scheduled to take place during the first 2 weeks of February. Onsite reviews are scheduled to begin in March.
| 10/1/15 4/1/16 5/1/16 | 8 | 8 | 8 | Begin passive enrollment of HARP eligibles ROS
| 10/1/14 7/1/15 10/1/15 1/1/15 1/1/16 7/1/16 | P | P | P | MCOs and HARPs rest of state (ROS) fully operational
| 2016-10-01 | P | P | P | ROS HCBS Implementation
| 10/1/14 7/1/15 | 8 | 8 | 8 | BHOs in rest of state fully operational fully operational
5101A |  |  |  |  | Project Name: Identify/Develop Mechanisms for improving behavioral health screening and treatment in primary care settings Division Lead: Office of Mental Health Team Lead: Dr. Lloyd Sederer Additional Staff: Dr. Steve Kipnis, Rob Piculell Description: | $0 | Completed - May 2013
| 2012-10-30 | P | P | P | OMH/DOH Leadership establish workgroup on development of Collaborative Care Model
| 12/15/12 3/15/13 | P | P | P | Workgroup recommendations to Leadership to address legal and regulatory concerns, confidentiality issues, clarification of covered services and staff credentials, billing rules and logistics, workforce training etc. to support Collaborative Care
| 1/15/13 4/15/13 | P | P | P | OMH/DOH Leadership finalize agreement on processes and policy issues to allow for services under Collaborative Care Model
| 2/1/13 5/1/13 | P | P | P | Guidance and protocols supporting collaborative Care published |  | 26 hospitals have been enrolled, meaning that OMH and DOH reviewed and approved their plans and funding has begun to flow. They are expected to begin providing collaborative care services under the approved protocol by July 1.
5101B |  |  |  |  | Project Name: Implement Joint licensure for clinics Division Lead: Office of Mental Health Team Lead: Marcia Fazio Additional Staff: Rob Kent, Henry Fernandez, Trisha Schell/Guy Description: | $0 | Completed - (Reflected in DSRIP WP and #7402, task 2)
| 9/21/12 9/28/12 | P | P | P | Identify billing and coding rules for participation in pilot phase. Modifications to e-MEDNY programming as needed
| 10/1/12 10/31/12 12/21/12 | P | P | P | Review project parameters, implementation and procedural issues with pilot agencies
| 10/8/12 11/1/12 | P | P | P | Begin review and approval of applications for integrated services from pilot agencies
| 11/30/12 1/31/13 4/1/13 | P | P | P | Review implementation and procedural issues with pilot agencies. Review initial data (fiscal, services, quality etc.) |  | Eligibility criteria for children to receive BH services through Managed Care have been identified. The team is in the process of drafting the kids BH 1115 waiver amendment targeted for CMS submission in December.
| 10/30/12 12/1/12 1/11/13 4/1/13 7/1/13 11/1/13 1/31/14 12/31/14 | 8 | 8 | 8 | Complete survey protocol and surveyor training across state agencies |  | Initial training across agencies completed. Additional inter agency monitoring and survey visits to be conducted to further enhance surveyor consistency in use of standards.
| 12/15/12 4/15/13 11/1/13 3/1/14 12/31/14 | 8 | 8 | 8 | Modify project parameters, procedures, and monitoring systems based on pilot experience |  | Ongoing throughout pilot phase, which is now scheduled to last until 12/31/14. This experience is now being incorporated into the work of the Governor's Cross-Agency Workgroup on Licensing, Inspection and Quality Review. This group has begun development of new regulations for the establishment and operation of sites providing integrated behavioral health and physical health services.
| 12/31/14 2/1/15 | 8 | 8 | 8 | Guidance and protocols supporting integrated services and single state agency oversight published |  | Evaluation of the pilot phase and development of program parameters and protocols for state wide implementation will be conducted after a majority of pilots sites have been fully operational.
5101C |  |  |  |  | Project Name: Care coordination model for children with behavioral health needs Division Lead: Office of Mental Health Team Lead: Donna Bradbury Additional Staff: Steve Hanson, Laura Velez, Linda Kelly Description: Develop a Care coordination model for children with behavioral health needs | $0 | Merged June 2017 with Phase 7 1115 WP
| 2012-09-10 | P | P | P | Draft paper with design recommendations and plan
| 2012-09-19 | P | P | P | Children's State Workgroup completes review of draft plan
| 9/28/12 10/5/12 | P | P | P | Children's State Workgroup meets to finalize document
| 10/8/12 10/25/12 | P | P | P | Identify project manager and project team members
| 10/15/12 11/26/12 | P | P | P | Meet with Children's BHO MRT Workgroup to discuss design recommendations and obtain feedback
| 2012-10-22 | P | P | P | Initiate work with Mercer to further develop work plan, advance model design , and begin actuarial analysis
| 2012-12-04 | P | P | P | Begin meeting with various stakeholder groups and present plan for feedback
| 1/1/13 1/31/13 3/1/13 | P | P | P | Finalize model and implementation work plan
| 10/16/13 10/21/13 | P | P | P | Meet with Children's MRT BH Subcommittee for feedback and discussion on current design
| 4/1/13 5/1/13 6/1/13 7/1/13 8/1/13 9/1/13 12/1/13 | P | P | P | Preliminary identification of populations served through children's behavioral health system
| 7/1/13 9/1/13 12/1/13 | P | P | P | Analyze current service array funded through state dollars or block grant and assess non Medicaid state plan services for inclusion in benefit package.
| 5/1/13 6/1/13 7/1/13 8/1/13 3/1/14 | 8 | 8 | 8 | Complete preliminary analysis of data on children likely to become Medicaid eligible through ACA Medicaid expansion and through potential expansion of behavioral health service edibility standards within managed care (latent population) |  | This milestone has been suspended for the time being.
| 3/1/14 | 8 | 8 | 8 | Finalize medical and psychosocial necessity criteria and network adequacy standards |  | This milestone has been suspended for the time being.
| 2014-04-28 | P | P | P | Meet with Children's MRT BH Subcommittee for feedback and discussion on current design
| 5/1/13 6/1/13 7/1/13 8/1/13 3/1/14 | 8 | 8 | 8 | Complete preliminary analysis of data on children likely to become Medicaid eligible through ACA Medicaid expansion and through potential expansion of behavioral health service eligibility standards within managed care (latent population) |  | This milestone has been suspended for the time being.
| 5/1/13 6/1/13 7/1/13 8/1/13 4/1/14 5/1/14 | P | P | P | Complete preliminary analysis of children's service providers in various MCO catchment areas
| 11/1/13 4/31/14 5/30/14 | P | P | P | Finalize role of Health Homes in service network; include relationship of HH and children's care coordination model
| 2014-06-30 | 8 | 8 | 8 | Meet with stakeholders on children's model |  | scheduled stakeholder meeting dates are already incorporated throughout calendar
| 3/1/14 1/1/14 3/1/14 4/1/14 5/1/14 7/30/14 | P | P | P | Finalize benefit package |  | Anticipate discussion/approval at next MRT BH Subcommittee in July
| 9/1/13 5/1/14 6/30/14 8/1/14 | P | P | P | Draft network adequacy standards
| 2014-09-01 | 8 | 8 | 8 | Finalize plan for the integration of state operated children’s inpatient and outpatient services into managed care
| 6/1/13 7/1/13 8/1/13 1/1/14 3/1/14 4/1/14 5/1/14 7/30/14 10/1/14 | P | P | P | Establish eligibility criteria for children to receive behavioral health services through managed care |  | One task remaining to achieve this milestone - establishing criteria for Level of Need determination
| 3/1/14 1/1/14 3/1/14 4/1/14 5/31/14 8/1/14 10/1/14 11/30/14 | P | P | P | Finalize service delivery model |  | Anticipate this being completed by 11/30/14
| 4/30/14 8/1/14/ 10/1/14 1/1/15 | P | P | P | Finalize year 1 performance metrics specific to children |  | Anticipate this being completed by 1/1/15
| 2015-03-01 | P | P | P | Draft medical and psychosocial necessity criteria
| 10/1/14 10/30/14 2/1/15 4/1/15 6/1/15 8/1/15 | P | P | P | Begin public notice and tribal consultation
| 4/30/14 8/1/14 10/1/14 11/30/14 3/1/15 4/1/15 7/1/15 8/19/15 | P | P | P | Draft 1115 waiver for internal review |  | Anticipate this being completed 11/30/14
| 6/30/14 9/1/14 10/1/14 2/28/15 6/1/15 10/1/15 | P | P | P | Draft continuity of care requirements |  | In line with Medicaid Model Contract changes for BH
| 6/15/2016 11/30/2016 | P | P | P | Finalize analysis of Conflict of Interest care coordination impact |  | Dependant on conversations with CMS
| 7/1/2016 8/1/2016 8/31/16 9/30/16 11/8/16 | P | P | P | Submit BH SPA for 6 new services to CMS |  | Documents moving through DOH for final approval for submission
| 9/23/2016 10/15/16 11/15/16 12/05/16 12/16/2016 1/31/17 TBD | 8 | 8 | 8 | Distribute Policy Paper for feedback to stakeholders
| 12/1/14 5/1/15 8/1/15 1/1/16 4/1/16 5/1/16 7/1/16 08/15/16 11/14/16 12/15/16 1/31/17 06/30/17 | 8 | 8 | 8 | Finalize MCO standards |  | Timeframe based on finalizing key policy decisions with Leadership
| 12/1/14 5/1/15 8/1/15 1/1/16 4/1/16 5/1/16 7/1/16 08/15/16 11/14/16 | P | P | P | Revise 1115 waiver based on policy decisions for internal review |  | The intial draft will need to be re-circulated based on key policy decisions with Leadership
| 7/31/14 12/1/14 3/31/15 9/1/15 1/1/16 4/1/16 10/10/16 11/7/16 12/1/16 TBD | 8 | 8 | 8 | Submit 1115 waiver to CMS | The Children’s design team continues to work to finalize the children’s BH SPA for submission and revising the 1115 waiver amendment. Timeframe based on finalizing key policy decisions with Leadership
| 3/31/14 3/1/15 | 8 | 8 | 8 | Draft revisions to 1115 Waiver
| 2014-07-30 | 8 | 8 | 8 | Finalize Plan design
| 3/1/14 8/1/14 | 8 | 8 | 8 | Identify and review data on eligibility, benefits, and cost to be used by actuaries
| 7/1/16 8/1/16 3/1/17 TBD | 8 | 8 | 8 | Finalize draft Managed Care Contract Requirement Amendments to DOH
| 2/1/16 5/1/16 10/15/16 1/15/17 3/31/17 06/30/17 | 8 | 8 | 8 | RFQ distribution to Plans |  | Pending key policy decisions
| 5/1/16 8/1/16 1/13/17 5/1/17 TBD | 8 | 8 | 8 | Designation of Plans |  | Pending key policy decisions
| 7/1/15 9/1/15 9/1/16 05/15/17 TBD | 8 | 8 | 8 | Begin readiness reviews of managed care plans to implement children's behavioral health services |  | Readiness reviews will run from July to November Pending timeframe for MCO qualification process
| 4/1/15 1/1/16 1/1/17 7/1/17 10/1/17 TBD | 8 | 8 | 8 | Qualified Managed Care Specialty Entities fully operational for Children’s Behavioral Health |  | Pending timeframe for MCO qualification process

## Ph 2 MLTC (Completed)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5201 |  |  |  |  | Project Name: Quality Measures for CCM Performance Division Lead: Division of Quality Improvement & Evaluation Team Lead: Pat Roohan Description: Quality Measures for CCM performance must be transparent and publicly reported.The MRT Managed Long Term Care Quality Subcommittee should continue to convene to review progress made by SDOH in developing and implementing quality measurement system based on recommendations. Wherever possible, alignment with recommendations of MRT Payment Reform and other workgroups should be achieved. |  | Merged with #5602
This project is referred to 5602, Quality Measurement
5202 |  |  |  |  | Project Name: Improve Fair Hearing Process Division Lead: Division of Long Term Care (for now) Team Lead: Mark Kissinger Hope Plavin and Margaret Willard Additional Staff: Maria Vidal Description: Consider the possibility of a targeted increase in resources to handle the move to mandatory enrollment in managed long term care or other care coordination models. Providers should receive notice of fair hearings requested by their clients. Ongoing training for ALJs pertaining to state law, rules, and regulations should be evaluated. Consumers and plans should have input and access to the training. The target timeframe for fair hearing resolution should be within 60 days of the request for the hearing. Regulations should be amended to require documented receipt of written notice of fair hearings to CCM administrators of record or legal counsel. |  | Merged with #7003
| 2012-03-08 | P | P | P | Develop internal DOH/OTDA team
| 2012-03-20 | P | P | P | First meeting of State team
| 7/1/12 7/9/12 8/17/12 | P | P | P | First draft of expenditure plan for budget investment
| 8/1/12 9/5/12 9/12/12 9/26/12 11/7/12 | P | P | P | Secure approvals for Expenditure plan
| 10/1/12 10/15/12 12/15/12 3/1/13 5/1/13 7/1/13 9/1/13 12/1/13 2/1/14 | 8 | 8 | 8 | Hold internal/external stakeholders meeting on improvements
| 12/1/12 12/15/12 2/15/13 5/1/13 7/1/13 10/1/13 11/1/13 2/1/14 | 8 | 8 | 8 | Hold 2nd meeting
| 12/31/12 1/15/13 5/1/13 7/1/13 10/1/13 12/1/13 1/1/14 | 8 | 8 | 8 | Develop template for reform measurement
| 2014-09-01 | P | P | P | Revision to Standardized fair hearing notices for MLTC and MMC including conferencing with stakeholders.
| 2014-11-01 | 8 | 8 | 8 | complete revisions to notices
| 2014-09-30 | 8 | 8 | 8 | implement enhanced OTDA communication with MLTC and MMC plans regarding requests and notification
| 2014-10-15 | 8 | 8 | 8 | Train existing and new ALJs on MLTC and FIDA
| 2014-11-15 | 8 | 8 | 8 | Meeting with OTDA, DOH DLA and program staff to review and discuss new standardized notices.
| 2014-12-01 | 8 | 8 | 8 | Rollout notices and train MLTC and MMC plans on proper use of standardized notices
5203 |  |  |  |  | Project Name: Workgroup on integration of self-directed program models Division Lead: Division of Long Term Care Team Lead: Margaret Willard Additional Staff: Mark Kissinger Description: Establish a work group to advise the Department on the integration of self-directed program models, including the consumer directed personal assistance program (CDPAP), into CCMs and Managed Long Term Care. |  | Completed - Jan 2014
| 2012-01-30 | P | P | P | Hold 1st meeting of workgroup
| 2012-03-15 | P | P | P | Hold 2nd meeting of workgroup
| 2012-06-15 | P | P | P | Hold 3rd meeting of workgroup
| 7/1/12 7/9/12 | P | P | P | Draft contract amendments for MLTC and MC inclusion of self-directed options
| 2012-08-14 | P | P | P | Receive comments on contract amendments from workgroup members
| 8/1/12 9/5/12 10/1/12 10/15/12 11/1/12 12/1/12 4/1/13 6/1/13 7/1/13 10/1/13 12/1/13 2/1/14 | 8 | 8 | 8 | Develop education and training materials on self-directed option
| 11/1/12 4/1/13 5/1/13 8/1/13 11/1/13 1/15/14 | 8 | 8 | 8 | Development of measures to track self-directed take up rate
| 12/31/12 5/1/13 7/1/13 9/1/13 10/1/13 12/1/13 | 8 | 8 | 8 | Determine whether to issue reminder and policy guidance on issues
| 2/1/13 6/1/13 7/1/13 10/1/13 1/1/14 | 8 | 8 | 8 | Additional work group meetings if necessary

## Ph 2 Health Disparities
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5301 |  |  |  |  | Project Name: Data Collection/Metrics to Measure Health Disparities Division Lead: Office of Public Health Team Lead: Geraldine Johnson Additional Staff: Representatives from Office of Public Health, Office of Primary Care and Prevention Services, Office of Health Disparities Reduction, Office of Health Insurance Programs, Information and Health Statistics Group, including Vital Records and SPARCS, and the METRIX Project Team |  | Completed - $2M in SFY 2012-2013 Budget; No Language Completed
| 2012-02-27 17:00 | P | P | P | Project Kick-Off Meeting
| 2012-06-01 17:00 | P | P | P | Create Project Management framework
| 2012-06-01 17:00 | P | P | P | Create business cases and project charter - define scope and deliverables
| 2012-06-15 17:00 | P | P | P | Identify and engage internal and external stakeholders and project team members |  | External stakeholders identified; meeting being scheduled for early September
| 2012-06-15 17:00 | P | P | P | Conduct literature search to identify best practices for data collection for purposes of addressing health disparities and report finding to project management group
| 2012-09-14 | P | P | P | Perform environmental scan of efforts and data sets throughout NYSDOH
| 10/15/12 | P | P | P | Establish a disparities research agenda |  | internal workgroup met 8-21-12
| 10/15/12 12/15/12 | 8 | 8 | 8 | Assess health disparities-related data currently collected - Issue RFP to facilitate assessment
| 2012-11-30 | P | P | P | Identify strategies for data analysis and expanded data collection.
| 12/31/12 1/1/13 | P | P | P | Implement expanded race/ethnicity data collection consistent with ACA standards for expanded behavioral research surveillance survey(EBRFSS). |  | Expanded EBRFSS implemented January 1, 2013
| 12/31/12 | P | P | P | Use ACA template/data standards to inform Health Insurance Exchange/Medicaid and EBRFSS surveys to collect health disparity data (pending Federal Secretary’s application template)
| 12/31/12 4/1/13 | P | P | P | QUALITY IMPROVEMENT INITIATIVE. Work with SPH to develop materials for use in hospital learning collaborative.
| 2013-04-01 17:00 | P | P | P | Initiate plan to assess and prepare selected existing NYSDOH data and expand data collection for selected survey(s) to measure, analyze and address health disparities. |  | Develop Guidance to Hospitals re: SPARCS– Expand the categories of race and ethnicity (consistent with ACA Standards) .
| 2013-04-01 17:00 | 8 | 8 | 8 | Select research proposal(s) for implementation.
| 2014-01-01 | P | P | P | Implement enhanced data SPARCS data collection
| 2014-04-01 17:00 | P | P | P | Develop programs and policy recommendations for implementation that address disparities based on data and analyses conducted by internal and external researchers.
5302 |  |  |  |  | Project Name: Improve Language Access to improve disparities Division Lead: DFRS Team Lead: John Gahan Janet Baggetta Additional Staff: Ronald Bass, Yvonne Lavoie, Monique Grimm & Tami Berdi. Description: Amend Medical Assistance Payments to provide reimbursement in hospital inpatient and outpatient, emergency room, Diagnostic and Treatment Centers and federally qualified health centers | $1.35M | Completed April 2017
| 6/15/12 8/15/12 | P | P | P | Develop regulations for hospital inpatient payment for this service
| 6/30/12 7/30/12 | P | P | P | State Plan Amendment Submission (Institutional SPA) |  | Submitted to CMS 9/28/12.
| 8/1/12 8/15/12 | P | P | P | Develop rate code for billing hospital inpatient payments for these services |  | RC promoted to eMedNY on 10/4/2012.
| 2012-10-01 | P | P | P | Modify APG payments to incorporate payment for these services |  | APG payment implemented effective 10/1/2012. Oct 2012 Medicaid Update advised on billing rules (HCPCS T1013)
| 2013-01-15 | P | P | P | Develop response for RAI request from CMS related to SPA #12-28 |  | Completed, sent to executive staff for sign off
| 2013-03-27 | P | P | P | Received CMS approval of SPA #12-38 |  | Dated 3/27/13
| 7/27/2015 9/14/15 | P | P | P | "Assessment of Public Comment" completed for the proposed regulation change.
| 2015-10-07 | P | P | P | Notice of Adoption received for Regulations
| 2/15/13 4/1/13 6/1/13 TBD 10/30/15 11/6/15 | P | P | P | Develop rate package for DOB approval
| 2015-11-20 | P | P | P | Receive Department and Division of the Budget Approval |  | At DOB: 11/13/ 2015
| 2/28/13 3/15/13 4/15/13 6/15/13 TBD 11/27/15 1/31/16 3/31/16 3/31/17 2/28/17 | P | P | P | Promote rates to eMedNY and notice facilities via an email blast and Medicaid Update and/or Notice letter Dear Administrator Letter
5303 |  |  |  |  | Project Name: Promote Language Accessible Prescription Labels Description: Amend public health law and the education law be amended to require that the State Board of Pharmacy develop regulations and standards to guide the following: creation of standardized prescription label instructions; to require that pharmacies with five or more stores and mail order pharmacies provide translation and interpretation services for limited English proficient (LEP) patients; and that NYS prescription pads be modified to allow prescribers to indicate if a patient is LEP. |  | Completed -Referred to Department of Ed
To be implemented by State Education Department. Public hearings were scheduled for 9/28 (Buffalo), 10/11 (Albany), 10/25 (NYC). For more information please contact Pharmbd@mail.nysed.gov .
5304 |  |  |  |  | Project Name: Medicaid Coverage of Primary and Secondary Community-Based Chronic Disease Preventive Services. Division Lead: Office of Public Health Team Lead: Barb Wallace Additional Staff: Yvonne Graham, Ron Bass, Kristen Pergolino Description: Implement changes/enhancement to the Medicaid basic benefit package to ensure Medicaid coverage of primary and secondary chronic disease prevention and treatment. 5304A: Diabetes 5304B: Asthma 5304C: Lead Poisoning 5304D: Automated blood pressure cuffs for home use |  | Complete - (Neither funding or language included in 2012-2013 SFY Budget; services to be included in waiver.)
| Ongoing | P | P | P | Convene monthly meetings/conference calls with the chronic disease subgroups (diabetes, asthma, lead, and automated blood pressure cuffs) to monitor progress of work plans, identify areas for coordination, and address any obstacles.
5304A |  |  |  |  | Project Name: Chronic Disease Preventive Services: Diabetes Team Lead: Maureen Spence Additional Staff: Ron Bass, Vida Wehren Description: Expand Medicaid (fee-for-services and managed care) coverage to include prediabetes group and individual counseling services including services offered by community-based providers. |  | Complete Included in MRT Waiver
| 4/30/12 | P | P | P | Determine information needs and timeframe for completion of work needed to provide detail regarding new benefit in waiver application.
| 4/30/12 | P | P | P | Convene internal DOH advisory committee to discuss new benefit and brainstorm details of implementation
| 5/15/12 | P | P | P | Define Site of Service and Delivery of Service Who may provide the service – including a description of needed credentials Who may order the service Where the service may be provided
| 6/15/12 | P | P | P | Define Patient eligibility Core eligibility criteria Optional self-referral criteria Exclusions
FUTURE TASKS AND DELIVERABLE DATES TO BE DETERMINED, AS THIS INITIATIVE IS INCLUDED IN MRT WAIVER PENDING APPROVAL BY CMS.
|  | 8 | 8 | 8 | Convene workgroup to discuss new benefit and brainstorm details of implementation
|  | 8 | 8 | 8 | Define Scope of services Required curriculum content (Core and Post Core Topics) Intervention duration and intensity
|  | 8 | 8 | 8 | Convene workgroup to discuss new benefit and brainstorm details of implementation
|  | 8 | 8 | 8 | Define Reimbursement for services Who may bill/be reimbursed Reimbursement rates Duration of the intervention
|  | 8 | 8 | 8 | Convene workgroup to discuss new benefit and brainstorm details of implementation
|  | 8 | 8 | 8 | Quality assurance Requirements for Pending and Full Recognition Status (National Diabetes Prevention Recognition Program) Proposed metrics for tracking individuals receiving services Proposed metrics for tracking receipt of services Proposed metrics for tracking health outcomes Proposed metrics for tracking cost
|  | 8 | 8 | 8 | Convene workgroup to discuss new benefit and brainstorm details of implementation
|  | 8 | 8 | 8 | Executive/DOB Approvals Regulatory Change Process SPA Approval Process
5304B |  |  |  |  | Project Name: Chronic Disease Preventive Services: Asthma Team Lead: Jennifer Mane Additional Staff: Patricia Waniewski, Daniel Luttinger, Amanda Reddy, Ron Bass, Donna Haskin, Akbar Khan, Vida Wehren, Diane Jones, Hope Plavin Description: Extend Medicaid coverage for home-based asthma services |  | Complete Included in MRT Waiver
| 2012-04-30 | P | P | P | Determine information needs and timeframe for completion of work needed to provide detail regarding new benefit in waiver application.
FUTURE TASKS AND DELIVERABLE DATES TO BE DETERMINED, AS THIS INITIATIVE IS INCLUDED IN MRT WAIVER PENDING APPROVAL BY CMS.
|  | 8 | 8 | 8 | Develop and Finalize Overall Benefit Description - Workgroup will meet monthly to review draft language. Revisions will be incorporated each month based on workgroup discussion and team member progress made between meetings to answer outstanding questions, gather missing information. Specific components of benefit description are outlined below.
|  | 8 | 8 | 8 | Develop and Finalize Site of service, Delivery of Service/Service Provider, Patient Eligibility, Scope of Services, Allowable Hours
|  | 8 | 8 | 8 | Develop and Finalize Reimbursement for Services.
|  | 8 | 8 | 8 | Develop and Finalize Quality Assurance
|  | 8 | 8 | 8 | Finalized Benefit Description to be shared with key stakeholders groups; feedback reviewed by team and incorporated where indicated
|  | 8 | 8 | 8 | Executive/DOB Approvals Regulatory Change Process
5304C |  |  |  |  | Project Name: Chronic Disease Preventive Services: Lead Poisoning Team Lead: Mike Cambridge Additional Staff: Ron Bass, Vida Wehren, Yvonne Graham Description: Expand Medicaid to include coverage for costs associated with environmental investigations, and care coordination for children on Medicaid with lead poisoning. |  | Complete Included in MRT Waiver
FUTURE TASKS AND DELIVERABLE DATES TO BE DETERMINED, AS THIS INITIATIVE IS INCLUDED IN MRT WAIVER PENDING APPROVAL BY CMS.
|  | 8 | 8 | 8 | Convene internal DOH advisory committee to discuss new benefit and brainstorm details of implementation
|  | 8 | 8 | 8 | Refine and Finalize Patient Eligibility including core eligibility; extraordinary circumstances and exclusions- Workgroup will review draft language. Revisions will be incorporated based on workgroup discussion and team member progress made between meetings to answer outstanding questions, gather missing information.
|  | 8 | 8 | 8 | Refine and Finalize Scope of Services - The following components will be finalized during this time period: Site of service, Delivery of Service/Service Provider, Extraordinary circumstances, Allowable Hours and exclusions.
|  | 8 | 8 | 8 | Define Reimbursement for services Who may bill/be reimbursed; Reimbursement rates ; and duration of intervention
|  | 8 | 8 | 8 | Quality assurance Proposed metrics for tracking individuals receiving services Proposed metrics for tracking receipt of services Proposed metrics for tracking investigation outcomes Proposed metrics for tracking cost
|  | 8 | 8 | 8 | Executive/DOB Approvals Regulatory Change Process
5304D |  |  |  |  | Project Name: Chronic Disease Preventive Services: Automated blood pressure cuffs for home use Team Lead: Barb Dennison Additional Staff: Ron Bass, Vida Werwen Description: Expand Medicaid to include coverage for validated automated home blood pressure monitors. |  | Completed - Dec 2012
| 2012-03-30 | P | P | P | Review Current Medicaid Procedures, Waiver processes for covering Semi-Automated and Automated blood pressure cuffs. Review number of waivers submitted and granted
| 2012-04-30 | P | P | P | Review Recommended Specifications for Automatic and Semi-automatic Blood Pressure Cuffs
| 5/30/12 | P | P | P | Collect and review coverage of Automatic and Semi-automatic blood pressure cuffs by other state Medicaid and NYS Private Payers
| 10/30/12 | P | P | P | Develop Draft Recommendations of Criteria and Specifications of Automatic and Semi-automatic blood pressure cuffs. Submit for Review.
| 12/30/12 | P | P | P | Finalize Recommendations of Criteria and Specifications of Automatic and Semi-automatic blood pressure cuffs and refer to Basic Benefits committee for consideration.
5305 |  |  |  |  | Project Name: Streamline and Improve Access to Emergency Medicaid Description: Clarify Emergency Medicaid Application Procedures, Prequalify Medicaid Financial Eligibility, and Implement a 12-month Certification Period for Certain Emergency Medical Conditions. |  | Merged with #5005
Merged - moved to Project 5005 (Program Streamlining work sheet).
5306 |  |  |  |  | Project Name: Address Disparities in Treatment at Teaching Facilities Division Lead: Office of Primary Care Team Lead: Tom Burke Additional Staff: Dina Addario Description: DOH will take administrative actions to assure that the health care delivered by academic medical teaching facilities to persons who are uninsured, to people covered by Medicaid and to people who are privately insured is comparable and meets the same standards of care. Enforce Draft Medicaid Primary Care Standards developed by the Department in 2008. |  | Cancelled
| 2012-07-30 | P | P | P | Internal meeting with DOH Counsel
| 2012-08-31 | P | P | P | Finalize stakeholder workgroup of physicians and policy experts.
| 2012-10-30 | P | P | P | Distribute patient-centered medical home (PCMH) standards, the Hospital-Medical Home Demonstration (HMHD) initiative, Residency Review Committee (RRC) standards (and other related documents) to the workgroup.
| 11/30/12 2/28/13 | P | P | P | The workgroup will crosswalk these standards, initiative and other existing requirements for teaching facilities to gauge current experiences and issues. |  | the workgroup met and will be developing next steps (that will add to the work plan) by the next scheduled timeframe (prior to 4/30/13).
| 12/28/12 4/30/13 6/28/13 | P | P | P | The workgroup will receive an update on the implementation of the HMHD and develop a plan for next steps.
| 10/31/13 12/31/13 | P | P | P | Staff Workgroup will develop draft a survey to collect information on current primary care standards of care followed in all types of practice settings within academic medical facilities and solicit comments.
| 12/31/13 | 8 | 8 | 8 | Survey will be approved by DOH and distributed to academic medical facilities
| 3/31/14 | 8 | 8 | 8 | Facilities will return responses to DOH
[5 empty] | Staff will obtain and analyze quality and access to care data from the HMHD. |  | Staff determined that much of the information requested in the survey is available from hospitals participating in the demo.
| 6/30/14 | 8 | 8 | 8 | Workgroup will identify possible areas of inequity analyze data within and between among institutions and settings, to as well as assess trends, commonalities, areas of concern and potential best practices for ensuring equitable access and care.
| 9/30/14 | 8 | 8 | 8 | Workgroup will compare these findings to GME training requirements and determine if policy changes are necessary
| 12/31/14 | 8 | 8 | 8 | Workgroup will submit policy recommendations to DOH
5307 |  |  |  |  | Project Name: Enhance Services to Promote Maternal and Child Health Division Lead: Office of Public Health Team Lead: Rachel deLong Additional Staff: Tom Tallon, Christine Pergolino Description: Take action on comprehensive initiatives to improve maternal and child health in New York State particularly among racial and ethnic minorities. 5307A: Expand access for contraception and other family planning services 5307B: Expand Medicaid coverage for inter-conceptional care 5307C: Expand Medicaid coverage to include breastfeeding education and lactation counseling and provide financial incentives to hospitals to provide breastfeeding support 5307D: Support initiatives to demonstrate effective and efficient use of HIT technology to improve care delivery for women and infants |  | Cancelled
5307A |  |  |  |  | Project Name: Expand access for contraception and other family planning services Team Lead: Wendy Butz Additional Staff: Description: Expand financial eligibility for Medicaid coverage for contraceptive and other family planning services from 200% FPL to 300% FPL. |  | Cancelled Pending 2015-16 Budget
|  | 8 | 8 | 8 | Pending for inclusion in next year's budget.
5307B |  |  |  |  | Project Name: Expand Medicaid coverage for inter-conceptional care Team Lead: Kristine Mesler Additional Staff: TBD Description: |  | Cancelled Medicaid expansions proposals deferred due to eligibility and fiscal impact concerns
|  | 8 | 8 | 8 | Deferred pending discussions with Medicaid staff
5307C |  |  |  |  | Project Name: Expand Medicaid coverage to include breastfeeding education and lactation counseling and provide financial incentives to hospitals to provide breastfeeding support Description: Provide Medicaid coverage for breastfeeding education and lactation counseling during pregnancy and in the postpartum period and provide financial incentives to hospitals that provide breastfeeding support. |  | Merged with #5402D
Merged with 5402D (Basic Benefit work sheet), Breastfeeding Support.
5307D |  |  |  |  | Project Name: Support initiatives to demonstrate effective and efficient use of HIT technology to coordinate and improve care delivery for women and infants Team Lead: Marilyn Kacica, Rudy Lewis Additional Staff: Ron Bass, Wendy Butz, OHIP, OPQS and OHITT representatives (TBD), Rachel de Long, Kris Mesler, Michael Acosta, Foster Gesten, Judy White, Marietta Angelotti, Kristen Farina, Shannon Kelley, and Steve Smith. Description: Coordinate service delivery among and between community-based social health and human services organizations (CBHOs), and clinical providers, and managed care plans using Health Information Technology (HIT) and uniform screening criteria for perinatal risks. |  | Completed - (Language and funding included in SFY 2012-2013 Budget. $2.5M state/$2.5M FMAP)
| 2012-06-08 | P | P | P | Reach out the MRT Health Disparities workgroup members to obtain further input on workgroup recommendation.
| 2012-06-18 | P | P | P | Meet with key leadership from OHITT and OPQS to discuss project
| 2012-07-15 | P | P | P | Convene internal SDOH team to develop project plan/charter
| 2012-07-15 | P | P | P | Research HIT technologies currently in use or under development to share information among health care providers and community-based health and human service organizations to better coordinate perinatal health care for women and infants.
| 2012-10-03 | P | P | P | Assess potential approaches to supporting use of HIT applications to better coordinate care on the local level, building on existing infrastructure and integrated with statewide DOH information systems, such as CHI2 and the SPDS. Include process for receiving stakeholder input.
| 2012-10-29 | P | P | P | Develop recommendations for use of funds to implement selected approaches (contained in expenditure plan).
| 11/15/12 1/15/13 3/1/13 | P | P | P | Secure approval for Federal matching funds for the $2.5M state funds allocated in SFY12 budget. |  | MA match memo in reviewed and SPA recommended for use of funds for HIT Initiative. ; funds to be awarded as add-on to perinatal to new contracts - 7/1/13 start date.
| 11/15/12 3/1/13 4/1/13 5/1/13 6/1/13 7/15/13 9/15/13 12/4/13 | P | P | P | Obtain necessary DOH and control agency approvals for proposed approach to distribute funds for local projects and/or state level systems/infrastructure. |  | Single source waiver is being forwarded to OSC to award funding to 6 entities that have evidenced interest and ability to implement this initiative.
| 4/1/13 5/1/13 6/1/13 7/15/13 9/15/13 1/1/14 | P | P | P | Award funds to selected local projects and begin implementation, with ongoing oversight and technical assistance. |  | Contracts to be awarded with a 1/1-12/31/14 period
5308 |  |  |  |  | Project Name: Address Disparities through Targeted Training for NYS Health Care Workforce Division Lead: Team Lead: Barry Gray Additional Staff: Tom Burke, Lyn Stevens, Dina Addario Description: Mandate training to promote care and reduce disparities experienced by people with disabilities, for Lesbian, Gay, Bisexual and Transgender (LGBT) persons and for persons at risk of suicide. |  | Cancelled
| 9/14/12 | P | P | P | Convene internal SDOH workgroup to discuss proposal and identify possible solutions
| 10/31/12 11/17/12 2/17/12 5/1/13 9/1/13 | 8 | 8 | 8 | Create inventory of DOH programs and resources that include cultural sensitivity training materials for LGBT, disabled and persons at risk of suicide.
| 10/31/12 11/30/12 3/1/12 5/1/13 9/1/13 | 8 | 8 | 8 | Review NYC HHC training model.
| 10/31/12 11/30/12 3/1/12 5/1/13 6/15/13 | P | P | P | Review ACA Sections 5307 and 5403 as potential funding sources to support training initiatives
| 11/30/12 3/1/13 5/1/13 9/1/13 | 8 | 8 | 8 | Convene 2nd internal SDOH workgroup to review resources and plan a strategy and possible solutions for presentation to State agencies
| 12/17/12 2/15/13 6/15/13 5/15/13 10/1/13 | 8 | 8 | 8 | Convene 3rdinternal SDOH workgroup to finalize strategy and presentation
| 1/30/13 3/28/13 6/28/13 9/1/13 | 8 | 8 | 8 | Convene interagency workgroup to evaluate mandated annual training of staff working within OASAS and OMH licensed programs on Sexual Orientation and Gender Identity and Expression to address cultural sensitivity as well as clinical issues that relate to the LGBT experience
5309 |  |  |  |  | Project Name: Enhance Services for Youth in Transition with Psychiatric Disabilities Division Lead: Office of Mental Health Team Lead: Additional Staff: Description: Develop comprehensive programs to serve youth in transition to adulthood with psychiatric disabilities across all systems of care including foster care, school populations that have youth with serious emotional diagnoses (SED) and the juvenile justice population to ensure that youth with psychiatric disabilities who are aging out of these programs do not end up homeless or in the criminal justice system. |  | Merged
Referred to the Behavioral Health Reform project 5101C, Kids Care Coordination
5310 |  |  |  |  | Project Name: Promote Effective Use of Charity Care Funds Division Lead: Team Lead: Additional Staff: Description: Revise the charity care reimbursement system to ensure that charity care funding is transparent and is used to pay for the care of the uninsured. |  | Merged with #5603
Merged into the Payment Reform & Quality Measurement project 5603, reform indigent care.
5311 |  |  |  |  | Project Name: Promote Hepatitis C Care and Treatment through Service Integration Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Colleen Flannigan, Jackie Treanor, Frank Laufer, Ron Bass, Mike Gwizdala Description: Integrate Hepatitis C (HCV) screening, treatment and supportive services into primary care settings including community health centers, HIV primary care clinics and OASAS substance use treatment programs. 5311A: Integrated Disease Management 5311B: Primary Care Settings 5311C: Utilize Health Homes care coordination framework for eligible HCV infected Medicaid population. |  | Completed: Funding in SFY 2012-2013 budget. $1.05M state share.
5311A |  |  |  |  | Project Name: Design an integrated HCV disease management initiative for HCV screening, care and treatment, and other supports in a variety of treatment settings: primary care clinics, HIV clinics and OASAS clinic programs. Include in Medicaid managed care plans chronic disease infrastructure. Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Colleen Flanigan, Jackie Treanor, Frank Laufer, Ron Bass, Mike Gwizdala Description: Expand HCV screening, treatment and supportive services for Medicaid managed care beneficiaries |  | Completed
| 6/1/12 | P | P | P | Convene internal SDOH staff to identify opportunities and barriers to promote HCV identification, treatment and supportive services for various treatment sites and targeting Medicaid managed care beneficiaries. |  | Completed .
| 7/10/12 | P | P | P | Consult with stakeholders. |  | Completed .
| 11/1/12 12/6/12 | P | P | P | Engage managed care plans to define and address current plan barriers for treatment access. Create Medicaid standard for HCV care to be adopted by providers and managed care plans. |  | Initial meeting completed; follow up planning under way.
| 12/1/12 3/1/13 | P | P | P | Develop framework for disease management programs which creates adequate capacity of providers for treatment and supports for retention in care.
| 1/1/13 3/1/13 | P | P | P | Define a new disease management program which will meet identified care needs
| 2/1/13 3/1/13 | P | P | P | Explore creating HCV peer and support groups as a Medicaid billable service to ensure treatment adherence.
| 5/1/14 | P | P | P | Hepatitis C care and treatment initiative moved to DSRIP due to availability of new treatment options. DSRIP projects 2.c.i Expanding use of telemedicine, 3.e.i HIV/ HCV Centers For Excellence, and 4.b.i. chronic disease action plan are examples of DSRIP projects readily adapted to the MRT action plan.
| 4/1/13 6/1/13 9/1/13 12/1/13 1/1/14 | 8 | 8 | 8 | Receive necessary State and Federal approvals. |  | HCV Standards circulating to internal and external stakeholders for comment
5311B |  |  |  |  | Project Name: Promote Hepatitis C Care and Treatment through Service Integration: Primary Care Settings Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Colleen Flannigan, Jackie Treanor, Frank Laufer, Ron Bass, Mike Gwizdala Description: Expand current HCV care and treatment infrastructure in primary care settings through the use of new technology, building upon emerging telemedicine infrastructure. Medicaid reimbursement for clinician services is needed to sustain efforts. |  | Completed
| 6/1/12 | P | P | P | Consult within department on current Medicaid reimbursement available for tele-consulting initiatives. |  | Collaborating with larger departmental telemedicine initiatives.
| 7/1/12 | P | P | P | Explore technologies available to provide consultations between primary care providers and HCV specialists.
| 7/10/12 | P | P | P | Consult with stakeholders.
| 11/1/12 12/6/12 | P | P | P | Consult with Medicaid managed care medical directors |  | Initial meeting completed; follow up planning under way.
| 8/1/12 - 12/1/12 4/1/13 | P | P | P | Develop infrastructure and seek necessary approvals to support specialist consultations through the use of new technologies. |  | Internal SDOH and managed care plan collaboration underway.
| 1/1/13 - 3/31/13 4/1/13 - 7/30/13 10/1/13 11/1/13 1/1/14 4/1/14 | 8 | 8 | 8 | Application process.
| 4/1/13 10/1/13 1/1/14 4/1/14 | 8 | 8 | 8 | Commence new initiative.
| 3/1/14 7/1/15 | 8 | 8 | 8 | Hepatitis C care and treatment initiative moved to DSRIP discussion due to availability of new treatment options.(see above)
5311C |  |  |  |  | Project Name: Promote Hepatitis C Care and Treatment through Service Integration: Health Home Expansion Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Colleen Flannigan, Jackie Treanor, Frank Laufer, Ron Bass, Vida Wehren Description: Utilize health homes care coordination framework for eligible HCV infected Medicaid enrollees for client engagement, care coordination and peer education/support services. Expand Health home eligibility to include HCV mono infected population. |  | Merged - Moved to Phase 4, Health Home Work Plan
| 6/1/12 | P | P | P | Internal SDOH planning for steps needed to add remaining HCV population to Medicaid Health Homes for care coordination services and supports. The majority of HCV population is already on State health home assignment lists.
| 7/10/12 | P | P | P | Stakeholder meeting on HCV initiative planning.
| 9/1/12 | P | P | P | Develop recommendations to ensure newly HCV diagnosed population are also served through Health Home bottom up referrals for treatment decisions and engagement in care.
| 9/1/12-12/31/12 | P | P | P | Promote avenues for adding providers to Health Home networks experienced with providing HCV treatment and ancillary services: HCV support groups, HCV peer services, side effect management. |  | Awaiting final approval and sign-off from OHIP
| 4/1/13 TBD | 8 | 8 | 8 | Develop proposal for HCV to be a single qualifying condition for Health Homes.
5312 |  |  |  |  | Project Name: Promote Full Access to the Mental Health Medication on the Medicaid Formulary Division Lead: Team Lead: Additional Staff: Description: |  | Merged with #5914
5313 |  |  |  |  | Project Name: Medicaid Support of Water Fluoridation Division Lead: Team Lead: Additional Staff: Description: |  | Completed - Implemented and enacted through Budget 15-16
5314 |  |  |  |  | Project Name: Medicaid Coverage of Harm Reduction Activities Division Lead: Office of Public Health Team Lead: Dan O'Connell Additional Staff: Barbara Agastein, Mark Hammer, Alma Candelas, Jackie Treanor, Frank Laufer Description: Promote and address health care needs of persons with chemical dependency. 5314A: Clarify Regulations 5314B: OASAS Provider Reimbursement 5314C: NYS DOH AIDS Institute Syringe Exchange providers reimbursement |  | Completed
| 5/1/12-12/1/12 | P | P | P | Explore mechanisms for the development of demonstration programs to learn the needs of the harm reduction/syringe exchange programs for infrastructure, creation of systems of documentation and reimbursement.
| 5/1/12-12/1/12 | P | P | P | Explore the ability of providing agencies with capacity building assistance, that will test models of services provision utilizing a harm reduction approach .
5314A |  |  |  |  | Project Name: Medicaid Coverage of Harm Reduction Activities: Clarify Regulations Team Lead: Dan O'Connell Additional Staff: Barbara Agatstein, Mark Hammer, Alma Candelas, Jackie Treanor Description: Clarify regulations to allow any medical provider to prescribe syringes to an injection drug user for purposes of preventing disease transmission, paid for by Medicaid. |  | Completed - April 2013Initiative Included in 2012-2013 NYS Budget: $410,000
| 2012-08-01 | P | P | P | Initial communication to stakeholders to confirm that there are no regulatory or practitioner practice impediments to the prescription of syringes to injection drug users for the purpose of preventing disease transmission. In addition ensure, there are no restrictions to pharmacies dispensing of syringes pursuant to such prescriptions. |  | Completed two stakeholder meetings
| 12/1/12 2/1/13 | P | P | P | Develop mechanisms to assure consistency with established medical and infectious disease recommendations to promote access to sterile syringes as a means of preventing disease transmission. |  | Verification under way with DLA and other internal SDOH offices
| 2013-03-01 | P | P | P | Collaborate to remove any impediments identified in the process.
| 4/1/13 | P | P | P | Promote access.
5314B |  |  |  |  | Project Name: Medicaid Coverage of Harm Reduction Activities: OASAS Provider Reimbursement Division Lead: Office of Public Health Team Lead: Dan O'Connell Additional Staff: Alma Candelas; Barbara Agatstein; Mark Hammer Description: Allow OASAS-licensed drug treatment providers to be reimbursed for harm reduction counseling. | 0 | Completed - Feb 2013
| 5/1/12-12/1/12 | P | P | P | Review OASAS regulations and obtain clarification on its intent with respect to regulatory changes enabling Medicaid reimbursement for its licensed services. |  | OASAS takes the lead. Planning calls underway.
| 5/1/12-12/1/12 | P | P | P | AIDS Institute coordinate with OASAS on developing collaborative "client centered" work plan.
| 12/1/12 2/1/13 | P | P | P | Work plan and tasks to be expanded pending discussions with OASAS.
5314C |  |  |  |  | Project Name: Medicaid Coverage of Harm Reduction Activities: AI providers reimbursement Division Lead: Office of Public Health Team Lead: Dan O'Connell Additional Staff: Babara Agastein, Mark Hammer, Alma Candelas, Jackie Treanor Description: Authorize NYS DOH AIDS Institute Syringe Exchange providers (community-based organizations) to be reimbursed by Medicaid for harm reduction/syringe exchange program services provided to Medicaid eligible individuals. | 0 | Merged - #8021
| 5/1/12-12/1/12 | P | P | P | Coordinate the parameters of this Medicaid proposal with the existing and ongoing grant funding of syringe exchange/harm reduction programs.
| 5/10/12 | P | P | P | Identify stakeholders to provide input regarding the overall direction of this MRT recommendation. These include MRT members; AIDS Institute staff; syringe exchange/harm reduction programs; HIV and viral hepatitis prevention and care providers; the Harm Reduction Coalition; the Injection Drug Users Health Alliance; VOCAL New York; the Drug Policy Alliance; Legal Action Center; the Foundation for AIDS Research; the New York City Department of Health and Mental Hygiene; the New York State Office of Alcoholism and Substance Abuse Services; the pharmacy and medical associations; and others.
| 2012-06-01 | P | P | P | Begin meeting with these stakeholders. |  | Two meetings with stakeholders.
| 7/1/12 | P | P | P | Convene a Harm Reduction MRT Advisory Work Group to provide input regarding the overall direction of this MRT recommendation This work group should draw from the various stakeholders.
| 1/1/13 | P | P | P | With guidance from the Harm Reduction MRT Advisory Work Group, define the specific recommended services for which Medicaid reimbursement will be available under this item and who will furnish those services |  | Completed 2 advisory group meetings in September and October 2012.
| 2/1/13 | P | P | P | Process begins for the development of the reimbursement structure and rates for this item, and discussion begins on the need for a Medicaid wavier or SPA.
| 8/1/13 | P | P | P | Convene a Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group which includes members of the Harm Reduction MRT Advisory Work Group to help define the standards for the various services (other than perhaps for syringe exchange for which there are already standards in the regulations and in the programs’ policies and procedures which must be approved by the Department).
| 3/25/14 | P | P | P | State submission of Harm reduction counseling State Plan Amendment (SPA) to CMS.
| 7/1/14 10/15/14 6/1/15 8/1/15 10/15/15 1/1/16 | 8 | 8 | 8 | Federal approval of Harm reduction SPA or 1915 waiver received |  | Merged
| 7/15/14 11/1/14 7/1/15 9/1/15 11/15/15 2/1/16 | 8 | 8 | 8 | DOB approval. |  | Merged
| 8/1/14 1/1/15 8/1/15 11/1/15 12/15/15 3/1/16 | 8 | 8 | 8 | Harm reduction reimbursement incorporated in Medicaid managed care monthly premium calculations. |  | Merged
| 9/1/14 1/1/15 9/1/15 11/1/15 12/15/15 3/1/16 | 8 | 8 | 8 | Qualified harm reduction providers contracted with health plans to provide service. |  | Merged
| 10/1/14 1/1/15 10/1/15 1/1/16 4/1/16 | 8 | 8 | 8 | Commence billing for HR services within a managed care reimbursement structure. |  | Merged
| 12/1/13 9/1/14 1/1/15 10/1/15 1/1/16 4/1/16 | 8 | 8 | 8 | With guidance from the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group, complete the standards for the various services and develop the necessary regulation (or guidance) for their promulgation. |  | Merged
| 1/1/14 | 8 | 8 | 8 | With guidance from the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group, define the quality assurance metrics applicable to each of the Medicaid reimbursed services. |  | Merged
| 2014-04-01 | 8 | 8 | 8 | Incorporate the services standards developed by the Harm Reduction Services Standards and Quality Assurance MRT Advisory Work Group in the necessary regulations (or guidance) for their promulgation. |  | Merged
5315 |  |  |  |  | Project Name: Expand HIV SNPs enrollment to include non-HIV high-need/high-cost populations (e.g., homeless) Division Lead: Office of Public Health Team Lead: Ira Feldman Additional Staff: Carol DeLaMarter, Frank Laufer, Jackie Treanor, Valencia Lloyd, Jennifer Dean Description: HIV SNPs enrollment of non-HIV high-need/high-cost populations (e.g., homeless) |  | Completed
| 4/1/12 | P | P | P | Obtain legislative approval.
| 5/1/12 | P | P | P | Commissioner of DOH designates new expansion population for HIV SNPs
| 6/1/12 | P | P | P | AI shares contract amendment language with OHIP
| 6/1/12 | P | P | P | Define process for securing an amendment to 1115 waiver, MMC contract amendments, network development, rate-setting and enrollment.
| 7/1/12 | P | P | P | Rate development by actuaries for non-HIV homeless population in SNPs.
| 1/1/13 | P | P | P | Finalize approval processes including contract amendment, rates, enrollment process.
| 1/1/13 4/1/13 TBD 7/1/13 9/1/13 10/1/13 1/1/14 | P | P | P | First non-HIV enrollment effective in SNP |  | working towards a 4/1/13 SPA submission for internal and external approvals. Final requirements under assessment by OHIP.
| 4/1/13 Ongoing | P | P | P | Monitoring/quality plan for non-HIV enrollments in place
| 4/1/13 Ongoing | P | P | P | Report impact to key stakeholders

## Ph 2 Basic Benefit (Completed)
MRT Project # | MRT Project # | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5401 |  |  |  |  | Project Name: Benefit Review Process Division Lead: Office of the Medical Director Team Lead: Foster Gesten Additional Staff: Ron Bass, Connie Donohue, Cyndy Sauer Description: Implement a detailed process for all benefit reviews. The process addresses the criteria used to determine if the benefit should be reviewed, the evidence to be considered, the clinical as well as financial aspects of the review, and the final approval authority. Establish an expert advisory panel to provide as needed guidance to the Medicaid program in regard to ongoing benefit design. |  | Completed - Oct 2012 Target Date: 4/1/2012
| 4/30/12 | P | P | P | Amend SUNY MOU to clarify roles/responsibilities of DOH, SUNY and OHSU.
| 4/25/12 | P | P | P | Decide on specific deliverables, including type(s) and number of reviews to be provided under the MOU.
| 5/4/12 | P | P | P | Identify core and ad hoc internal work group members.
| 5/4/12 | P | P | P | Arrange meeting schedule with core internal work group members.
| 7/6/12 5/15/12 6/15/12 10/1/12 | P | P | P | Identify external work group members, including a consumer.
| 8/31/12 6/15/12 10/1/12 | P | P | P | Identify ad hoc internal work group members
| 5/4/12 6/15/12 7/6/12 | P | P | P | Make arrangements for training for work group members, targeting fall 2012. |  | Contacted Milbank; Arranging training
| 8/31/12 9/28/12 | P | P | P | Develop business work plan to guide internal work group, including meeting schedule, engagement of ad hoc members, flow diagrams, definitions of types of reviews, dossier process, process for voting, process for integration of clinical and fiscal data, communication strategy with all relevant stakeholders.
5402 |  |  |  |  | Project Name: Benefit Reforms Division Lead: Division of Program Development and Management Team Lead: Greg Allen Additional Staff: Description: Specific benefit reforms 5402A: Podiatry for Diabetics 5402B: Knee Arthroscopy 5402C: Back Pain Treatments 5402D: Breastfeeding Support 5402E: Percutaneous Coronary Intervention (Angioplasty) 5402F: Reduce payment for Elective Cesarean Sections and Inductions <39 Weeks gestation 5402G: Growth Hormone 5402H: Tobacco Cessation Counseling by Dentists - No longer viable
5402A |  |  |  |  | Project Name: Podiatry for Diabetics Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Connie Donohue, Ron Bass Additional Staff: Cris Carter, Andrea Swire, Joan Sicard Description: Permit adult MA recipients who have a diagnosis of Diabetes Mellitus to obtain care from a private practicing podiatrist. |  | Completed - Sept 2012
| 2012-04-01 | P | P | P | Statute change (Article VII).
| 2012-04-06 | P | P | P | Evaluate ICD-9 diagnosis code(s) that apply to determine whether edits are needed. |  | It was determined that no edits are needed.
| 2012-04-06 | P | P | P | Identify systems impact/changes necessary to implement MRT.
| 2012-04-06 | P | P | P | Submit Evolution Project outlining systems edits.
| 2012-04-09 | P | P | P | Review the need for developing pre-payment edits vs. post payment review process. |  | It was determined that no edits/changes are needed.
| 6/1/12 5/1/12 4/11/12 | P | P | P | Prepare draft SPA. |  | SPA currently in final stages of review
| 2012-04-20 | P | P | P | Evaluate CPT/HCPCS procedure code(s) that apply; determine number and frequency of visit, and reimbursement. |  | Existing codes, visits and reimbursement methodology will be use.
| 2012-04-30 | P | P | P | Prepare a draft Medicaid Update article. |  | 5/22/2012 currently in final stages of review
| 5/24/12 5/31/12 | P | P | P | Meet with internal stakeholders. |  | meeting rescheduled to 5/24/12; 5/3/2012 meeting to be rescheduled.
| 6/15/12 5/8/12 6/29/12 | P | P | P | Draft Q & As.
| 8/30/12 7/27/12 6/15/12 5/15/12 9/30/12 | P | P | P | Educate Helpline Call Center staff.
| 6/1/12 6/30/12 | P | P | P | Submit SPA to CMS.
| 2012-08-17 | P | P | P | Respond to RAIs from CMS
| 2012-09-30 | P | P | P | Obtain SPA approval from CMS
| 9/30/12 8/30/12 8/17/12 7/1/12 6/1/12 10/30/12 | P | P | P | Develop outcomes metrics. |  | Meeting scheduled with data people for 10/30/12
| 8/30/12 7/15/12 6/15/12 9/30/12 | P | P | P | Assure that CSC staff are aware of changes to ensure that accurate policy information is communicated to providers.
| 7/15/12 6/15/12 9/30/12 | P | P | P | Complete and submit Medicaid Update. |  | Medicaid update sent in for publication in October 2012 Medicaid Update
| 9/1/12 7/15/12 7/1/12 9/30/12 | P | P | P | Implement policy resulting from Article VII Statute change. |  | SPA approval received. Implementation date November 1, 2012
5402B |  |  |  |  | Project Name: Knee Arthroscopy Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Donna Urban, Joan Sicard Description: Limit coverage for arthroscopic knee surgery when primary diagnosis is osteoarthritis of the knee (without mechanical destruction of the knee). | (0.20) | Completed - Sept 2012
| 3/15/12 | P | P | P | Prepare coverage guidelines and identify ICD-9 diagnosis code(s) and CPT/HCPCS procedure code(s) that apply.
| 3/15/12 | P | P | P | Identify systems impact/changes necessary to implement MRT. Consider developing pre-payment edits vs. post-payment review process.
| 3/15/12 | P | P | P | Confer with internal and external stakeholders on coverage guidelines.
| 4/1/12 5/1/12 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy. |  | Medicaid update article completed and forwarded to Dr. Gesten for review. Plan April, 2012 inclusion in Medicaid Update. (April 20, 2012 submission deadline date).
| 5/1/12 8/27/12 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees. |  | Q&As prepared. Being circulated for review.
| 9//27/12 7/13/12 9/7/12 | P | P | P | Educate CSC staff to ensure that accurate policy information is communicated to providers and enrollees. |  | Q&As prepared. Being circulated for review.
| 2012-05-01 | P | P | P | Implement policy.
| 7/13/12 5/1/12 6/15/12 7/16/12 | P | P | P | Develop outcomes metrics. |  | Met with data staff. Metrics developed.
5402C |  |  |  |  | Project Name: Back Pain Treatments Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Cyndy Sauer, Debbie Bush, Joan Sicard Description: Limit/exclude coverage of prolotherapy, intradiscal steroid injections, facet joint steroid injections, systemic corticosteroids and traction (continuous or intermittent). | (3.85) | Completed - Sept 2012
| 3/8/12 | P | P | P | Prepare coverage guidelines and identify the ICD-9 diagnosis code(s) and CPT/HCPCS procedure(s) codes that apply.
| 2012-03-15 | P | P | P | Identify systems impact/changes necessary to implement MRT. Consider developing pre-payment edits and/or post-payment review process.
| 2012-03-15 | P | P | P | Discuss options for exceptions with internal and external stakeholders.
| 2012-04-01 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy. |  | Medicaid update article completed and reviewed by Dr. Gesten, Managed Care, and OHSU staff. Published April Medicaid Update (on 5/1/2012).
| 2012-05-01 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees. |  | Provider calls are of a clinical nature, and should be handled by Policy staff.
| 8/31/12 9/30/12 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees. |  | Numerous complicated policy questions received to dated / To develop add'l guidance to help Helpline and CSC triage calls effectively.
| 2012-05-01 | P | P | P | Implement policy.
| 7/13/12 6/30/12 5/1/12 9/30/12 | P | P | P | Develop outcomes metrics.
5402D |  |  |  |  | Project Name: Breastfeeding Support Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Donna Urban, Melissa Kinnicut, Joan Sicard, Dr. Dennison (OPH) Description: Provide Medicaid reimbursement for International Board Certified Lactation Consultant (IBCLC) services for eligible pregnant women. | (4.20) | Completed - Mar 2013
| 2012-04-01 | P | P | P | Implement statute change (Article VII).
| 4/20/12 | P | P | P | Review other insurers' coverage policy/guidelines on breastfeeding education/counseling
| 5/1/12 | P | P | P | Identify ICD-9 diagnosis code(s) and CPT/HCPCS procedure code(s) that apply.
| 4/20/12 | P | P | P | Meet with internal stakeholders (Bureau of Women's' Health, Bureau of Health Policy, Bureau of Nutrition, etc.) to determine coverage guidelines (certification requirements, reimbursement rates, length & frequency of counseling sessions - prenatally and/or postnatally, individual and/or group, etc.) |  | 4/9/12 -Internal conference call 4/13/12-Internal/external conference call
| 6/1/12 5/21/12 1/12 6/28/12 | P | P | P | Draft/submit SPA. |  | 6/28/12 submitted SPA to CMS
| 8/27/12 9/15/12 | P | P | P | Respond to RAIs from CMS |  | Currently working on responses.
| 12/21/12 10/31/12 9/30/12 1/18/13 | P | P | P | Obtain SPA approval from CMS |  | Per information provided by CMS on conference call, the SPA has been approved. Approval to be sent. 1/24/13 - Continue to await formal CMS approval.
| 5/1/12 5/11/12 | P | P | P | Identify systems impact/changes necessary to implement MRT. |  | 5/11/2012-Internal conference call. Documents in final stages of preparation. Transmittal planned to activate codes.
| 6/1/12 |  |  |  | Submit Evolution project outlining systems edits.
| 8/1/12 5/11/12 | P | P | P | Meet with staff from the Division of Health Plan Contracting & Oversight, the Division of OHIP Operations and the Division of Finance & Rate Setting to facilitate changes. |  | 5/11/2012-Finalized process.
| 8/15/12 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy. |  | 5/22/2012-Draft Medicaid article completed. Plan final review. 8/20/12-Await SPA approval.
| 2/15/13 12/21/12 9/1/12 3/20/13 | P | P | P | Develop outcomes metrics.
| 2/15/13 12/14/12 9/1/12 11/16/12 3/20/13 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees.
| 3/1/13 2/1/13 1/1/13 9/1/12 12/1/12 10/1/12 4/1/13 | P | P | P | Implement policy. |  | Per SPA, the date of implementation will occur the first day of the month following 30 days after SPA approval.
5402E |  |  |  |  | Project Name: Percutaneous Coronary Intervention (PCI) Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Cyndy Sauer, Joan Sicard, Ed Hannon, Anna Colello (OHSM) Description: Limit coverage for PCI to only those patients who are not inappropriate for the procedure based on ACC/AHA appropriateness criteria. | (1.45) | Completed - June 2013
| 7/25/12 6/30/12 4/30/12 9/30/12 | P | P | P | Prepare coverage guidelines based on ACC/AHA appropriateness criteria with input from stakeholders, as appropriate.
| 8/27/12 7/25/12 4/30/12 9/30/12 | P | P | P | Identify ICD-9 diagnosis code(s) and CPT/HCPCS procedure code(s) that apply.
| 2012-05-15 | P | P | P | Make arrangements for exchange of data with between DOH and Cardiac Services Data (contingent on review of Data Exchange Agreement Application).
| 7/25/12 6/30/12 6/1/12 9/30/12 | P | P | P | Develop criteria, exceptions to criteria and an appeals process.
| 9/30/12 7/15/12 6/30/12 | P | P | P | Meet with external and internal stakeholders to review guidelines.
| 9/25/12 | P | P | P | Run trial Medicaid/ Cardiac Services Registry data match
| 11/1/12 | P | P | P | Share PCI policy and billing guidance with Managed Care Plan directors
| 9/30/12 7/15/12 6/15/12 12/14/12 | P | P | P | Meet with IPRO to discuss /set up retrospective review/appeals process.
| 12/21/12 1/31/13 | P | P | P | Share Medicaid Update article outlining policy and billing guidance with HANYS and GNYHA |  | Foster to share
| 12/21/12 | P | P | P | Share Medicaid Update article outlining policy and billing guidance with Managed Care Plan directors |  | Foster to share
| 12/21/12 2/4/13 | P | P | P | Schedule meeting with eMedNY to work out details of FFS takeback (for inappropriate PCIs)
| 3/20/13 | P | P | P | Schedule follow-up meeting with parties involved in data match/transfer.
| 7/31/12 8/31/12 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy. |  | Draft article under internal review (8/1/2012)
| 4/5/13 4/9/13 | P | P | P | Schedule follow-up meeting with DOH and IPRO to continue to work out details regarding notification letter to be sent to providers and process for appeals.
| 5/13/13 | P | P | P | Process for PCI data match, transfer, voiding of claims for inappropriate PCIs, and appeal process outlined and shared with involved parties. Meeting to discuss scheduled.
| 5/29/13 | P | P | P | Set up meeting with M/C and IPRO to discuss aligning M/C appeal process with FFS
| 6/14/13 5/24/13 4/19/13 3/20/13 2/15/13 9/30/12 8/31/12 6/26/13 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees.
| 4/19/13 3/20/13 2/15/13 12/21/12 10/1/12 9/1/12 5/24/13 | P | P | P | Develop outcomes metrics.
| 5/1/13 4/1/13 3/1/13 2/1/13 1/1/13 10/1/12 9/1/12 7/1/13 | P | P | P | Implement policy.
5402F |  |  |  |  | Project Name: Reduce payments for elective Cesarean sections and inductions Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Donna Urban, Joan Sicard, Dr. Marilyn Kacica (OPH) Description: Eliminate coverage of elective C-section deliveries or elective induction of labor less than 39 weeks gestation unless a documented medical indication is present. | (2.50) | Completed - July 2013
| 5/15/12 61/12 | P | P | P | Meet/obtain input from key internal and external stakeholders (Bureau of Women's health, ACOG, NY Chapter of March of Dimes, etc.). |  | 5/15/2012-Initial conference call. 6/1/2012 - follow up meeting with internal/external stakeholders.
| 6/7/12 6/1/12 | P | P | P | Identify medical indications (consensus list) that would necessitate an elective C-section or induction of labor at less than 39 weeks gestation. |  | 8/1/12-ICD-9 Codes isolated (medical indications). Await approval from internal stakeholders for final draft completion.
| 7/1/12 6/7/12 | P | P | P | Identify ICD-9 diagnosis code(s) and CPT/HCPCS procedure code(s) that apply. |  | 8/1/12 ICD-9 codes isolated. Await approval from internal stakeholders for final draft completion.
| 7/1/12 7/13/12 | P | P | P | Determine reduction in reimbursement that would be applied. Integrate quality and safety into overall payment policy. |  | Parameters for reductions in elective deliveries <39 weeks completed.
| 6/7/12 7/1/12 7/20/12 | P | P | P | Prepare coverage guidelines. |  | Consults with Drs. Kacica and Hohmann completed.
| 7/20/12 6/7/12 6/1/12 8/30/12 | P | P | P | Identify systems impact/changes necessary to implement MRT. For physician/practitioner claims, consider developing post-payment / retrospective review process. |  | 8/20/12-Transmittal planned to activate codes pending final internal approval of ICD-9 codes and Modifier.
| 5/15/12 6/1/12 | P | P | P | Discuss options for exceptions with internal and external stakeholders. |  | Completed.
| 5/22/12 7/27/12 | P | P | P | Meet with staff from the Division of Health Plan Contracting & Oversight, the Division of OHIP Operations and the Division of Finance & Rate Setting to facilitate changes. |  | 5/22/2012-Initial telephone conference call.
| 10/15/12 | P | P | P | Develop modifiers (< 39 wks. gestation and 39 wks. or greater gestation) and a process for those case where there is not medical necessity for an elective delivery (C-section or induction) < 39 weeks
| 10/20/12 | P | P | P | Prepare evolution project reducing payment for claims submitted by practitioners, hospitals an birthing ctrs for deliveries < 39 wks. without a justifiable diagnosis code (as determined by internal and external clinical team).
| 2/28/13 | P | P | P | Prepare/submit request for 2 new condition codes to Nat'l Uniform Billing Committee (NUBC) |  | Letter sent to chairman of NUBC - to be presented by Stew Presser
| 10/31/12 12/17/12 | P | P | P | Submit evolution project (following internal review/sign-off)
| 1/7/12 10/31/12 2/15/13 | P | P | P | Develop outcomes metrics. Identify ongoing data source that would allow us to identify providers and practitioners that are outliers. |  | 7/16/12-Met with data staff to outline outcome metrics.
| 7/31/12 8/31/12 | P | P | P | Prepare a Medicaid Update article outlining changes to coverage policy. |  | Draft article completed. Await final ICD-9/modifier.
| 11/2/12 | P | P | P | Share policy and billing guidance with Managed Care Plan directors.
| 12/21/12 2/15/13 | P | P | P | Share Medicaid Update article outlining policy and billing guidance with GNYHA and HANYS |  | To be shared by Foster
| 5/24/13 | P | P | P | Meet with IPRO and eMedNY staff to discuss possible appeal process.
| 6/12/13 | P | P | P | Meet with DOIT staff regarding Evolution projects
| 6/14/13 5/24/13 3/20/13 2/15/13 12/21/12 11/2/12 9/30/12 9/1/12 6/26/13 | P | P | P | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees.
| 6/1/13 4/1/13 3/1/13 1/1/13 12/1/ 12 10/1/12 9/1/12 7/1/13 | P | P | P | Implement policy.
5402G |  |  |  |  | Project Name: Growth Hormone Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Mary Carroll Additional Staff: Tony Merola, John Naoti Description: Limit coverage of growth hormone injections for idiopathic short stature in children. | (5.00) | Completed - Sept 2012 Target Date: 4/1/2012 Fiscal based on SUNY UB preliminary GH report for DURB. Nov 2010- Oct 2011 total spend within FFS populations for ISS indication = $1.12M gross. CMS and Supplemental rebates not included in this fiscal estimate.
| 2012-09-01 | P | P | P | Discuss proposals with UB staff and MRT/DURB member(s) regarding how to approach this initiative within the context of the next DURB meeting.
|  | P | P | P | Add item to DURB March meeting agenda. |  | Item is scheduled to be presented at March 8, 2012 public DUR Board meeting.
| 1/24/12 | P | P | P | Post DURB March meeting agenda.
| 1/31/12 | P | P | P | Provide DURB with background meeting materials to be reviewed during the March meeting.
| 2/9/12 | P | P | P | Discuss proposal with DURB chair and vice chair. |  | Item is posted on DUR website as past of DUR Board meeting agenda.
| 2/14/12 | P | P | P | DURB meeting. |  | GH executive summary report prepared by UB distributed to DURB week of 2/20-24/2012.
| 3/1/12 | P | P | P | Develop a process to eliminate or phase out coverage for GH for ISS. |  | Meeting among DOH Pharmacy Bureau and DURB chair and vice chair scheduled for 2/14/12.
| 3/9/12 | P | P | P | Test system edits to ensure proper POS editing. |  | March 8, 2012
| 3/12/12 | P | P | P | Update MMA map criteria for GH PA requests.
| 3/18/12 | P | P | P | DURB Meeting Summary with recommendations posted on the DOH website.
| 3/30/12 | P | P | P | Send e-blast to providers regarding the elimination of GH coverage for ISS.
| 3/23/12 | P | P | P | Notify beneficiaries currently utilizing GH for ISS.
| 3/23/12 | P | P | P | Notify prescribers utilizing GH in beneficiaries with ISS.
| 3/30/12 5/3/12 | P | P | P | Implement initiative via enhanced pharmacy system edits at point of service.
5402H |  |  |  |  | Project Name: Tobacco Cessation Counseling by Dentists Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Linda Palmer, Mark Tremblay, Donna Haskin, Lee Perry, DDS, Jay Kumar, DDS Description: Enable dentists to be reimbursed by Medicaid for delivering smoking cessation counseling. | (4.25) | Completed - 2013-2014 enacted Budget
Resolve potential scope of practice issues with SED.
Meet with internal stakeholders to discuss provider-specific reimbursement rates.
Identify provider-specific CPT/HCPCS procedure codes.
Identify systems impact/changes necessary to implement MRT. Consider developing pre-payment edits vs. post-payment review process.
Submit Evolution Project outlining systems edits.
Meet with staff from the Division of Health Plan Contracting & Oversight, the Division of OHIP Operations and the Division of Finance & Rate Setting to facilitate changes.
Update Provider Manuals and guidance documents.
Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees.
Implement policy.
Develop outcomes metrics.
5403 |  |  |  |  | Project Name: Benefit Reforms Related to Waiver Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: See Below Description: Specific benefit reforms 5403A: Obesity Treatment 5404B: Nurse Family Partnership (NFP)
5403A |  |  |  |  | Project Name: Obesity Treatment Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Cyndy Sauer, Andrea Swire, Joan Sicard, Dr. Barbara Dennison (OPH) Description: Cover intensive behavioral therapy for treatment of obesity. |  | Cancelled
| 2012-06-01 |  |  |  | Review USPSTF guidelines, recommendations for coverage by the AAP and CMS's recommendations for coverage.
| 2012-06-22 |  |  |  | Meet with/obtain input from internal and external stakeholders to discuss reimbursement rates, length & frequency of counseling sessions, practitioners who may provide the service, age of recipients, etc.
| 2012-07-06 |  |  |  | Prepare coverage guidelines.
| 2012-07-18 |  |  |  | Waiver submission - provide supporting documentation/language for DOH.
| 2012-07-25 |  |  |  | Identify systems impact/changes necessary to implement MRT.
| 7/18/12 |  |  |  | Meet with staff from the Division of Health Plan Contracting & Oversight, the Division of OHIP Operations and the Division of Finance & Rate Setting to facilitate changes.
| 7/25/12 |  |  |  | Prepare a Medicaid Update article outlining changes to coverage policy.
| 2012-08-15 |  |  |  | Update Provider Manuals and guidance documents.
| 2012-08-30 |  |  |  | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees..
| 2012-09-15 |  |  |  | Implement policy.
| 2012-10-01 |  |  |  | Develop outcomes metrics.
5403B |  |  |  |  | Project Name: Nurse Family Partnership (NFP) Division Lead: Greg Allen / Division of Program Development and Management Team Lead: Constance Donohue, Ron Bass Additional Staff: Cris Carter, Melissa Kinnicut, Joan Sicard, Bev Paisley, Dr. Richard DeLong Description: Expand Medicaid coverage for all services under the NFP, and additionally expand coverage to the entire State. |  | Complete Included in MRT Waiver
| 2012-10-01 | 8 | 8 | 8 | Research national models of NFP program. |  | In Progress
| 2012-08-15 | P | P | P | Met with nat'l representatives from NFP, external stakeholders and public health colleagues to discuss the National NFP model and options for NYS
| 2012-05-21 | 8 | 8 | 8 | Meet with internal stakeholders to define roles and responsibilities for MRT development and implementation. |  | To be included in 1115 Mega waiver
| 2012-06-01 | 8 | 8 | 8 | Define Medicaid covered services for potential addition to NFP
| 2012-06-08 | 8 | 8 | 8 | Identify systems impact/changes necessary to implement MRT.
| 2012-06-15 | 8 | 8 | 8 | Submit Evolution project outlining systems edits.
| 2012-07-15 | 8 | 8 | 8 | Meet with staff from Division of OHIP Operations and the Division of Finance & Rate Setting to facilitate changes.
| 2012-08-15 | 8 | 8 | 8 | Meet with internal and external stakeholders to discuss reimbursement rates, provider capacity for each potential county/region.
| 2012-09-07 | 8 | 8 | 8 | Waiver submission - provide supporting documentation/language for DOH.
| 2012-10-01 | 8 | 8 | 8 | Update Provider Manuals and guidance documents.
| 2013-01-10 | 8 | 8 | 8 | Educate Helpline and CSC staff to ensure that accurate policy information is communicated to providers and enrollees.
| 2013-02-01 | 8 | 8 | 8 | Develop outcomes metrics.
| 2013-02-07 | 8 | 8 | 8 | Prepare Medicaid Update article outlining changes to coverage policy.
| 2013-04-01 | 8 | 8 | 8 | Implement policy.

## Ph 2 Workforce
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5501 |  |  |  |  | Project Name: Advisory Committee to the Office of the Professions of the State Education Department. Division Lead: Lisa Ullman OPCHSM Team Lead: Barry Gray Additional Staff: Tom Burke, Caleb Wistar Description: Establish an Advisory Committee to the Office of the Professions of the State Education Department that supports collaborative, comprehensive and systematic assessments of proposals designed to improve health workforce flexibility in the state, including, but not limited to proposals to develop, expand or modify scopes of practice for health care professionals and/or scopes of services for assistive health personnel. |  | Cancelled - DOH and SED have had discussions on scope of practice issues on a case-by-case basis due to their complexity.
| 5/30/13 6/11/13 | P | P | P | Meet with SED to discuss roles/responsibilities and the structure and processes for an advisory workgroup to the NYS Regents health care workgroup
| 6/30/13 7/31/13 | P | P | P | Identify study group that frames health workforce issues and presents findings to the Regents. Study group may consist of representatives from DOH, SED, DOL, SUNY, CUNY and the NYS Center for Health Workforce Studies
| 7/15/13 8/15/13 8/20/13 | P | P | P | Nominate members; Get DOH/SED approvals for membership
| 6/11/13 ongoing to 7/1/14 | P | P | P | Identify potential scope of practice proposals to research; conduct research (ongoing and iterative)
| 6/30/13 7/31/13 7/1/14 8/31/13 ongoing to 7/1/14 | P | P | P | Obtain DOH and SED approvals for proposed research
| 8/11/13 8/31/13 7/1/14 9/30/13 ongoing to 7/1/14 | P | P | P | Present to Regents research and possible recommendations, as requested
| 8/11/13 8/31/13 7/1/14 9/30/13 ongoing to 7/1/14 | P | P | P | Make regulatory or legislative recommendations, as appropriate
| 2014-07-03 | P | P | P | Develop work plan and identify additional workgroup members
| 2014-08-13 | P | P | P | Convene kickoff meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2014-09-10 | P | P | P | Convene second meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2014-10-07 | P | P | P | Convene third meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2014-11-05 | P | P | P | Convene fourth meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2014-12-02 | P | P | P | Convene fifth and final meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 12/2/14 12/22/14 | P | P | P | Convene sixth meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2/23/15 2/3/15 | P | P | P | Convene sixth seventh meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 3/2/15 2/23/15 | P | P | P | Convene seventh eighth and final meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 2015-03-02 | P | P | P | Convene ninth and final meeting of stakeholders to develop tasks and curricula for Advance Home Health Aides
| 12/15/14 1/2/15 2/2/15 2/12/15 3/6/15 3/18/15 | P | P | P | Draft and disseminate recommendations document.
| 4/1/15 5/1/15 6/1/15 | 8 | 8 | 8 | Develop policies and next steps
| 1/2/15 2/15/15 2/28/15 3/15/15 4/15/15 5/15/15 6/15/15 | 8 | 8 | 8 | Secure executive approval of policies and next steps.
5502 |  |  |  |  | Project Name: Scope of Practice Changes: Legislative Initiative Division Lead: Lisa Ullman OPCHSM Team Lead: Caleb Wistar Additional Staff: See below Description: Multiple statutory scope of practice changes 5502A: Advanced Aides 5502B: Advanced Home Care Aide Certification 5502C: Remove collaboration practice agreement requirement for Certified Nurse Practitioners 5502D: Collaborative Practice of Dental Hygienists/Definition of Dental Hygiene 5502E: Removal of physician supervisory ratio of physician assistants (PAs) 5502F: Children’s Dental Health Certificate |  | Pending 15-16 Budget Suspended pending 2015 program bill or 2016-2017 budget
5502A |  |  |  |  | Project Name: Advanced Aides Division Lead: Caleb Wistar OPCHSM Team Lead: Becky Gray Additional Staff: Diane Jones, Marjorie Brier Lynch Description: Permit home care providers, including LHCSAs, CHHAs, LTHHCPs, MLTCPs, and home hospices to identify non-self-directing consumers who can be safely assisted by an Advanced Aide to take routine pre-poured medications, including routine pre-filled injections of insulin, as is currently permitted for self-directing individuals under “special circumstances”. |  | Pending 15-16 Budget Cancelled
| 2014-04-01 | T | T | T | Rejected.
| 2014-06-03 | P | P | P | Re-introduced as Program bill 37; includes 5502A and 5502B
| 2014-06-20 | T | T | T | Rejected.
| 2015-04-01 | T | T | T | Rejected.
| 2015-01-21 | P | P | P | Re-introduced in Governor's proposed Article VII budget; includes 5502A and 5502B
5502B |  |  |  |  | Project Name: Advanced Home Care Aide Certification Division Lead: Caleb Wistar OPCHSM Team Lead: Becky Gray Additional Staff: Diane Jones, Marjorie Brier Lynch Description: Create an advanced home care aide certification and outline the minimum training and qualifications required. Training would focus on accurate reporting, communication skills and problem solving. Registered Nurses, based on their assessment of the advanced home care aide, the self-directing resident and the home care environment, would assign an expanded range of tasks to Advanced Aides, under the same requirements and restrictions currently outlined for tasks which can be assigned to home health aides in “special circumstances.” The expanded range of tasks would be determined through a stakeholder process directed by the Department. |  | Cancelled
| 2014-04-01 | T | T | T | Rejected.
| 2014-06-03 | P | P | P | Re-introduced as Program bill 37; includes 5502A and 5502B
| 2014-06-20 | T | T | T | Rejected.
| 2015-01-21 | P | P | P | Re-introduced in Governor's proposed Article VII budget; includes 5502A and 5502B
| 2015-04-01 | T | T | T | Rejected.
5502C |  |  |  |  | Project Name: Remove collaboration practice agreement requirement for Certified Nurse Practitioners Division Lead: Caleb Wistar OPCHSM Team Lead: Wendy Shaw, DFH Additional Staff: Rachel DeLong, DFH Description: Remove the requirements for written collaboration agreements and written practice protocols between nurse practitioners and physicians. |  | Completed - April 2014
| 2014-04-01 | P | P | P | Approved
5502D |  |  |  |  | Project Name: Collaborative Practice of Dental Hygienists/Definition of Dental Hygiene Division Lead: Caleb Wistar OPCHSM Team Lead: Jay Kumar (check) Additional Staff: (check) Description: Amend statute and regulation to allow for the practice of dental hygiene under a collaborative practice agreement rather than under the supervision of a licensed dentist. Redefine the practice of dental hygiene in accordance with the dental hygiene process of care. |  | Completed - May 2013
| 2013-04-01 | T | T | T | Rejected by Senate
| 2013-05-14 | P | P | P | Meet to develop next steps for potential program bill.
| 2013-05-30 | P | P | P | Develop bill language per 5/14/13 meeting; secure Executive approval.
| 6/15/13 6/24/13 | P | P | P | Secure Legislative approval of bill; enact bill.
5502E |  |  |  |  | Project Name: Removal of physician supervisory ratio of physician assistants (PAs) Division Lead: Caleb Wistar OPCHSM Team Lead: Mary Ellen Hennessey (check), Caleb Wistar Additional Staff: Description: Removes the arbitrary restriction on the number of physician assistants a physician may supervise, allowing this to be determined by the physician at the practice or facility. |  | Completed-Feb Mar 2015
| 2013-04-01 | P | P | P | Enacted in 13-14 Education Bill, Part T.
| 2013-03-29 | P | P | P | Submit to DLA draft "consensus regulations" to amend 10 CFR 94.2 to conform to legislation.
| 4/15/13 5/15/13 6/1/13 6/30/13 7/10/13 | P | P | P | DLA approves draft reg
| 5/15/13 6/1/13 6/15/13 7/15/13 | P | P | P | Reg approved by Commissioner
| 6/1/13 6/15/13 6/30/13 7/30/13 8/14/13 | P | P | P | Reg submitted to Department of State for posting to State Register |  | Published 8/14/13; advised by DLA that a full reg is now needed, as there were relevant comments by stakeholders on the consensus reg.
| 2013-09-15 | P | P | P | Submit to DLA draft amended "full regulation" to amend consensus reg re: 10 CFR 94.2 to conform to legislation.
| 10/1/13 10/15/13 11/1/13 12/2/13 12/27/13 | P | P | P | DLA, Commissioner approves draft amended reg
| 10/15/13 10/30/13 11/15/13 12/15/13 1/15/14 2/3/14 | P | P | P | Reg approved by Executive
| 11/1/13 11/18/13 12/18/13 1/18/14 2/6/14 | P | P | P | Reg submitted to Department of State for posting to State Register
| 11/30/13 12/17/13 1/17/14 2/1/14 2/15/14 4/15/14 | P | P | P | Comment period ends |  | This was posted on 2/26/14; public comment period ended 4/14/14.
| 2014-05-09 | P | P | P | DLA determined that a new round of public comment needed based on OPCHSM/BNE recommendation.
| 6/30/14 7/30/14 7/10/14 | P | P | P | DLA to prepare and approve new round of rulemaking
| 7/30/14 8/31/14 7/10/14 | P | P | P | Rule approved by Acting Commissioner
| 8/30/14 9/30/14 10/14/14 | P | P | P | Rule approved by DOB, Executive
| 6/30/14 10/30/14 11/28/14 | P | P | P | Additional public comment period completed.
| 1/28/15 3/18/15 | P | P | P | Regulation adopted.
5502F |  |  |  |  | Project Name: Children’s Dental Health Certificate Division Lead: Caleb Wistar OPCHSM Team Lead: Jay Kumar (check) Additional Staff: (check) Description: Amend education law, Section 903, 2.a. to include Registered Dental Hygienists as an additional oral health provider able to perform the school readiness oral health examination and by means of follow-up, case manage to enroll children within a dental home. |  | Completed - Aug 2013
| 2013-04-01 | P | P | P | Enacted in 13-14 Education Bill, Part S.
| 5/15/13 6/3/13 6/14/13 | P | P | P | Meet with SED to identify the changes required to implement the law.
| 8/1/13 7/15/13 | P | P | P | Revise SED guidance documents and SED website to reflect the changes
| 7/1/13 8/1/13 | P | P | P | Communicate with stakeholders (e.g., NYS Dental Society and NYS Dental Hygienists Assoc.)
5503 |  |  |  |  | Project Name: Scope of Practice Changes: Regulatory Changes Division Lead: Lisa Ullman OPCHSM Team Lead: Barry Gray Additional Staff: Description: Multiple regulatory scope of practice changes 5503A: Standing Orders/Physician Practice Protocols 5503B: Enable physician home visits 5503C: Stackable certification and credentials for direct care workers |  | Competed Jan 2016
5503A |  |  |  |  | Project Name: Standing Orders/Physician Practice Protocols Division Lead: Barry Gray OPCHSM Team Lead: Caleb Wistar, Gus Birkhead Description: Enable the use of practice protocols, or “standing orders” in defined situations consistent with recently announced CMS rule changes/prevailing national standards intended to improve the quality of care and efficiency of delivery. |  | Cancelled
| 2014-06-05 | P | P | P | Convene meeting with OPCHSM and DLA regarding need for regulation versus statute change. Will flesh out work plan after meeting.
| 6/13/14 | P | P | P | Develop position paper regarding policies and next steps
| 7/1/14 7/30/14 10/30/14 | P | P | P | Get executive sign-off on paper and develop next steps on work plan.
| 11/15/14 11/14/14 | P | P | P | Convene internal (DOH) expert panel to recommend additional evidence-based regimens to existing roster; e.g., mandatory administration of newborn prophylaxis and other immunizations, and other protocols in emergency departments for conditions such as acute asthma, acute myocardial infarction, transient ischemic attacks and other types of stroke.
| 2014-11-30 | P | P | P | Panel submits recommendations to DOH for approval; next steps in work plan developed as appropriate.
| TBD | 8 | 8 | 8 | Additional actions on hold.
5503B |  |  |  |  | Project Name: Enable physician home visits Division Lead: Barry Gray OPCHSM Team Lead: John Gahan Additional Staff: Description: Allow all Article 28 licensed hospitals and D&TCs to provide practitioner home visits services to chronically ill, homebound Medicaid patients. |  | Cancelled
| 2012-10-30 | P | P | P | Meet internally with OHIP staff to develop policy issues to be resolved.
| 11/28/12 12/15/12 12/26/12 | P | P | P | Finalize federal public notice for hospitals and clinics
| 12/14/12 1/16/13 | T | T | T | Work plan on hold pending discussions with CMS |  | CMS OKs approach for proposal March 2013
| 12/17/12 1/30/13 3/25/13 | P | P | P | Submit SPA to CMS for approval. Effective date of new rates 1/1/13 when SPA approved |  | SPA submitted 3/25/13
| 1/1/13 | 8 | 8 | 8 | Effective date of new rates
| 11/19/12 12/3/12 4/1/13 4/15/13 5/30/13 6/3/13 | P | P | P | Meetings with hospital associations.
| 11/19/12 12/3/12 4/1/13 4/15/13 5/30/13 6/6/13 6/30/13 7/22/13 | P | P | P | Meetings with clinic associations
| 6/30/13 7/15/13 8/14/13 | P | P | P | Complete DLA review of proposal's consistency with Part 401 of regs and issue of allowing home visits as locations which are not licensed or otherwise approved as service locations.
| 7/15/13 8/1/13 8/15/13 8/21/13 9/15/13 | P | P | P | Meet internally with OHSM staff to develop plan to draft and enact revisions to relevant regulations. additional policy issues to be resolved.
| 2013-10-01 | P | P | P | Draft plan/policy document describing proposed revisions to relevant regulations.
| 2014-06-05 | P | P | P | Internal meeting to re-visit policy re: MD home visits.
| 10/15/13 11/1/13 12/2/13 1/2/14 2/1/14 3/1/14 4/1/14 5/1/14 6/1/14 6/12/14 7/1/14 | P | P | P | Secure DOH executive approval for proposed revisions. Begin revision process for regulation changes.
| 10/30/12 11/26/12 4/30/13 6/15/13 8/15/13 10/15/13 11/15/13 12/16/13 1/16/14 2/16/14 3/16/14 4/15/14 5/15/14 6/15/14 6/30/14 7/30/14 12/19/14 | P | P | P | Complete development of billing policies and initial impacts related to physician home visits working with stakeholders (associations and providers)
| 11/30/12 12/15/12 4/30/13 6/30/13 8/31/13 10/31/13 11/30/13 12/31/13 1/31/14 2/28/14 3/28/14 4/30/14 5/30/14 7/30/14 12/17/14 | P | P | P | Finalize estimated Medicaid fiscals related to this new service
| 12/17/12 1/1/13 4/30/13 6/30/13 8/31/13 10/31/13 11/30/13 12/31/13 1/31/14 2/28/14 3/28/14 4/30/14 5/30/14 6/30/14 7/15/14 8/15/14 12/18/15 | P | P | P | Determine if draft regulations in 86-8-APG rates needed; if so, develop regulations and add relevant steps to work plan.
| 2014-12-22 | P | P | P | Complete the SPA RAI based on 12/17/19 meeting and email to all on meeting notice for their review.
| 2015-01-06 | P | P | P | Meet with hospital associations to finalize SPA RAI and effective date.
| 12/17/12 1/1/13 4/30/13 6/30/13 8/31/13 10/31/13 11/30/13 12/31/13 3/15/14 4/15/14 5/15/14 6/15/14 7/31/14 9/1/14 1/12/15 | P | P | P | Submit evolution project to EMedNY for new rates, if needed. |  | Is this needed? Probably not, per Janet.
| 8/1/15 4/1/15 5/6/15 TBD | 8 | 8 | 8 | Regulation changes to policy approved. NOTE: This pertains to the action completed on 7/1/14 above, not to the potential RBRVS.
| 6/1/15 TBD | 8 | 8 | 8 | CMS approves SPA related to home visit billing for Medicaid. |  | Depends on when the reg gets finalized
| 12/28/12 1/15/13 6/30/13 8/30/13 10/31/13 11/30/13 12/31/13 1/31/14 4/1/14 5/1/14 6/1/14 7/1/14 8/15/14 8/15/15 5/1/15 7/1/15 TBD | 8 | 8 | 8 | Communicate with and educate providers |  | Depends on when the reg gets finalized
5503C |  |  |  |  | Project Name: Stackable certification and credentials for direct care workers Division Lead: Barry Gray OPCHSM Team Lead: Becky Gray Additional Staff: Diane Jones, Marjorie Brier Lynch, Beth Dichter Description: Articulate training from PCA to HHA to CNA in order to avoid repeating training already received and demonstrated. |  | Cancelled
| 2012-05-15 | P | P | P | Identify initial In-house staffing needs and resources to review existing curriculums and education requirements and identify differences
| 2012-10-12 | 8 | 8 | 8 | Identify key Stakeholders including industry representatives; other state agencies; DOH home and community based programs that will be impacted potentially by any needed changes to curriculums and competency testing requirements
| 2012-11-05 | 8 | 8 | 8 | Schedule Stakeholder meetings/identify members: SED, Nursing home and home care representatives
| 2012-10-15 | 8 | 8 | 8 | Develop agendas and work plan objectives for stakeholder meetings
| 2012-11-05 | 8 | 8 | 8 | Identify chairperson(s) and workgroup leads
| 12/3/12 3/1/13 5/1/13 6/1/13 7/1/13 7/15/13 8/15/13 9/15/13 11/4/13 | P | P | P | Solicit stakeholder input to realign guidelines and training in the paraprofessional workforce. consistent with the structure and process to be created for proposal 5501
CURRICULUM DEVELOPMENT
| 2012-12-01 | P | P | P | Identify changes required in curriculums to articulate training from the PCA to Certified NA in order to avoid repeat training
| 6/1/13 8/1/13 10/1/13 12/31/13 | P | P | P | Develop curricula that encompass minimum training and qualifications that articulate training requirements from PCA to HHA to Certified NA. Identify need for any contractual curricula development if necessary.
BUDGET DEVELOPMENT
| 6/1/13 8/1/13 10/1/13 11/15/13 1/31/14 4/1/15 2/1/16 11/1/15 | 8 | 8 | 8 | Identify Budget Components- costs for system changes; training development and curriculum, research, design and implementation |  | Likeliest time would be next budget season (SFY 16-17)
| 2/28/13 4/30/13 5/15/13 1/31/14 4/1/15 4/1/16 12/1/15 | 8 | 8 | 8 | Develop budget for system changes required for home care registry, CNA registry, CHRC, HHATP and PCATP data bases
TRAINING, POLICY AND PROCEDURE DEVELOPMENT
| 4/15/15 4/15/16 | 8 | 8 | 8 | Collaborate with the SED on any associated changes with aide training curricula
| 8/1/15 8/1/16 | 8 | 8 | 8 | Develop provider training for impending registry changes
| 10/15/15 10/1/16 | 8 | 8 | 8 | Conduct provider training as necessary regarding changes to be made to training program requirements through webinar and other means
| 12/1/15 12/1/16 | 8 | 8 | 8 | Post DAL's to the HPN to home care agencies, nursing homes and training programs
| 10/1/15 12/1/16 | 8 | 8 | 8 | Revise surveillance training to surveyors and disseminate revised materials to regional offices
| 1/15/16 1/15/17 | 8 | 8 | 8 | Work with stakeholder organizations to develop FAQ document(s) to respond to questions, if needed.
REGULATION DEVELOPMENT AND REVISIONS IF NEEDED
| 4/15/13 6/15/13 8/15/13 10/15/13 11/1/13 2/4/14 4/1/15 4/1/16 | 8 | 8 | 8 | Draft revised home care regulations for Title 10 parts 400, 700, 763, 765 and 766 and Title 18 part 505
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Prepare notice to state register for publication of regulations | Draft revised home care regulations for Title 10 parts 400, 700, 763, 765 and 766 and Title 18 part 505
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Secure Governor's Counsel's Office approval of revised regulations.
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Present regulations to PHHPC Code Committee for discussion
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Present to PHHPC for discussion
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Revise regulations, if necessary
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Publish proposed regulations in State Register
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | 45-day comment period
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Prepare response to public comments
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Present regulations to PHHPC Codes Committee for recommendation and to full Council for adoption.
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Publish Notice of Adoption in State Register
| 4/15/13 6/15/13 8/15/13 10/15/13 ongoing to 4/15/15 4/15/16 | 8 | 8 | 8 | Draft DAL informing providers of revised requirements and effective dates
| 4/15/15 4/15/16 | 8 | 8 | 8 | Post DAL's to the HCS informing providers of the revised regulation policy and procedure
5504 |  |  |  |  | Project Name: New York State Primary Care Service Corps (PCSC) Division Lead: Karen Westervelt OPCHSM Team Lead: Caleb Wistar Additional Staff: Tom Burke; Mike Reynolds (HESC); Bill Lawton Description: The NYS PCSC is a service-obligated loan repayment program to be administered by DOH. Its purpose would be to increase the supply of midwives, nurse practitioners and physician assistants and others who practice in underserved communities. Eligible clinicians would receive loan repayment funding in return for a commitment to practice in an underserved area. |  | Completed - Mar 2013 (3/15/13)
| 2012-06-02 | P | P | P | Apply for matching funding prospectively under the federal State Loan Repayment Program (SLRP)
| 2012-04-01 | P | P | P | Secure funding to support PCSC (contingent on Budget)
| 2012-04-30 | P | P | P | Convene a “PCSC” development committee consisting of representatives of OHSM, the Primary Care Office, Public Affairs Group, the Office of Health Disparities Prevention and the Higher Education Services Corp (HESC)
| 2012-05-15 | P | P | P | Develop program guidelines with advice and consent of the development committee
| 2012-06-29 | P | P | P | Draft a Request for Applications (RFA)
| 10/15/12 11/30/12 12/11/12 | P | P | P | Draft and execute inter-agency memorandum of agreement (MOA) between DOH and HESC related to the roles and responsibilities of DOH and HESC
| 10/30/12 11/30/12 1/2/13 1/31/13 2/15/13 3/1/13 3/11/13 | P | P | P | Secure all approvals for RFA
| 11/15/12 12/15/12 1/15/13 2/15/13 2/28/13 3/15/13 | P | P | P | Issue RFA on DOH website. Work with development committee to publicize and disseminate word on the availability of RFA and funding
5505 |  |  |  |  | Project Name: Exempt license requirement for certain titles in NYS agencies Division Lead: Office of Mental Health / OPCHSM Team Lead: Henry Fernandez Additional Staff: John Tauriello Jay Zucker Description: Extend authorization permanently to July 1, 2016 in the Education Law that currently permits the activities or services on the part of specific titles in the employ of a program or service operated, regulated, funded, or approved by New York State Agencies to continue to serve without licenses in their current capacities. |  | Suspended Pending 2016-2017 Budget
| 2013-04-01 | P | P | P | Enacted in 13-14 State Education Law, Part AA.
| 9/1/14 10/1/14 | P | P | P | State agencies included in the exemption to provide data and recommendations to the Commissioner of Education on the number of individuals employed in exempt programs operated, funded, regulated or approved by each state agency.
| 11/10/14 11/24/14 12/10/14 | P | P | P | SED shares a written draft with the exempt agencies, as well as the interested parties identified in statute, for review and comment.
| 1/1/15 2/2/15 | P | P | P | SED releases final report with the exempt agencies, as well as the interested parties identified in statute.
| 2015-10-01 | 8 | 8 | 8 | State agencies provide DOB and Governor's office w/data and recommendations concerning continued need for permanent exemption. |  | Temporarily suspended
5506 |  |  |  |  | Project Name: Promote programs such as CDPAP Division Lead: Barry Gray OPCHSM Team Lead: Leslie Galusha, Additional Staff: Margaret Willard Description: Promote underutilized programs such as the Consumer Directed Personal Assistance Program that are cost-effective and build on consumers’ strengths. |  | Completed - June 2012
|  | P | P | P | Referred to MLTC project 5203, Workgroup on integration of self-directed program models
| 2012-03-02 | P | P | P | Provide assessment of progress to date and effectiveness of current program. (quarterly report due 3/2)
| 2012-03-30 | P | P | P | Check on funding stream to ensure it is extended through SFY 2012-13 (funding included)
| 3/30/12 | P | P | P | Provide an opportunity for CDPAP to complete its initial implementation phase and demonstrate the effectiveness of its outreach and education efforts. (pending contract extension ends 5/31/12)
| 6/15/12 | P | P | P | Extend current contract.

## Ph 2 Payment Reform (Completed)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5601 |  |  |  |  | Project Name: Integrate Medicaid & Medicare service delivery and financing Division Lead: DLTC Team Lead: Mark Kissinger Additional Staff: Description: Pursue partnership agreement with CMS to integrate Medicaid & Medicare service delivery and financing for the dual eligible population. |  | Merged with #90
See MRT #90, Mandatory Enrollment in MLTC Plans/Health Home Conversion
5602 |  |  |  |  | Project Name: Quality Measurement Division Lead: DQIE Team Lead: Pat Roohan Additional Staff: Description: Continue to collect quality data on Medicaid managed care and Managed long term care (MLTC); begin measurement of Health Home populations in 2012-2013; begin measurement of mental health/substance abuse in 2012; begin measurement of long term care (outside of MLTC) in 2012; expand measurement of mental health/substance abuse in 2013-2014; expand measurement of long term care in 2013-2014. |  | Completed - May 2012
| 2012-05-25 | P | P | P | Post Quality Metrics to MRT Website
5603 |  |  |  |  | Project Name: Indigent Care Funding Program Division Lead: DFRS Team Lead: Roland Guilz Ann Foster Additional Staff: Ann Heilmann, Kevin Wright, Doreen Caffery, Matt Lomaestro Adele Compton and Maureen Flanagan Description: Reform the New York State Indigent Care Program. |  | Completed
| 2012-02-09 | P | P | P | Discuss project goals, presentation format and anticipated timeline. Determine staff who will participate. |  | Project will need to have a compressed schedule to meet aggressive timeline.
| 2012-02-10 | P | P | P | Provide associations with necessary data and files to begin discussions. |  | Send to contacts at HANYS and GNYHA.
| 2012-02-15 | P | P | P | Meet with associations mid-week to discuss data provided by the Department and obtain their views on how the distribution methodology should be revised to conform with Federal Law. |  | These discussions will be important to determine direction of modeling.
| 2012-02-22 | P | P | P | Complete PowerPoint presentation and obtain sign-off from DOH senior staff. |  | Modify to include any information necessary from association discussions.
| 2012-02-24 | P | P | P | Complete first round of modeling. |  | This will be a time consuming process.
| 2012-02-29 | P | P | P | Share approved models with associations for feedback. Obtain any information or models they may have developed based on data shared by DOH in the prior week. Determine a transition model that is acceptable to all parties. |  | Associations should be aware of DOH's intent to "own" modeling responsibilities.
| 2012-03-02 | P | P | P | Make necessary modifications to and finalize model based on industry feedback. Share with DOH senior staff, DOB and Governor's Office. |  | May take additional time depending on industry feedback.
| 2012-03-02 | P | P | P | Request DOH Counsel draft Article VII and appropriation language for inclusion in Budget. |  | May want to have separate appropriations for various categories of facilities. Discuss with DOB to ensure proper breakout in appropriations.
| 2012-03-02 | P | P | P | Present reform methodology to MRT Workgroup members and obtain sign-off. |  | If possible, information should be shared throughout the process to keep necessary individuals in loop.
| 2012-03-07 | P | P | P | Final MRT Workgroup Recommendation presented to Legislature. |  | It is likely the necessary individuals will be aware of DOH's recommendations from MRT discussions and will have shared information with key players.
| 2012-06-21 |  |  |  | Obtain Legislative approval of Reform package as a Governor's Program Bill. UNSUCCESSFUL IN HAVING BILL INTRODUCED |  | Pending next budget.
| 2012-07-27 | 8 | 8 | 8 | Submit proposed regulations for approval. |  | To be done shortly after Leg. approval.
| 2012-08-31 | 8 | 8 | 8 | Post all appropriate materials to DOH website. |  | Soon after providers are notified.
| 2012-12-31 | 8 | 8 | 8 | Submit Federal Public Notice to Department of State |  | Needs to be done by the day prior to effective date.
| 2013-01-01 | 8 | 8 | 8 | Begin discussions with CMS on State Plan Amendment. |  | Work to ensure timely approval of Plan.
| 2013-03-01 | 8 | 8 | 8 | Submit State Plan Amendment to CMS. |  | Needs to be done within the quarter the proposal is effective.
| 2013-04-01 | 8 | 8 | 8 | Notify providers of 2013 distributions. |  | Via letter or email blast.
| 2013-04-25 | 8 | 8 | 8 | Transmit distributions to providers. |  | Through OPA.
| ongoing | 8 | 8 | 8 | Answer provider phone calls and questions. |  | Call volume may be heavy upon initial notification and initial distributions.
FINANCIAL AID LAW EDUCATION
| 2012-06-15 | P | P | P | Meet with KPMG to discuss inclusion of FAL review in ICR Audit.
| 2012-06-22 | P | P | P | Meet with OHSM to obtain input. |  | Ruth Leslie and Lora Lefebvre
| 2012-06-27 | P | P | P | Meet with Associations to inform them of DOH's intentions to include FAL in ICR Audit.
| 2012-07-11 | P | P | P | Participate in KPMG educational "kick off" webinar with industry to discuss FAL review.
| 2012-08-14 | P | P | P | Educational webinar at HANYS |  | Roland Guilz/Mike Ogborn/Ruth Leslie to attend and present.
| 2012-11-30 | P | P | P | Begin reviewing results of Year 1 audit.
| 12/31/12 3/1/13 | P | P | P | Develop strategies with Industry/Associations to improve hospital performance in Year 2 audits.
| 12/31/12 3/1/13 3/15/13 | P | P | P | Provide additional education to industry based on year 1 findings.
| 4/15/13 5/15/13 5/31/13 6/15/13 7/1/13 8/7/13 9/6/13 9/20/13 10/18/13 10/31/13 11/4/13 | P | P | P | Transmit Revised FAL Questionnaire to hospitals |  | Met and shared questionnaire with associations. Received additional comments from GNYHA. Revised questionnaire, letter and checklist sent to hospitals via HCS.
| 4/15/13 5/15/13 5/31/13 6/15/13 7/1/13 8/7/13 9/6/13 9/20/13 10/18/13 10/31/13 11/4/13 | P | P | P | Transmit Dear Administrator Letter to hospitals providing further guidance. |  | Met and shared questionnaire with associations. Received additional comments from GNYHA. Revised questionnaire, letter sent to hospitals via HCS.
| 5/1/13 6/1/13 6/30/13 8/31/13 9/30/13 10/31/13 | P | P | P | Review year 2 findings. |  | Findings have been reviewed, incorporating results into scoring matrix.
| ongoing 7/31/14 | P | P | P | Continued education and review. |  | Another webinar to be scheduled to explain the distributions of the Financial Aid Law Compliance funds and to provider guidance for those hospitals deemed out of compliance.
INDIGENT CARE REFORM
| 2012-08-28 | P | P | P | Present Indigent Care Reform Methodology at HANYS Retreat |  | Meetings and Presentations with various stakeholders will be ongoing leading up to the Executive Budget release.
| 9/21/12 10/31/12 | P | P | P | Present Indigent Care Reform Methodology to Medicaid Matters (Lara Kassel) and other stakeholders
| 2012-11-15 | P | P | P | Present Indigent Care Financial Aid Law Reform Measures to Medicaid Matters (Lara Kassel) and other stakeholders
| 2012-12-01 | P | P | P | Include Reform as part of 2013-14 Executive Budget
| 2012-12-31 | P | P | P | Submit Federal Public Notice to Department of State |  | Needs to be done by the day prior to effective date.
| 2013-01-23 | P | P | P | Brief Legislature on Indigent Care Reform bill |  | Present PowerPoint slides and explain bill at legislative briefing.
| 2013-02-06 | P | P | P | Requested a 21-day amendment to not sunset the Major Academic Medical Center grants as part of the Indigent Care Pool Reform bill. |  | The statutory authority for these grants is imbedded in the existing Indigent care Pool statute, and should not be terminated as part of ICP Reform.
| 2013-02-06 | P | P | P | Discuss impacts with hospital associations and transmit impacts to DOB |  | Impact schedules transmitted to associations and DOB
| 1/1/13 2/1/13 2/13/13 | P | P | P | Begin discussions with CMS on State Plan Amendment. |  | Work to ensure timely approval of Plan.
| 3/1/13 3/15/13 3/20/13 | P | P | P | Submit State Plan Amendment to CMS. |  | Needs to be done within the quarter the proposal is effective.
| 2013-03-20 | P | P | P | Achieve legislative approval of proposed bill language |  | Senate has agreed to Executive and Assembly language with a minor modification.
| 4/15/13 5/15/13 5/31/13 6/15/13 | P | P | P | Submit Regulations detailing Indigent Care Reform methodology |  | Regulations have been submitted to Governor's Office. Responding to questions from Governor's Office. Ready to be approved.
| 4/15/13 5/15/13 5/31/13 6/15/13 | P | P | P | Submit Regulations detailing Indigent Care Reform methodology |  | Regulations have been submitted to Governor's Office. Responding to questions from Governor's Office. Ready to be approved.
| 4/1/13 4/15/13 5/15/13 5/31/13 6/11/13 7/1/13 8/15/13 9/16/13 10/18/13 11/30/13 3/31/14 4/30/14 5/30/14 | P | P | P | Notify providers of 2013 distributions. |  | Letters for both 2013 and 2014 were transmitted on May 30, 2014.
| 4/25/13 7/15/13 8/15/13 9/30/13 10/31/13 11/30/13 3/31/14 4/30/14 | P | P | P | Transmit distributions to providers. |  | The 2014 distributions are being paid in the proper amounts. A reconciliation of the 2013 distributions will occur in July 2014.
| 6/1/14 12/31/14 | P | P | P | Submit report to legislature after first year, pursuant to statute. |  | Will need to request an extension, as impact of methodology change will not be known by this time due to the delay in SPA approval.
| ongoing 7/31/14 | P | P | P | Continue to meet with stakeholders |  | One or two more webinars to be scheduled; one to explain 2013 and another to explain 2014.
| ongoing 7/31/14 | P | P | P | Answer provider phone calls and questions. |  | Calls have begun, being handled. One or two more webinars to be scheduled to further explain the changes.
5604 |  |  |  |  | Project Name: Essential Community Provider Network & Vital Access Providers Division Lead: DFRS/OHSM Team Lead: Lora Lefebvre Additional Staff: John Ulberg Description: Establish Essential Community Provider Network (short-term funding) and Vital Access Providers (ongoing rate enhancement or other support) - to ensure access to care for patients. |  | Merged with #67 That work plan will be expanded to reflect the tasks necessary to implement these initiatives.
See MRT Phase 1 Work plan # 67

## Ph 2 Affordable Housing (Comp)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5700 |  |  |  |  | Project Name: Re-engage the MRT Affordable Housing Work Group Division Lead: Liz Misa and Mark Kissinger Description: The MRT Affordable Housing Work Group will reconvene to further work on supportive housing initiatives. |  | Completed - Meetings ongoing
| 9/15/12 | P | P | P | Develop Work Group Charge and Membership
| 10/1/12 | P | P | P | Finalize agenda, Workgroup Charge and membership
| 10/25/12 | P | P | P | Commence First Meeting
| 2012-11-19 | P | P | P | Hold First MRT Affordable Housing Meeting
| 2012-12-11 | P | P | P | Formed Three Sub-Groups and Identified Chairs
| 12/18/12 1/10/13 | P | P | P | Hold Second MRT Affordable Housing Meeting
| 1/20/13 2/22/13 | P | P | P | Hold Third MRT Affordable Housing Meeting
| 2013-03-28 | P | P | P | Hold Fourth Meeting.
| 9/1/13 10/15/13 | P | P | P | Reconvene the MRT Affordable Housing Work Group
5701 |  |  |  |  | Project Name: Supportive Housing Division Lead: NYC Team Lead: Andrea Cohen Additional Staff: Liz Misa and Mark Kissinger Description: Work with New York City to develop a NY/NY IV agreement and with other interested counties to make a similar commitment that will provide integrated funds for capital, operating expenses/rent and services in new supportive housing units targeting high-cost, high need users of Medicaid, especially those transitioning out of restrictive institutional settings. |  | Merged with #5700
| 2012-09-05 | P | P | P | Refer to 5700
5702 |  |  |  |  | Project Name: Establish dedicated fund for supportive housing development Division Lead: Division of Long Term Care & Division of Finance and Rate Setting Team Lead: Mark Kissinger, John Ulberg, Ken Evans Additional Staff: Lana Earle, Bob Loftus, Lora Lefebvre Description: Establish a formal mechanism to set aside a portion of Medicaid and non-Medicaid savings related to any reduction of inpatient hospital or nursing home capacity to a fund dedicated to housing development. |  | Completed - Dec 2012
| 2012-04-01 | P | P | P | Secure passage of Article VII provision
| 2012-04-24 | P | P | P | Meet internally with Finance and rate setting to discuss methodology
| 2012-08-15 | P | P | P | Participated in internal meeting with DOH to discuss methodology
| 2012-10-15 | P | P | P | Develop database to measure starting point for NH and Hospital beds
| 2012-10-15 | P | P | P | Meet w/ finance and rate setting, and OSHM to discuss methodology
| 2012-12-11 | P | P | P | Secure DOB concurrence of fiscal estimates and build appropriation into the Governor's proposed budget
| 2013-02-22 | P | P | P | Engage MRT Affordable Housing Workgroup for spending proposals
| 2013-04-01 | P | P | P | Fund established and included in the Enacted 2012-13 budget.
5703 |  |  |  |  | Project Name: Provide immediate support to supportive housing development. Division Lead: Division of Long Term Care Team Lead: Mark Kissinger & Liz Misa Additional Staff: Sean Fitgerald (HCR), Bob Myers (OMH), Lucinda Grant-Griffin (OPWDD), Linda Glassman (OTDA), Frank Walsh (DOB), Louis Raffaele (DOB). Description: A portion of the $75 million in the SFY 2012-13 MRT funding allocation plan should be transferred to OMH, OTDA, and HCR for distribution through HHAP, OMH programs, Housing Trust Fund and tax-exempt bond programs. OPWDD programs should also be considered for investment. |  | Completed - May 2013
| 2012-03-15 | P | P | P | Develop internal matrix on options for $75 million investment working with DHCR
| 2012-04-01 | P | P | P | Secure passage of Article VII provision
| 2012-04-25 | P | P | P | Meet with agency representatives to discuss implementation plan
| 2012-05-01 | P | P | P | Draft Supportive Housing Allocation Plan to submit to DOB
| 2012-05-25 | P | P | P | Draft Supportive Housing Press Release to formally announce funding allocations
| 2012-06-01 | P | P | P | Secure Governor’s office and DOB approval of 2012-13 investment strategy
| 2012-06-07 | P | P | P | Formally announce allocation plan and press release for $75 million investment
| 2012-06-28 | P | P | P | Meet weekly with Agency Leads to discuss and track progress
| 2012-06-28 | P | P | P | Initiate Data Workgroup with Salient staff to finalize a methodology to track Medicaid savings
| 2012-07-15 | P | P | P | Initiate bi-weekly meetings of State staff work team to track investment progress
| 2012-07-26 | P | P | P | Bi-weekly meeting to track investment progress
| 8/6/12 8/20/12 9/5/12 | P | P | P | Develop Medicaid cap monthly allocation
| 2012-11-01 | P | P | P | Finalize Budget Certificates and move funding allocations to relevant agencies.
| 2012-11-01 | P | P | P | Transfer funding allocations to each agency and have each agency finalize and post their RFPs
| 11/1/12 4/1/13 | P | P | P | Finalize Salient methodology to capture and track Medicaid savings
| 2013-05-15 | P | P | P | Distribute Salient Tracking Spreadsheet to Agencies
| 2013-05-15 | P | P | P | Submit Evolution Project to MDW
5704 |  |  |  |  | Project Name: Unfreeze OMH capital funding Division Lead: Office of Mental Health Team Lead: Bob Myers Additional Staff: Description: Unfreeze OMH capital and operating funding for supportive housing for SFY2012-13 and SFY2013-14. |  | Completed - April 2012
|  | P | P | P | Completed in enacted budget (per Bob Myers of OMH)
5705 |  |  |  |  | Project Name: Increase set-asides and incentives for supportive housing Division Lead: HCR Team Lead: Sean Fitzgerald Additional Staff: Description: Evaluate and consider set-asides and incentives for supportive housing construction in HCR Qualified Allocation Plan when awarding federal Low-income Housing Tax Credits. |  | Merged with #5700
| 2012-09-05 | P | P | P | Refer to 5700
5706 |  |  |  |  | Project Name: Include funds for ongoing services and operating costs in MRT 1115 Medicaid Waiver Division Lead: Division of Long Term Care Team Lead: Liz Misa Additional Staff: Description: Include in MRT 1115 Medicaid waiver funding for ongoing housing services and supports and operating costs. |  | Complete Included in MRT Waiver
| 2012-06-01 | P | P | P | Initiative internal meeting to discuss inclusion into 1115 Super Waiver Proposal
| 2012-08-06 | P | P | P | Proposal submitted to CMS
| 2012-08-10 | P | P | P | Participated in call with CMS to outline supportive housing waiver purpose
5707 |  |  |  |  | Project Name: Pilot "Social Impact Investment Bonds" for supportive housing Division Lead: Team Lead: Additional Staff: Description: Explore the creation of a pilot program of “social impact investment bonds” that would pay for development, operations and services in supportive housing. |  | Merged with #5700
|  | P | P | P | Refer to 5700
5708 |  |  |  |  | Project Name: Improve interagency coordination of supportive housing policy and implementation Division Lead: Team Lead: Additional Staff: Description: Establish an interagency council of state and local agency representatives to assist with coordination and implementation of supportive housing policy. |  | Merged with #5700
| 9/5/12 | P | P | P | Merge with MRT Affordable Housing Workshop - (refer to 5700)
5709 |  |  |  |  | Project Name: Establish a work group to identify and improve the supportive/affordable housing capital development process Division Lead: DOH OHIP Team Lead: Liz Misa and Mark Kissinger Additional Staff: Description: Establish a work group to identify and improve the supportive/affordable housing capital development process |  | Completed - Sept 2012
| 2012-06-01 | P | P | P | Participate in internal meeting to identify informal Workgroup and Formal workgroup members
| 7/1/12 9/1/12 | P | P | P | Merge with MRT Affordable Housing Workshop - (refer to 5700)
5710 |  |  |  |  | Project Name: Evaluate perceived barriers to maximizing existing resources and expanding opportunities Division Lead: Team Lead: Additional Staff: Description: Evaluate perceived barriers to proper utilization of existing supportive housing units such as the State’s interpretation of Section 504 requirements for accessible housing, whether existing special needs stock reserved for those with mobility impairments are occupied by such individuals, whether providers are maximizing opportunities for accessible housing units and whether effective compliance reviews are included in regulatory agreements for set-aside projects. In addition, identify and target existing and new resources to fund rental subsidies for all high-cost Medicaid populations. |  | Merged with #5700
| 2012-09-05 | P | P | P | Merge with MRT Affordable Housing Workshop - (refer to 5700)
5711 |  |  |  |  | Project Name: Identify and resolve barriers to transitioning individuals to supportive housing; Establish “Moving On” initiative Division Lead: Division of Long Term Care Team Lead: Mark Kissinger, Becky Corso Additional Staff: Description: Establish an additional State-led work group that includes sector experts to identify barriers to moving high-need individuals into supportive housing. This work group’s charge would include identifying the need and developing subsequent targets for heavy Medicaid users. This work group should also design a “Moving On” Initiative to incentivize and support tenants who are ready to or already live in independent housing. |  | Merged with #5700
| 2012-07-27 | P | P | P | Participate in Internal Discussions
| 2012-09-01 | P | P | P | Merge with MRT Affordable Housing Workshop - (refer to 5700)
5712 |  |  |  |  | Project Name: ALP Reform Division Lead: Division of Long Term Care Team Lead: Margaret Willard Additional Staff: Mark Kissinger Description: Multiple ALP Reform Initiatives 5712A: Registered Nurse Assessment for ALP services. 5712B: Increase ALP Reimbursement 5712C: Establish Post-Admission Audits for ALP enrollment 5712D: Nursing Home Beds/ALP 5712E: Lift CHHA moratorium 5712F: LHCSA Aides scope of practice 5712G: ALP/CHHA/LTHHCP Contracting 5712H: ALP & Therapy Services 5712I: ALP Survey Process 5712J: ALP Program Forum to evaluate implementation |  | Completed - April 2014
5712A |  |  |  |  | Project Name: Registered Nurse Assessment for ALP services. Team Lead: Additional Staff: Description: Allow the Registered Nurse (RN) employed by the ALP’s Licensed Home Care Services Agency (LHCSA) to conduct assessments to determine initial and ongoing clinical eligibility |  | Completed
| 2012-05-01 | P | P | P | Secure legislative amendment to allow
| 2012-06-01 | P | P | P | Issue guidance to all ALPs on changes
| 4/1/13 6/1/13 8/1/13 | 8 | 8 | 8 | Evaluate change in policy and issue summary report
| 9/1/13 11/1/13 12/15/13 | P | P | P | Linked to 5712B - will go together when SPA is approved
5712B |  |  |  |  | Project Name: Reimbursement for Registered Nurse Assessment for ALP services Team Lead: John Ulberg Additional Staff: Regina Deyette; Yvonne Lavoie Description: Establish payment rate to allow ALPs to bill for conducting preadmission and ongoing assessments to determine clinical eligibility |  | Completed - May 2018
| 2012-04-01 | P | P | P | Work with DHCF to evaluate rate implications
| 6//30/12 | P | P | P | Develop and submit SPA for CMS approval |  | SPA submitted on 6/28/12
| 10/1/12 3/1/13 3/15/13 6/1/13 TBD 11/1/13 TBD | P | P | P | Receive CMS approval |  | RAI received on 9/27/12. Response currently pending DFRS sign-off.
| 2013-06-01 | P | P | P | Revise Part 86-7 regs to establish payment methodology. |  | Consensus regs to Division Office on 5/1/13 for processing.
| 10/1/12 4/1/13 6/1/13 | P | P | P | Develop rate code for billing (w/systems staff) |  | RC 3299 is currently being set up in eMedNY Data Dictionary for billing.
| 10/15/12 5/1/13 6/1/13 TBD | P | P | P | Secure DOB approval on rate package |  | Impact is fiscally neutral
| 11/30/12 6/15/13 TBD | P | P | P | Implement rate changes (Post rates to eMedNY, Provider DAL)
5712C |  |  |  |  | Project Name: Establish Post-Admission Audits for ALP enrollment Team Lead: Additional Staff: Description: Expedite enrollment into ALPs by allowing for an individual to be admitted to an ALP without an assessment conducted by local department of social services (LDSS) or HRA prior to admission. Rather, the LDSS can conduct post-admission audits to ensure appropriate admissions. |  | Completed - July 2012
| 2012-06-15 | P | P | P | Issue guidance to ALPs and LDSS on policy change
| 2012-07-09 | P | P | P | Issue GIS to local districts
| 4/1/13 8/1/13 10/1/13 | 8 | 8 | 8 | Follow-up on process
5712D |  |  |  |  | Project Name: Nursing Home Beds/ALP Team Lead: Additional Staff: Description: Repeal the section of social services law that requires a reduction in nursing home beds to create new ALP beds, but maintain the expansion of the ALP. |  | Completed - June 2012
| 2012-04-01 | P | P | P | Secure Article VII approval
| 2012-05-01 | P | P | P | Develop need methodology and options paper for Executive Chamber
| 2012-05-01 | P | P | P | Secure Chamber approval of process for new ALPs
| 2012-06-15 | P | P | P | Implemented
5712E |  |  |  |  | Project Name: Lift CHHA moratorium Team Lead: Additional Staff: Description: Lift the moratorium on CHHAs to enable ALPs to serve their residents. |  | Completed - Dec 2012
| 2012-03-08 | P | P | P | CHHA applications are due to DOH
| 2012-05-01 | P | P | P | Evaluate options received
| 2012-12-31 | P | P | P | Secure PHHPC approval if necessary
5712F |  |  |  |  | Project Name: LHCSA Aides scope of practice Team Lead: Additional Staff: Description: Allow ALPs the option to utilize their LHCSA home health aides to perform all functions within their scope of practice/tasks. |  | Completed - July 2013
| 6/15/12 | P | P | P | Issue DAL
| 2012-08-01 | P | P | P | Issue guidance to ALPs
| 4/1/13 8/1/13 12/31/13 | 8 | 8 | 8 | Measure impact of policy change (depending on staff availability)
5712G |  |  |  |  | Project Name: ALP/CHHA/LTHHCP Contracting Team Lead: Mark Kissinger Additional Staff: Description: Enable the ALP to contract with more than one CHHA or LTHHCP. |  | Completed - July 2015
| 2012-04-01 | P | P | P | Secure Article VII approval
| 2012-06-15 | P | P | P | Issue guidance to ALPs and CHHAs
| 4/1/13 9/1/13 12/31/13 6/30/14 12/1/14 3/1/15 6/1/15 9/1/15 | P | P | P | Measure impact of policy change (depending on staff availability) Draft survey in process Survey sent to Local Departments of Social Services 5/20/15. Analysis of Survey completed 7/15.
5712H |  |  |  |  | Project Name: ALP & Therapy Services Team Lead: Additional Staff: Description: Allow ALPs to access Medicare-covered therapy services from providers other than CHHAs or LTHHCPs. |  | Completed - Mar 2015
| 6/15/12 12/31/12 8/1/13 10/1/13 | 8 | 8 | 8 | Issue guidance to ALPs on policy change
5712I |  |  |  |  | Project Name: ALP Survey Process Team Lead: Keith Servis Additional Staff: Description: Improve the ALP survey process. |  | Completed - Mar 2015
| 8/1/12 10/1/12 2/15/13 9/1/13 1/1/14 | P | P | P | Work with OHSM and ALP providers on possible policy changes
| 3/1/13 5/1/13 10/1/13 12/31/13 4/1/14 | P | P | P | Develop draft changes survey process
5712J |  |  |  |  | Project Name: ALP Program Forum to Evaluate Implementation Team Lead: Keith Servis Additional Staff: Description: |  | Completed - Mar 2015
| 8/1/13 2/1/14 | P | P | P | Create evaluation group
5713 |  |  |  |  | Project Name: Co-Locate Community Health Centers for Supportive Housing Residents Division Lead: Team Lead: Karen Westervelt Mark Kissinger Additional Staff: Description: Co-locate community health centers to expand services available to supportive housing residents |  | Cancelled
| 2012-07-01 | P | P | P | Participate in internal discussion
| 2012-08-15 | P | P | P | Participate in internal meeting with DOH staff to discuss
| 2012-08-15 | P | P | P | Pursue in MRT Waiver
| 1/1/13 9/1/13 1/1/14 | 8 | 8 | 8 | Develop Work plan pending waiver approval
5714 |  |  |  |  | Project Name: Notice and best effort education Division Lead: Division of Long Term Care Team Lead: Karen Meier Additional Staff: Description: Encourage communities to support populations in need of supportive and affordable housing by evaluating whether local requirements could be aligned to require community “notice and best effort education." |  | Completed - Mar 2013
| 9/15/12 | P | P | P | Develop internal DOH work plan
| 2012-10-01 | P | P | P | Review existing manuals, videos and other materials that could be linked to MRT website for use by developers, non-profits and supporters to buy community in to benefits of SH.
| 2012-12-01 | P | P | P | Obtain permission from organizations that produced materials for placement on website.
| 2013-03-01 | P | P | P | Post to MRT website a Community Notice and Best Effort Education Resource.
5715 |  |  |  |  | Project Name: Expand and improve independent senior housing opportunities Division Lead: Division of Long Term Care Team Lead: Mark Kissinger Additional Staff: Paul Pfliegler Val Deetz Description: Address concerns about independent senior housing by: clearly defining independent senior housing in regulation; streamlining regulatory barriers to improve outcomes and achieve efficiencies; identifying resources to develop and preserve quality independent affordable housing for seniors that can serve as a platform for services to maximize their ability to be maintained in their homes and communities; and identifying new funding sources and new services from best practices in the supportive housing industry to support independent senior housing. |  | Merged with #7106
| 2/1/13 8/1/13 9/1/13 11/1/13 1/1/14 3/1/14 | 8 | 8 | 8 | Develop internal work plan
| 10/1/12 4/1/13 8/1/13 10/1/13 12/31/13 2/1/14 | 8 | 8 | 8 | Coordinate, schedule and participate in stakeholder meeting
5716 |  |  |  |  | Project Name: Maintain housing subsidies and focus of NHTD/TBI Waivers Division Lead: Division of Long Term Care Team Lead: Mary Ann Anglin Lydia Kosinski Additional Staff: Description: Ensure continuation of housing subsidies provided through the NHTD/TBI Medicaid Waivers after the transition to Managed Long Term Care (MLTC) and that these programs, and their housing focus, are fully incorporated into MLTC and other Care Coordination Models. |  | Merged with #5700
| 4/1/13 7/1/13 | 8 | 8 | 8 | Develop issue paper outlining impact and recommendations of policy changes. Merged into 5700.
5717 |  |  |  |  | Project Name: Medical Respite for homeless individuals Division Lead: OASAS Team Lead: Rob Kent Additional Staff: Description: Develop programs that serve the short term needs of people who need a temporary increase in the level of care in order to avoid hospitalization and emergency departments or in order to be discharged in a timely fashion (e.g. crisis intervention, hospital diversion, hospital step-down programs and medical respite care). |  | Completed - Jan 2013
| 2012-06-01 | P | P | P | DOH and OASAS discussion on development of work plan
| 2012-08-15 | P | P | P | Internal discussion with Rob Kent
| 2013-01-01 | P | P | P | OASAS is developing a work plan. Merge into BHO Work plan.
5718 |  |  |  |  | Project Name: Coordinate supportive housing with Health Homes Initiative Division Lead: Team Lead: Additional Staff: Description: Ensure that Health Homes work with supportive housing providers to insure their residents and clients have maximum opportunities for inclusion and that the supportive housing provider has the opportunity to participate in service coordination. |  | Merged with #89
Referred to MRT Phase 1 Project #89, Health Homes.

## Ph 2 Catch-All WP (Completed)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2012-2013 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
5901 |  |  |  |  | Project Name: Payment for Enteral Formula with Medical Necessity Criteria (Revision) Division Lead: DPRUM Team Lead: Kevin Hepp Additional Staff: Jonathan Bick, Deborah Henderson, Dr. Curtin Description: Evaluate coverage criteria/authorization process of Enteral formula consistent with 12-13 Budget language (Section 7, Part D) |  | Completed - May 2014
LEGISLATIVE CHANGE
| 2012-04-01 | P | P | P | Legislation Enacted
REGULATION CHANGES (DATES IF FILING EMERGENCY REGS)
| 6/22/12 7/6/12 | P | P | P | Develop final/revised Regulation language
| 7/2/12 7/17/12 8/24/12 | P | P | P | Submit revised Regulation language to DOH for approvals
| 7/17/12 7/27/12 9/14/12 11/16/12 12/5/12 12/12/12 2/28/13 4/30/13 | P | P | P | Obtain DOH approvals |  | Submitted 8/27/12
| 7/18/12 7/30/12 9/17/12 11/19/12 12/5/12 12/12/12 2/13/13 3/20/13 | P | P | P | Submit revised Regulation language to Governor's office for approval
| 8/13/12 8/27/12 10/5/12 12/31/12 2/28/13 6/1/13 8/1/13 | P | P | P | Obtain Governor's office approval
| 8/14/12 9/4/12 10/16/12 1/15/13 1/3/13 3/1/13 5/1/13 6/1/13 8/1/13 | P | P | P | File Emergency Regs
| 8/29/12 9/19/12 11/1/12 2/1/13 4/1/13 6/1/13 7/1/13 9/1/13 | P | P | P | Emergency Regulation Effective date |  | effective 6/7/13
| 10/31/12 12/19/12 1/31/13 4/1/13 6/1/13 8/1/13 9/1/13 11/1/13 4/1/14 2/7/14 2/28/14 | P | P | P | Public Comment period
| 10/31/12 11/31/12 2/28/13 5/1/13 7/1/13 9/1/13 10/1/13 1/31/13 | P | P | P | Assess rule for final adoption or further revision/re-file emergency reg
| 2014-05-01 | P | P | P | Final Adoption
FINAL ANALYSIS
| 4/27/12 | P | P | P | Draft of fiscal analysis
| 6/20/12 7/6/12 | P | P | P | Final fiscal analysis complete
| 6/20/12 7/9/12 | P | P | P | Submit fiscal analysis to DFRS
| 6/29/12 7/16/12 | P | P | P | Obtain DFRS decision
PRIOR AUTHORIZATION SYSTEM CHANGES
| 4/25/12 | P | P | P | Data Analysis of PA/fiscal impact
| 4/27/12 | P | P | P | Identify PA/Criteria change options
| 6/22/12 6/20/12 7/6/12 | P | P | P | Finalize PA/Criteria changes
| 8/29/12 9/19/12 11/1/12 2/1/13 4/1/13 6/1/13 9/1/13 | P | P | P | Implement changes (effective date)
SYSTEM CHANGES
| 4/26/12 6/30/12 9/21/12 | P | P | P | Verify DIRAD purchase order in place and available dollars
| 7/13/12 8/3/12 9/21/12 12/7/12 | P | P | P | Identify final DIRAD and/or procedure file changes
| 7/17/12 8/8/12 9/28/12 12/14/12 | P | P | P | Initial meeting with DIRAD to establish potential time frame/scope/cost of changes
| 8/3/12 8/8/12 9/28/12 12/14/12 3/1/13 5/1/13 3/26/13 | P | P | P | Schedule tentative date for final DIRAD meeting
| 8/17/12 8/31/12 10/12/12 1/11/13 3/15/13 5/15/13 3/26/13 | P | P | P | Final meeting with DIRAD |  | May be phone conference if changes from initial meeting are minimal
| 8/24/12 9/7/12 10/19/12 1/25/13 3/25/13 5/25/13 6/25/13 8/25/13 | 8 | 8 | 8 | Procedure file changes (if necessary) |  | not required
| 8/21/12 9/7/12 10/17/12 12/21/12 3/20/13 5/20/13 3/31/13 | P | P | P | Secure final estimate of DIRAD script changes
| 8/21/12 9/7/12 10/17/12 12/21/12 3/20/13 5/20/13 3/31/13 | P | P | P | Verify estimate within available funds
| 8/31/12 9/14/12 10/26/12 1/25/13 3/25/13 4/1/13 6/1/13 7/1/13 6/21/13 7/5/13 | P | P | P | DIRAD programming and testing complete
STAKEHOLDER NOTIFICATION
| 5/4/12 | P | P | P | Schedule Webinar and Twitter Chat
| 5/11/12 | P | P | P | Stakeholder contact information database
| 5/11/12 | P | P | P | Release Webinar and Twitter chat dates/time
| 5/25/12 5/17/12 | P | P | P | Develop Webinar PowerPoint/presentation structure
| 6/1/12 5/18/12 | P | P | P | Hold Webinar
| 6/4/12 5/25/12 | P | P | P | Post Webinar PowerPoint
| 6/1/12 6/8/12 | P | P | P | Schedule Twitter chat (if necessary)
| 6/4/12 6/11/12 6/21/12 | P | P | P | Release Twitter date/time (if necessary)
| 5/25/12 6/5/12 | P | P | P | Establish/finalize Twitter protocol
| 6/8/12 6/26/12 | P | P | P | Hold Twitter chat (if necessary)
| 6/11/12 | 8 | 8 | 8 | Schedule Webinar #2 (if necessary)
| 6/12/12 | 8 | 8 | 8 | Release Webinar #2 date/time (if necessary)
| 6/15/12 | 8 | 8 | 8 | Hold Webinar #2 (if necessary)
| 10/15/12 1/15/13 3/15/13 5/15/13 6/15/13 8/15/13 | P | P | P | Hold 2nd Webinar advising stakeholders of changes
| 6/19/12 7/5/12 | P | P | P | Assess feedback from Webinar/Twitter/Email
| 8/21/12 9/12/12 10/19/12 1/25/13 3/25/13 5/25/13 6/15/13 8/15/13 6/14/13 | P | P | P | Develop Notifications to be posted/sent
| 8/22/12 9/13/12 10/12/12 1/18/13 3/18/13 5/18/13 6/15/13 8/15/13 6/14/13 | P | P | P | Update MMC
| 8/24/12 10/26/12 1/25/13 3/25/13 5/23/13 6/25/13 8/25/13 6/26/13 7/12/13 | P | P | P | Email blast of finalized Criteria/PA process
| 8/24/12 9/14/12 10/26/12 1/25/13 3/25/13 5/25/13 6/25/13 8/25/13 6/26/13 | P | P | P | Emedny.org notification
| 8/29/12 9/19/12 10/26/12 1/25/13 3/25/13 5/25/13 6/25/13 8/25/13 7/1/13 | P | P | P | DME Provider manual update
| 8/29/12 9/19/12 10/26/12 1/25/13 3/25/13 5/25/13 6/25/13 8/25/13 7/1/13 | P | P | P | Pharmacy Provider manual update
STAFF TRAINING
| 4/4/12 | P | P | P | Develop and implement process for tracking Stakeholder contacts
| 8/24/12 9/14/12 10/31/12 1/11/13 3/25/13 5/25/13 6/25/13 8/25/13 6/26/13 7/12/13 | P | P | P | PA/Criteria/Regulation changes
| 8/24/12 9/14/12 10/31/12 1/11/13 3/25/13 5/25/13 6/25/13 8/25/13 6/26/13 | P | P | P | Revise template for phone staff
| 8/24/12 9/14/12 10/31/12 1/11/13 3/25/13 5/25/13 6/25/13 8/25/13 6/26/13 | P | P | P | Notify CSC Call Center
| 8/24/12 9/14/12 10/31/12 1/11/13 3/25/13 5/25/13 6/25/13 8/25/13 6/26/13 | P | P | P | Pended claims/PA units re: workload impact
5902 |  |  |  |  | Project Name: Enhancing the Quality of Adult Lives (EQUAL) Division Lead: Center for Health Care Quality and Surveillance Team Lead: Dorothy Persico Additional Staff: Mary Hart, Jennifer Treacy, Angela Whyland Description: For services and expenses of a quality program for adult care facilities, including enriched housing facilities, targeted at improving the quality of life for adult care facility residents. |  | Completed - May 2013
| 2012-09-14 | P | P | P | Confirm how much cash is behind appropriation
| 2012-09-21 | P | P | P | Review past procedures to determine if improvements/modifications are necessary
| 2012-09-28 | P | P | P | Develop allocation methodology
| 2012-10-05 | P | P | P | Obtain executive approval on allocation methodology, announcement and award process
| 2012-10-05 | P | P | P | Submit for B-1184 approval
| 2012-10-05 | P | P | P | Develop application and announcement (DAL) for providers
| 1/22/13 2/8/13 2/22/13 4/15/13 5/17/13 | P | P | P | Develop process of distributing awards, ensure all providers have SFS access
| 1/22/13 2/8/13 2/22/13 4/15/13 5/17/13 | P | P | P | Develop plan for how utilization of funds will be monitored (regional office staff review records upon survey, etc), how non-compliance will be handled
| 10/10/12 12/30/12 1/29/13 2/8/13 2/14/13 | P | P | P | Post announcement (DAL) and application on HCS
| 10/10/12 12/30/12 1/28/13 2/8/13 2/14/13 | P | P | P | Share announcement, application and process with associations and regional offices
| 11/1/12 1/1/13 2/1/13-4/1/13 2/22/13 | P | P | P | Receive applications and expenditure plans, review for completeness
| 1/15/13 4/15/13 3/30/13 4/15/13 | P | P | P | Notify providers of awards
5903 |  |  |  |  | Project Name: Emergency Department Triage Division Lead: DHFP Team Lead: Joe DiMura Eduardo Santana Additional Staff: Description: Through a triage process, identify MA and uninsured patients with high Emergency Room utilization history and those without a PCP and link them to medical homes. (Section 26, Part D) |  | Completed - May 2014
| 2012-07-12 | P | P | P | Convene DOH/Stakeholder Work Group(WG) - participants include representation from : HANYS, GNYHA, CHCANYS, Montefiore MC and DOH staff from DLA, OHSM, OHIP &OHITT
PROJECT IMPLEMENTATION WG/TEAM:
| 2012-08-24 | P | P | P | Bi-weekly planning mtgs: first meeting held and project scope and deliverables assigned. Meetings are ongoing.
| 2012-08-24 | P | P | P | At first meeting: after careful deliberation, WG concluded that this is a unique opportunity to identify any program or strategy that attempts to address overcrowding, overutilization and lack of medical home.
| 2012-08-24 | P | P | P | At first meeting: agreed to invite Joy Tapper of Milwaukee Health Care Partnership to present to the WG.
| 2012-09-13 | P | P | P | Discussion on what mechanisms were available to the WG to help identify existing Triage or other strategies currently in use in NYS.
| 2012-09-13 | P | P | P | Determined that a survey administered through the Health Department's Health emergency Response Data System was the most efficient and effect approach.
| 2012-09-13 | P | P | P | Small sub WG established to draft survey
| 2012-09-13 | P | P | P | Announced that Joy Tapper Executive Director of MHCP will present at next meeting on 10/15/12.
| 2012-09-13 | P | P | P | Discussion on whether or not to include a representative from the Insurance Industry - no decision made.
| 2012-10-15 | P | P | P | Joy Tapper of Milwaukee Health Care Partnership to present on strategies, challenges and opportunities of an integrated Triage system.
| 2012-10-15 | P | P | P | Ms. Tapper identified several key challenges to any Triage program including: -HIT - EHR and interconnectivity between scheduling systems of participating members. -Executive Support/authorization. -Communication between partner members. -Capacity of network. -Funding for startup and continued operations.
| 2012-10-15 | P | P | P | Draft ED survey that will identify programs and/or strategies currently being used in NYS to address overcrowding, overutilization and patients with no medical home reviewed by WG.
| 2012-10-15 | P | P | P | Next meeting of the workgroup 11/19/12
| 2012-11-19 | P | P | P | Review and approval of ED survey completed.
| 2012-11-19 | P | P | P | WG agreed to invite representation from the insurance industry.
| 2012-11-19 | P | P | P | Joe will reach out to Arlene Halpert of NY Health Plan Association
| 2012-11-19 | P | P | P | WG discussed what, if any funding is available to support implementation of identified programs and/or strategies.
| 2012-11-19 | P | P | P | next meeting scheduled for 12/17/12.
| 2012-12-14 | P | P | P | ED survey will be issued through the department's HERDS program by 12/14.
| 2013-01-07 | P | P | P | ED Best Practices Survey issued through the Department's HERDS program.
| 2013-01-17 | P | P | P | GNY and HANYS will send out a notice through their secure server to ask all their members who have an ED to complete the survey and submit to DOH for review.
| 2013-01-17 | P | P | P | the work group discussed establishing an email address to accept questions, presentation packages, papers etc. from hospital's that are willing to share their strategies with the work group.
| 1/17/13 ongoing 4/15/13 | P | P | P | work group had a discussion on the possible challenges to implementing strategies that will likely result in reduction in a hospital's reimbursement due to redirecting patients to alternate care. Further discussion is needed and Insurance representatives will be key players in this discussion moving forward.
| 1/17/13 ongoing 3/31/13 | P | P | P | The department's policy regarding Free Standing ED's was discussed. The WG needs time to understand the department's position and how it might effect this MRT initiative. There could possibly be significant implications and challenges to this initiative depending on how the demo is structured.
| 2013-01-17 | P | P | P | Paul Macielak of NYSHPA has joined the work group and will invite individual health plans to participate.
| 2013-01-22 | P | P | P | Individual work group members have agree to and begun reaching out to hospitals throughout NYS and identify currently employed strategies. Will report back to work group at next meeting on findings.
| 2013-01-22 | P | P | P | Q&A's for the Commissioner's budget hearing have been completed and submitted. Status report and challenges that the WG face have been included in that submission.
| 2013-02-08 | P | P | P | • gather Survey response data: WG has begun to identify best practices for review.
| 1/25/13 2/28/13 3/29/13 4/30/13 7/30/13 10/19/13 3/31/14 | 8 | 8 | 8 | WG to establish essential criteria for acceptable programs/strategies.
| 2013-01-24 | P | P | P | HANYS has identified Adirondack PCMH as a facility that is currently using a strategy for redirecting patients who present in their ED to appropriate alternate care. We will be asking Adirondack to present their strategy at our next meeting and then completing a thorough analysis of the initiative.
| 2013-03-01 | P | P | P | Complete review and analysis of survey responses and create a catalog of "best practices/strategies" currently being utilized by NYS Hospitals.
| 2013-03-05 | P | P | P | WG has developed and released a follow-up letter to several hospital's asking them to present their initiative and strategies to the workgroup
| 2013-03-06 | P | P | P | Adirondack PCMH presented their initiative to the WG
| 2013-03-06 | P | P | P | Sub WG making follow-up calls to hospital's who have agreed to provide more detail on their initiative with the idea of inviting several to present to WG at future meetings.
| 2013-03-20 | P | P | P | First draft of final report discussed at WG meeting and sent out to WG for review and approval of doc.
| 3/29/13 6/30/13 11/1/13 | P | P | P | create a Salient query of identified facilities to verify if initiatives/strategies are reducing costs to the Medicaid system.
| 2013-04-01 | P | P | P | need to verify what, if any funding is available to support roll out of Demonstration Projects. At this time WG is under the belief no funding will be available.
| 2013-04-03 | P | P | P | WG comments/changes to Draft report due back.
| 2013-04-22 | P | P | P | Submit Ed report to Karen Westervelt/Commissioner
| 2013-05-16 | P | P | P | Briefing held with Karen Westervelt on report. Awaiting response from Commissioner on next steps.
| 2013-11-12 | P | P | P | Meeting with Dept. Commissioner to discuss required revisions to the report completed.
| 12/20/13 1/16/14 | P | P | P | Revisions to the report to be completed
| 2014-03-06 | P | P | P | a review of the statute shows that the report to the Legislature is due after the triage system is implemented. Therefore, the Commissioner has directed us to reconvene the workgroup to continue and complete the review of initiatives implemented by NYS hospitals designed to reduce avoidable ED visits and resulting admissions. The workgroup will be reconvened shortly after the 2014-15 budget is finalized.
| 1/25/13 2/28/13 3/29/13 4/30/13 7/30/13 10/19/13 3/31/14 4/30/14 | 8 | 8 | 8 | Based on the re-examination of the budget language, the commissioner has decided to engage a WG to continue to study this issue.
| 4/17/13 5/30/14 | 8 | 8 | 8 | HIT needs assessment - interoperable EHR's platform is a minimum requirement of the triage project
| 5/27/13 2/27/14 8/30/14 | 8 | 8 | 8 | Give special consideration to existing networks or affiliations.
| 5/27/13 3/31/14 9/15/14 | 8 | 8 | 8 | Allow for creation of networks or affiliations that agree to self fund.
| 2014-09-15 | 8 | 8 | 8 | Evaluate and choose a hospital from high ED utilization regions
| 6/28/13 6/22/14 9/15/14 | 8 | 8 | 8 | Choose a sponsor in rural area of NYS
| 6/13 - 3/14 12/15/14 | 8 | 8 | 8 | Select and evaluate Demonstration Project facilities
| 7/13/13 6/15/14 12/15/14 | 8 | 8 | 8 | Key process decision points:
| 8/13/13 6/14/15 | 8 | 8 | 8 | Identify and establish report process.
| 8/13/13 10/19/14 | 8 | 8 | 8 | Establish metric for assessing program/strategy performance.
| 8/13/13 9/20/14 | 8 | 8 | 8 | Establish quarterly review of programs/strategies.
5904 |  |  |  |  | Project Name: Stakeholder Consultation for Nursing Home Capital Reimbursement Division Lead: DFRS Team Lead: John Ulberg Additional Staff: Mark Kissinger Description: (Section 34a, Part D) |  | Completed. Included in MRT Waiver
| Ongoing |  |  |  | Part of MRT Waiver discussions
5905 |  |  |  |  | Project Name: Workgroup on Medically Fragile Children Division Lead: OHIP, DHCBS, OPWDD Team Lead: Lana Earle Additional Staff: Vicki Schultz (OPWDD) Description: (Section 34b, Part D) |  | Completed - Feb 2013
| 2012-06-07 | P | P | P | Internal DOH OPWDD Meeting to discuss objectives, data, MFC population and programs, Work Plan
| 2012-06-12 | P | P | P | Internal DOH OPWDD Meeting to discuss objectives, data, MFC population and programs, Work Plan
| 6/21/12 | P | P | P | Internal DOH OPWDD Meeting to discuss objectives, data, MFC population and programs, Work Plan, Review Draft PPT for First Meeting, continue to develop recommendations for Work Group members
| 6/25/12 | P | P | P | During this week finalize Work Group members, set up first Work Group Meeting
| 6/26/12 | P | P | P | Internal DOH OPWDD Work Group meeting, review Medicaid data/identify MFC population, Finalize recommendations for Work Group circulate to principals for approval
| 7/10/12 | P | P | P | Finalize PPT for first Work Group meeting
| 7/12/12 7/19/12 | P | P | P | First Work Group meeting
| 7/26/12 8/2/12 | P | P | P | Second Work Group meeting
| 8/9/12 8/15/12 | P | P | P | Third Work Group meeting
| 8/23/12 8/30/12 9/20/12 | P | P | P | Fourth Work Group meeting
| 9/27/12 | P | P | P | Work Group members provide feedback no possible recommendations for report.
| 10/12/12 | P | P | P | Distribute 1st internal draft of work group report to work group members
| 10/25/12 | P | P | P | Distribute 2nd internal draft of work group report to work group members
| 11/2/12 | P | P | P | Distribute internal drafts of work group report to DOH staff
| 11/30/12 | P | P | P | Distribute final internal draft of work group report to DOH senior staff
| 8/29/12 9/10/12 10/4/12 11/7/12 12/3/12 12/17/12 | P | P | P | DOH/OPWDD distribute final draft of Work Group Report to work group members for review
| 9/10/12 9/17/12 10/9/12 11/21/12 12/12/12 12/26/12 1/16/13 | P | P | P | Receive Comments on final draft report from Work Group.
| 9/17/12 9/24/12 10/12/12 11/28/12 12/19/12 1/3/13 1/18/13 1/25/13 | P | P | P | Circulate revised final draft reflecting Work Group comments to Executive DOH staff for review
| 10/1/12 10/15/12 12/1/12 12/21/12 1/5/13 1/25/13 2/4/13 | P | P | P | Upon executive approval of report, present Work Group findings to the Governor and the Legislative Fiscal and Health Committees
5906 |  |  |  |  | Project Name: Limited Administrative Review - FQHCs (Section 36, Part D) Division Lead: OHIP Team Lead: John Gahan Additional Staff: Rick Nair/Janet Baggetta Description: Expedited review process for certain HRSA-funded projects submitted by FQHCs |  | Completed - May 2014
| 2012-04-01 | P | P | P | Enacted SFY 2012-2013 State Budget (Ch. 56, L. 2012) includes amendment to PHL establishing a new Section 2807-z to provide for an expedited review process for FQHC capital projects funded in whole or in part with federal monies pursuant to Section 330 of the Public Health Service Act, 42 USC 254b, or pursuant to the federal Capital Development-Building Capacity Grant Program and Immediate Facility Improvements Grant Program.
| 2012-05-03 | P | P | P | HRSA announces first round of CD-BC and IFI Grant recipients for NYS.
| 2012-05-14 | P | P | P | Staff meet with CHCANYS to discuss "clean-up" amendments needed to new statute to not covered to-be-Established entities, clarify "budget", and otherwise streamline for purposes of meeting goals and intent.
| 6/7/12 | P | P | P | Technical correction legislation introduced (A.10606/S.7602)
| 6/19/12 | P | P | P | Legislation passes.
| 2012-06-20 | P | P | P | HRSA announces New Access Point Grant recipients for NYS.
| 2012-07-31 | P | P | P | "Dear Administrator Letter", outlining the expedited process to be used by applicants sent.
| 2012-08-08 | P | P | P | Posted "Dear Administrator Letter" to the DOH website.
| 8/30/12 | P | P | P | Staff communicate to all Regional Office Directors the specifics of the new expedited process statute for FQHCs, in particular the need for expedited site visits/close-out of related CONs
Bureau of Primary and Acute Care Reimbursement (BPACR) developing regulatory package to address capital rates relative to new statute. In particular, for qualifying capital projects that are exempt from CON requirements the Department will establish a mechanism to account for capital costs of such project in the applicant’s rate and eligibility for uncompensated care reimbursement through the D&TC supplemental indigent care pool per the applicants request. While the Department currently possesses this mechanism for CONs LRAs, there is now no CON/LRA required for certain projects. Therefore, the Department must first promulgate regulations to recognize capital in rates and for the supplemental indigent care piece that is covered by the statute for projects not needing CON/LRA approval.
| 9/21/12 | P | P | P | DHFP/OHSM meet with BPACR/OHIP to discuss existing business practice for processing CONs/LRAs, and how expedited review process for affected FQHC applications differs.
| 9/30/12 11/10/12 | P | P | P | BPACR/OHIP draft revised regulation to recognize capital in rates and for the supplemental indigent care pool for affected FQHC projects not needing CON/LRA approval.
| 11/14/12 11/16/12 | P | P | P | Prepare notice to State Register for publication of regulations.
| 12/26/12 2/20/13 3/20/13 6/4/13 | P | P | P | Publish emergency regulations in State Register |  | Emergency Regulation package sent to DOS on 5/30/13 and regulations effective that date.
| 12/5/12 12/26/12 2/20/13 3/20/13 7/1/13 8/15/13 8/30/13 | P | P | P | Publish proposed regulations in State Register, for permanent regulatory package.
| 3/1/13 12/18/12 1/25/13 2/25/13 7/01/13 8/1/13 8/30/13 | P | P | P | Draft "Dear Administrator Letter" (DAL) informing FQHCs of revised regulation to recognize capital in rates and for the supplemental indigent care pool for affected FQHC projects not needing CON/LRA approval.
| 3/8/13 1/1/13 2/20/13 3/20/13 6/20/13 7/10/13 8/5/13 8/30/13 | P | P | P | Post DAL to the HCS informing providers of the revised regulation policy and procedure. Posting DAL to public website versus HCS since the HCS is a secure website and the letter will only reach individuals with an account on the site. The public website will reach a larger audience.
| 1/1/13 6/15/13 5/30/13 | 8 | 8 | 8 | Effective Date of Emergency Regulations
| 1/19/13 3/5/13 4/6/13 5/6/13 7/1/13 | 8 | 8 | 8 | 45-day public comment period for permanent regulatory package.
| 2/27/13 4/3/13 4/24/13 5/24/13 8/15/13 9/30/13 10/30/13 | 8 | 8 | 8 | Publish Notice of Adoption in State Register for permanent regulatory package.
| 11/13/13 | P | P | P | Revised reg will be published in the 11/13/13 State Register.
| 12/30/13 | P | P | P | The public comment period will expire on 12/30/13.
| 2/28/14 | P | P | P | Counsel’s office will prepare the Notice of Adoption package and Approval by DLA and the Commissioner
5907 |  |  |  |  | Project Name: Exclusive Pharmacy Network Criteria in Managed Care Division Lead: Division of Program Development and Management Team Lead: Patty Keller, RPh., Anne Blanchard, RPh. Additional Staff: Mary Carroll, Janet Zachary-Elkind Description: Implement process for the Commissioner to identify drugs that qualify for distribution through an exclusive pharmacy network within the managed care pharmacy benefit (Section 51, Part D) |  | Cancelled
This Work plan is On Hold, Pending Action per Court Order
ADMINISTRATIVE
| 4/20/12 | P | P | P | Identify Work Group |  | OHIP, MC
PROGRAM DEVELOPMENT
| 5/2/12 5/25/12 | P | P | P | Establish criteria |  | OHIP
| 5/9/12 5/31/12 7/20/12 | P | P | P | Obtain criteria approval |  | Approved 6/26/12
| 5/9/12 6/8/12 8/3/12 9/7/12 | P | P | P | Establish list of Exclusive Pharmacy Network Drugs/Limited Distribution
| 5/16/12 7/31/12 8/15/12 9/19/12 | P | P | P | Establish process for new additions
| 7/1/12 9/7/12 10/8/12 | 8 | 8 | 8 | Program implementation |  | Hold per court order
PREPAID CAPITATION RATE
| 6/1/12 8/1/12 9/3/12 10/19/12 | 8 | 8 | 8 | DOH/Mercer/develops assumptions used to augment rates; share with plans
| 6/15/12 8/15/12 9/14/12 10/25/12 | 8 | 8 | 8 | DOH/Mercer/develop draft rates; share with plans
| 7/2/12 9/4/12 11/8/12 | 8 | 8 | 8 | Plans provide feedback on assumptions/draft rates
| 8/1/12 10/1/12 11/1/12 11/20/12 | 8 | 8 | 8 | DOH/Mercer /finalize rate adjustments
| 9/3/12 11/2/12 12/3/12 12/12/12 | 8 | 8 | 8 | Rates approved by DOB, CMS
| 9/17/12 11/16/12 12/14/12 12/28/12 | 8 | 8 | 8 | Rates loaded to the system
NOTIFICATIONS
| 5/16/12 | P | P | P | Establish coverage determination document not required per MC 5/10/12
| 5/16/12 6/15/12 8/15/12 9/14/12 | P | P | P | Develop and send written (e-blasts, website update, Medicaid Update etc.) and oral communications with stakeholders
| 5/16/12 7/31/12 10/5/12 11/5/12 | 8 | 8 | 8 | MCO's send letter of notification to targeted members and providers completed by 10/5/12 regarding drug access after final list determined
EVOLUTION
| 6/13/12 8/17/12 | P | P | P | Update formulary file for submission of Exclusive Pharmacy Network Drugs
| 6/13/12 7/31/12 8/17/12 9/17/12 10/17/12 | 8 | 8 | 8 | Develop and implement an oversight plan
POST IMPLEMENTATION
| 7/1/12 7/31/12 8/17/12 | P | P | P | Determine reporting requirements
| 7/1/12 8/31/12 | P | P | P | Coordinate data exchange with MC plans
5908 |  |  |  |  | Project Name: Rural Telehealth Demonstration Division Lead: Office of Primary Care Team Lead: Rebecca Fuller Gray Additional Staff: Mike Heeran Description: (Section 51, Part D) |  | Completed - June 2013
| 2012-04-01 | P | P | P | Enacted SFY 2012-2013 State Budget (Ch. 56, Part D, Section 51) authorizes the commissioner to establish a rural home telehealth delivery demonstration study
| 2012-06-01 | P | P | P | Identify County and Providers eligible to participate in the study based on criteria included in the budget bill
| 2012-09-05 | P | P | P | Develop an expenditure plan and cash disbursement schedule
| 2012-09-21 | P | P | P | Develop scope of work
| 2012-09-28 | P | P | P | Develop funding announcement, Dear Applicant Letter and Scoring Criteria
| 2012-09-28 | P | P | P | Submit to Contract Reporter
| 2012-10-05 | P | P | P | Issue Dear Potential Applicant Letter
| 2012-11-09 | P | P | P | Applications Due
| 2012-12-06 | P | P | P | Award(s) made. Award letter(s) issued.
| 2013-01-01 | P | P | P | Study start date
| 3/31/13 6/14/13 | P | P | P | Awardees submit Report to the Governor, Legislature, the Commissioner, and Legislative Committee on Rural Resources on Study Results
5909 |  |  |  |  | Project Name: Doctors Across New York Physician Loan Repayment and Physician Practice Support Division Lead: Office of Primary Care Team Lead: Thomas Burke Additional Staff: Helen Crane, Barbara Anderson, Prabhakar Rajupet, Caleb Wistar Description: Streamline application process and include input from stakeholder workgroup to increase applicant completion success rate (Section 53-54, Part D) |  | Completed - Dec 2012
| 2012-04-25 | P | P | P | 1. Prepare a list of associations/representatives for workgroup.
| 2012-04-26 | P | P | P | 2. Distribute an agenda/charge/materials to the workgroup.
| 2012-05-01 | P | P | P | 3. Convene meeting of the workgroup.
| 2012-05-29 | P | P | P | 4. Submit 1184s for new Cycle 3 application solicitation.
| 2012-05-29 | P | P | P | 5. Based upon comments by the workgroup, prepare and distribute draft streamlined application process to the workgroup.
| 2012-05-31 | P | P | P | 6. Deadline for workgroup to finalize streamlined application process.
| 2012-06-15 | P | P | P | 7. Distribute all remaining DANY documents to the workgroup.
| 2012-06-19 | P | P | P | 8. Deadline for workgroup to provide final comments on DANY documents.
| 7/15/12 7/31/12 | P | P | P | 9. Submit all documents for posting on DANY website.
| 6/29/12 7/31/12 8/31/12 | P | P | P | 10. Program completes review tool, DOH procedures and internal control process for DOH approval.
| 11/1/12 11/15/12 11/30/12 12/15/12 12/24/12 | P | P | P | 11. Release RFA
5910 |  |  |  |  | Project Name: Prescriber Prevails in Managed Care Division Lead: Division of Program Development and Management Team Lead: Patty Keller, RPh., Anne Blanchard, RPh. Additional Staff: Mary Carroll, Janet Zachary-Elkind Description: Implement Prescriber Prevails for Atypical Antipsychotics in Managed Care (Section 55, Part D) |  | Completed - May 2013
ADMINISTRATIVE
| 2012-06-06 | P | P | P | Identify Work Group |  | OHIP, MC
PROGRAM DEVELOPMENT
| 7/9/12 7/30/12 | P | P | P | Provide policy and procedure guidance for MC plans
| 7/9/12 7/31/12 | P | P | P | Consensus
| 7/18/12 | P | P | P | Identify list of drugs
| 7/18/12 7/30/12 10/3/12 | P | P | P | Establish process for new additions
| 1/1/13 | P | P | P | Program implementation
NOTIFICATIONS
| 7/25/12 | P | P | P | Establish coverage determination document |  | Not required per MC 6/19/12
| 7/9/12 11/26/12 12/19/12 12/28/12 | P | P | P | Develop Medicaid Update and oral communications with stakeholders
PREPAID CAPITATION RATE
| 7/15/12 8/1/12 10/19/12 | P | P | P | DOH/Mercer develops assumptions used to augment rates; share with plans
| 8/2/12 10/25/12 | P | P | P | DOH/Mercer develop draft rates; share with plans
| 8/15/12 11/8/12 3/1/13 | P | P | P | Plans provide feedback on assumptions/draft rates
| 9/4/12 11/20/12 3/1/13 3/29/13 4/19/13 | P | P | P | DOH/Mercer finalize rate adjustments
| 12/3/12 12/12/12 3/15/13 3/29/13 5/3/13 | P | P | P | Rates approved by DOB, CMS
| 12/28/12 3/27/13 4/12/13 5/3/13 | P | P | P | Rates loaded to the system
EVOLUTION
| 1/1/13 | P | P | P | Update MC formulary file submission data to identify provider prevails meds
| 7/25/12 8/29/12 10/3/12 12/14/12 12/28/12 1/29/13 2/27/13 | P | P | P | Develop and implement an oversight plan
POST IMPLEMENTATION
| 7/25/12 8/29/12 10/3/12 12/14/12 12/28/12 1/29/13 2/27/13 | P | P | P | Determine reporting requirements
| 4/1/13 | P | P | P | Coordinate data exchange with MC plans
5911 | 2013-01-01 |  |  |  | Project Name: EPIC Coverage Expansion Division Lead: DPDM Team Lead: Rhonda Cooper Additional Staff: Diane Reed, Mary Carroll, Janet Elkind Description: Implement partial reinstatement of EPIC program as detailed in enacted 12/13 Executive budget. (Part T) |  | Completed - April 2013
POLICY
| 2012-05-01 | P | P | P | Review final legislation.
| 2012-08-01 | P | P | P | Modify existing EPIC policies based on changes.
ENROLLMENT AND APPLICATION PROCESSING
| 2012-10-01 | P | P | P | Develop procedures and correspondence for members who are not enrolled in Part D, disenroll from Part D, Part D plan is no longer a benchmark plan in the following year.
| 2012-10-01 | P | P | P | Set up bank lock-box and develop accounting system to track EPIC fees paid and refunded
| 2012-11-01 | P | P | P | Fee Program - Develop EPIC billing, non-payment cancelation, and reinstatement processes; waive fees for members with Medicare LIS
| 2013-01-01 | P | P | P | Modify EPIC Enrollment and Eligibility system to include the Fee and Deductible Programs with prescribed income bands and copayment maximums
| 2013-01-01 | P | P | P | Apply payments received from the bank lock box and develop process to handle insufficient funds and reinstatements process.
| 2013-01-01 | P | P | P | Credit EPIC deductible for Deductible plan members with incomes higher than $23,000 single and $29,000 married – lower income deductible members do not get a credit to deductible since EPIC pays their Part D premiums. (requires system programming)
| 2013-01-01 | P | P | P | Modify existing member correspondence; develop new system correspondence
| 2013-01-01 | P | P | P | Modify tax match process to consider all bands of income for enrollment and renewal – fees and deductibles based on matched income
| 2013-01-01 | P | P | P | Modify Third Party Query Process for income verification?
| 2013-01-01 | P | P | P | Modify imaging system if necessary for changes to EPIC application
SYSTEMS
| 2012-06-15 | P | P | P | Develop Requirements for:- enrollment , renewal , billing, claims, Part D premium payments, and manufacturers rebates systems changes
| 2012-07-01 | P | P | P | Review system designs
| 2012-11-15 | P | P | P | Review test plans
| 12/1/12 1/1/13 | P | P | P | Review test cases
| 2012-12-01 | P | P | P | Establish reporting requirements and modify existing reports
| 2013-01-31 | P | P | P | Monitor system implementations
PART D PREMIUM PAYMENTS
| 2013-01-01 | P | P | P | Modify Part D premium payment system for 2013 program changes.
| 2013-01-01 | P | P | P | Modify Part D payment reconciliation and reporting processes
CLAIMS PROCESSING
| 2012-09-30 | P | P | P | Review current system edits to see if they apply
| 2013-01-01 | P | P | P | Modify claims processing system to pay claims for Part D covered and Part D excluded drugs in all phases of Medicare Part D coverage except for Deductible phase.
| 2013-01-01 | P | P | P | Develop new reporting requirements and modify existing reports
PHARMACY
| 2012-11-01 | P | P | P | Review Part D excluded drug policy
| 2012-11-01 | P | P | P | Review rebate issues and drug coverage
| 11/1/12 12/1/12 | P | P | P | review pharmacy reports and develop new requirements
| 2012-11-01 | P | P | P | Draft communications for pharmacy providers and prescribers
| 12/1/12 1/1/13 1/31/13 2/28/13 3/31/13 | P | P | P | Update manuals
| 2012-12-01 | P | P | P | Review Pro-DUR policy
| 2012-12-01 | P | P | P | Consider need to monitor Part B claims
REBATES
| 4/1/13 5/15/13 | P | P | P | Reinstate EPIC rebate system - First Quarter Rebate Invoices Generate 5/15/13
| 2013-04-01 | P | P | P | Modify to accommodate D.0. claims processing changes.
COMMUNICATIONS/EDUCATION
| 2012-04-15 | P | P | P | Develop interim, FAQ’s for website and Helpline
| 2012-06-15 | P | P | P | Develop member, provider, prescriber communication timeline
| 2012-09-01 | P | P | P | Draft and finalize letters, emails and articles for all stakeholders
| 2012-09-01 | P | P | P | Develop training materials for outreach staff and Helpline
| 2012-09-01 | P | P | P | Provide training for all advocates and stakeholders via phone conferences.
| 2012-09-01 | P | P | P | Notify Part D drug plans about changes
| 2013-01-01 | P | P | P | EPIC Application/Brochure revision
| 1/1/13 1/31/13 | P | P | P | EPIC web site revision
5912 |  |  |  |  | Project Name: Reduction of APG Hospital Investment by $25M Division Lead: DFRS Team Lead: Janet Baggetta Additional Staff: Joseph Sohn, Kashif Gill Description: Reduce investment in Hospital APGs by $25M effective 4/1/2012 5/1/2012. | ($12.5) | Completed - Feb 2013
| 4/5/12 4/25/12 | P | P | P | Federal Public Notice
| 6/15/12 6/30/12 | P | P | P | Submit State Plan Amendment to CMS |  | RAI received but cannot be responded to until prior SPAs approved.
| 6/22/12 7/27/12 9/14/12 10/5/12 11/19/12 1/25/13 | P | P | P | Calculate revised Hospital APG base rates
| 6/22/12 7/27/12 9/14/12 10/5/12 11/19/12 1/25/13 | P | P | P | Prepare Budget package
| 6/22/12 7/27/12 9/14/12 10/5/12 11/19/12 1/30/13 1/28/13 | P | P | P | Receive Budget Package Executive approval
[5 empty] | Implemented reduction in investment when SPA 99-65 was approved by CMS for payment of the additional $92M investment |  | Received CMS approval 2/7/2013 to include the investment in the APG rates. Directive from Division was to include this reduction into the processing of the added investment rates.
| 9/30/12 12/3/12 2/7/13 3/31/13 Implemented 2/15/13 | P | P | P | Receive CMS Approval
| 10/1/12 12/3/12 1/31/13 1/28/13 | P | P | P | Submit Budget package/rates to DOB for approval
| 10/19/12 12/17/12 2/7/13 2/15/13 2/12/13 | P | P | P | Receive DOB Approval |  | Data transmitted but being held pending DOB approval.
| 10/26/12 12/21/12 2/8/13 2/6/13 | P | P | P | Transmit revised APG rates and other required data to eMedNY.
5913 |  |  |  |  | Project Name: Promote Full Access to the Mental Health Medication on the Medicaid Formulary Division Lead: OHIP Team Lead: Janet Elkind Additional Staff: Tony Merola, Monica Toohey, Kristin Woodlock, Description: Continue full access to mental health medications under the Medicaid formulary for all Medicaid recipients who are in managed care plans where the pharmacy benefit is no longer carved out . |  | Completed - Nov 2013
WORK GROUP
| 2012-05-01 | P | P | P | Establish provider/plan workgroup
| 5/18/12 | P | P | P | Preliminary work group meeting
| 8/21/12 | P | P | P | Second work group meeting
| 9/19/12 | P | P | P | Establish sub committees (clinical/administrative)
| 9/21/12 9/28/12 10/25/12 | P | P | P | Brief sub committee
RECOMMENDATIONS
| 11/31/12 12/14/12 1/18/13 2/5/13 2/22/13 | P | P | P | Finalize recommendations
| 12/30/12 2/28/12 3/31/13 4/30/13 | P | P | P | Finalize work plans and submit to DOH Present recommendations to Workgroup
IMPLEMENTATION
| 1/11/13 3/31/13 4/30/13 5/31/13 6/12/13 | P | P | P | Prioritize recommendations and develop implementation timeline Review with MCOs and develop tracking mechanism.
| 7/1/13 9/1/13 9/13/13 9/27/13 | P | P | P | Implementation of prioritized recommendations. Tracking of plan response to recommendations.
| 10/31/13 11/22/13 | P | P | P | Brief Workgroup on plan adoption and implementation progress

## Boo-yah
BOO-YAH!