## Ph 6 Catch All
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2016-2017 ($millions) | Status/Team Lead Information
Key |  |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 2018-10-24
9001 |  |  |  |  | Project Name: Distressed Hospital Funding Division Lead: OPCHSM Team Lead: Dan Sheppard Description: Additional funding for Distressed Hospitals (VAPAP/VBPQIP) |  | Complete
Office of Primary Care & Health Systems Management
|  | P | P | P
|  | 8 | 8 | 8
9002 |  |  |  |  | Project Name: End of AIDS Epidemic Investment |  | completed May 2017
Division Lead: OPH/AIDS Institute
Team Lead: Ira Feldman Additional Staff: Jackie Treanor, Leah Caola, Ann Maxwell
Description: Ending the AIDS Epidemic activites will include Pre-Exposure Prophylaxis (PrEP), high impact prevention, and linkage and retention in care.
Office of Public Health
| 2016-10-01 | P | P | P | Additional awards for Pre-Exposure Prophylaxis (PrEP). Funding supports expansion of PrEP services, including contracts with providers serving the highest risk populations for outreach, education, screening, linkage to PrEP services, and PrEP Specialists. | These contracts are in place and will last five years total, until 2021.
| 2016-10-01 | P | P | P | Additional community based grant awards for behavioral interventions targeted to reach the highest risk populations (MSM).
| 2016-10-01 | P | P | P | Additional awards to support contracts with providers for programs focused on linkage to and retention in care.
9003 |  |  |  |  | Project Name: 1115 Waiver for Supportive Housing Division Lead: Division of Long-Term Care Team Lead: Liz Misa, Mark Kissinger Additional Staff: Denard Cummings, Andrew Segal, Emily Engel, Kirk Dobson Description: Seeking CMS approval for reimbursement of supportive housing services |  | Suspended Merged from #8306
Division of Long Term Care
| 2016-03-22 | P | P | P | Draft Letter to CMS
| 2016-05-20 | P | P | P | Submit tribal and public notices
| 7/20/16 8/1/16 9/1/16 | P | P | P | Submit request to CMS
| 11/1/2016 12/1/16 | 8 | 8 | 8 | Resubmit proposal with budget neutrality statement
| 2017-07-01 | 8 | 8 | 8 | Following negotiation, receive draft Special Terms and Conditions from CMS
| 2017-08-01 | 8 | 8 | 8 | Review and comment on draft Special Terms and Conditions
| 2017-09-01 | 8 | 8 | 8 | Receive approval and final Special Terms and Conditions from CMS
9004 |  |  |  |  | Project Name: MCO Penalities Division Lead: DHPCO Team Lead: Matthew Rogers Additional Staff: Mark Kissinger Description: Penalty for Late/Incorrect Encounter data from MCOs |  | Completed December 2017
Division of Health Plan Contracting & Oversight
| 2016-02-13 | P | P | P | Introduced statutory language
| 2016-02-23 | P | P | P | Develop encounter data quality assurance protocols to implement the Executive budget proposed penalty measures intended to ensure that encounters are submitted timely and accurately
| 2016-04-01 | P | P | P | Enacted statutory language on encounter penalty proposal
| 2016-05-06 | P | P | P | Outline encounter data quality assurance measures to successfully implement subdivision 32 of § 15. Section 364-j of the social services law
| 2016-05-20 | P | P | P | Develop tier 1 report, measuring timeliness per model contract requirements, determining appropriate threshold
| 2016-05-20 | P | P | P | Develop tier 2 report, measuring full file rejections, determining appropriate threshold
| 2016-05-20 | P | P | P | Develop tier 3 report, measuring completeness based on volume, determining appropriate threshold
| 2016-05-25 | P | P | P | Meet with MCOs regarding report card and penalties
| 2016-06-01 | P | P | P | Distribute "preliminary" report card to MCOs, responding to inquiries
| 2016-06-15 | P | P | P | Distribute May's report card to MCOs, revising, if needed, based on feedback
| 7/15/16 7/29/16 | P | P | P | Distribute June's report card to MCOs
| 2016-09-01 | P | P | P | Outline penalty implementation plan
| 2016-09-30 | P | P | P | Develop corrective action plans including plan outreach
| 10/14/16 10/27/16 | P | P | P | Distribute quarterly report card to MCOs
| 10/31/2016 1/31/20172/7/2017 | P | P | P | Issue penalties Issue Statement of Findings
| 11/30/2016 2/28/20173/14/2017 4/14/17 | P | P | P | Release final appeal determination
| 1/31/20172/7/2017 | P | P | P | Outline advance resubmission standards/requirements
| 2017-10-01 | 8 | 8 | 8 | Develop phase 2 Timeliness Measure: will check if an issuer is submitting pharmacy encounters every business day in accordance with Model Contract requirements
| 2017-10-01 | P | P | P | Develop phase 2 Accuracy Measure: will also require Issuers to maintain an encounter acceptance rate within an appropriate threshold
| 5/20/16 4/30/17 | 8 | 8 | 8 | Develop tier 1 report, measuring overall timeliness based on elapsed time between date of payment and submission, determining appropriate threshold
| 5/20/16 4/30/17 | 8 | 8 | 8 | Develop tier 2 report, measuring hard edit rejections, determining appropriate threshold
| 5/20/16 4/30/17 | 8 | 8 | 8 | Develop tier 3 report, measuring accuracy based on soft edits, determining appropriate threshold
| 5/20/16 4/30/17 | 8 | 8 | 8 | Develop tier 3 report, validating completeness and accuracy by comparing aggregate encounter data to MCO's financial reports, determining appropriate threshold

## Ph 6 Finance & Rate Setting
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2016-2017 ($millions) | Status/Team Lead Information
Key |  |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
Division of Finance & Rate Setting
9101 |  |  |  |  | Project Name: Repatriated Patients' Data Division Lead: DFRS Team Lead: Steve Simmons Additional Staff: Mark Kissinger, Ann Foster, Frank Czernicki Description: Provide Legislature with data associated with repatriation of patients placed in out-of-state facilities |  | Completed April 2017
| 2016-05-06 | P | P | P | Initial Meeting with responsible parties NF & OPWDD to find and define data elements needed
| 2016-05-16 | P | P | P | Meeting with Bureau of Medical Review / OHIP Div of Operations to outline process for residents leaving and coming back to NYS - determine numbers
| 2016-05-17 | P | P | P | Define Nursing Home Data Elements
| 2016-05-25 | P | P | P | Review Database of approved OOS placements
| 2016-05-25 | P | P | P | Determine tracking for OOS NF Residents
| 2016-06-01 | P | P | P | Discuss with OPWDD tracking routines
| 6/1/2016 12/1/16 3/31/17 | 8 | 8 | 8 | Determine improvements to tracking
| 2016-10-01 | P | P | P | Begin report on NF OOS placements: current efforts / improvements to system / discuss possible need to more NYS beds in high OOS areas
| 2016-10-15 | P | P | P | Report in Review (Executive Staff)
9102 |  |  |  |  | Project Name: Global Cap: Legislative Meetings Division Lead: DFRS Team Lead: Mark Shutts Additional Staff: Ann Foster, Donna Cater Description: Meet w/leg staff & health committee chairs at least 6 times annually re: Global Cap |  | complete
| 2016-05-11 | P | P | P | 2015-16 Global Cap Closeout Briefing
| 7/13/16 8/5/16 | P | P | P | 2016-17 Global Cap Model
| 2016-08-05 | P | P | P | Briefings Scheduled with Legislative Staff (9/7/16, 11/2/16, 1/4/17, 3/1/17)
| 2016-09-07 | 8 | 8 | 8 | Global Cap Briefing with Legislature
| 2016-11-02 | 8 | 8 | 8 | Global Cap Briefing with Legislature
| 2017-01-04 | 8 | 8 | 8 | Global Cap Briefing with Legislature
| 2017-03-01 | 8 | 8 | 8 | Global Cap Briefing with Legislature
| 2016-09-15 | 8 | 8 | 8 | 2016-17 GC Update - Actuals through August
| 2016-11-15 | 8 | 8 | 8 | Mid-Year Update to 2016-17 GC Model
| 2017-01-16 | 8 | 8 | 8 | Executive Budget
| 2017-03-15 | 8 | 8 | 8 | 2016-17 preliminary closeout
9103 |  |  |  |  | Project Name: HHC/Public Hospital VBPQIP Payments Division Lead: DFRS Team Lead: Mike Dembrowsky Additional Staff: Mike Ogborn Description: Authorize VBPQIP payments to HHC and other public hospitals |  | Complete Feb 2017
| 2016-08-01 | P | P | P | Develop methodology for reimbursement
| 10/1/16 11/14/16 11/28/16 1/16/17 | P | P | P | Review methodology with stakeholders
| 12/1/16 12/14/16 1/30/17 | P | P | P | Finalize methodology
| 2016-12-12 | P | P | P | Sent to DOB
| 2016-11-08 | P | P | P | Sent to CMS
| 2017-02-13 | P | P | P | Draft rates to plans
| 2017-02-13 | P | P | P | Approved by DOB
| 2017-02-27 | P | P | P | Load rates to the system.
9104 |  |  |  |  | Project Name: Uncompensated Care Division Lead: DFRS Team Lead: Mike Ogborn/Janet Baggetta/Joseph Sohn Additional Staff: John Ulberg Description: Obtain federal approval for uncompensated care for 2015/2016 |  | Completed April 2017
| 2014-05-15 | P | P | P | Five year Waiver extension (thru 2019) request submitted to CMS which includes the Clinic Uncomp. Program (Clinic piece denied by CMS 12/31/14).
| 2015-03-16 | P | P | P | Paper submitted to CMS requesting extension of Clinic program until 2017. Maintains old methodology and updates to metric-based in the future.
| 2016-02-23 | P | P | P | Proposal (#2) submitted to CMS that would allow the State to pay up to provider uninsured cost.
| 2016-04-15 | P | P | P | Additional options (3a and 3b) presented to CHCANYS (formally denied 4/20). As a result, these were not taken to CMS.
CMS/State ongoing discussions regarding 2/23 option to pay up to provider uninsured cost.
| 2016-07-06 | P | P | P | Share new clinic distribution model with CMS
| 2016-07-12 | P | P | P | Submit Federal Public Notice (effective 7/28)
| 7/29/2016 9/2/2016 | P | P | P | Receive CMS approval on new methodology
| 8/26/16 9/29/16 | P | P | P | Submit State Plan Amendment
| 11/15/16 12/15/16 | P | P | P | Receive SPA Approval from CMS
| 2017-01-04 | P | P | P | Clinics notified of the distribution amount for their facility
| 11/16/16 12/21/16 1/10/17 | P | P | P | Submit distribution to Budget for approval
| 11/30/16 12/27/16 1/30/17 2/1/2017 | P | P | P | Receive Budget approval
| 12/16/16 1/3/17 2/2/17 3/31/17 3/22/17 | P | P | P | Payment distributed to providers | Payment included in cycle 2063; For providers on lag payment check release date 3/22/17
9105 |  |  |  |  | Project Name: MC/MLTC Regional Rate Adjustment Division Lead: DFRS Team Lead: Dan Carmody Additional Staff: Mike Dembrowsky, Mike Ogborn, Description: |  | Completed - May 2016
| 2016-04-01 | P | P | P | Review MC/MLTC rates to ensure they are actuarially sound and adhere to all applicable State and Federal regulations
9106 |  |  |  |  | Project Name: Pediatric Ventilator Bed Rate Increases Division Lead: DFRS Team Lead: Janet Baggetta Additional Staff: Mike Ogborn, Connor Gemerek Kristina Thouin Description: Revise the Medical Rehabilitation exempt unit rate in a hospital setting for pediatric ventilator beds. |  | Completed - January 2018
| 2016-05-13 | P | P | P | Federal Public Notice Submission
| 2016-05-13 | P | P | P | SPA development & submitted for review and approval
| 6/30/2016 6/20/2016 | P | P | P | SPA # 16-0029 transmitted to CMS for approval
| 7/15/16 8/15/16 9/30/16 12/30/16 1/31/17 3/1/17 5/1/17 9/1/17 11/1/17 2/1/18 | 8 | 8 | 8 | Regulation submission
| 7/15/16 8/15/16 9/30/16 12/30/16 1/31/17 3/1/17 5/1/17 7/1/17 6/12/17 | P | P | P | Appeal write-up and rate development
| 11/30/16 1/16/17 2/28/17 4/30/17 3/22/17 | P | P | P | SPA approval by CMS
| 11/30/2016 3/31/17 4/30/17 6/30/17 8/30/17 10/31/17 4/1/18 | 8 | 8 | 8 | Regulation approval
| 12/12/2016 3/31/17 4/30/17 6/30/17 8/30/17 6/26/17 | P | P | P | OHIP approval of appeal
| 12/19/2016 4/14/17 5/15/17 7/15/17 9/15/17 7/7/17 | P | P | P | DOB approval of appeal
| 12/20/2016 4/17/17 5/20/17 7/20/17 9/21/17 12/31/17 1/31/18 | 8 | 8 | 8 | Transmit rates to eMedNY/close out appeal
9107 |  |  |  |  | Project Name: Restorative Care Unit Demonstration Program Division Lead: DFRS/ DLTC Team Lead: Mark Kissinger, John Ulberg, Ann Foster Additional Staff: Michelle Santos, Frank Czernicki, Laura Palmer, Rose Avellino Description: |  | In Progress
| 2016-07-01 | P | P | P | Start meetings with Provider (4 times a year)
| 8/1/16 10/1/16 | P | P | P | Determine a schedule for payments, milestones, and metrics
| 2016-10-20 | P | P | P | Request Meeting to Discuss SPA/FFS - to be scheduled
| 9/1/2016 11/1/16 10/01/17 8/31/17 | P | P | P | Establish baseline of current hospital/ readmission rates for site
| 2016-12-15 | P | P | P | Meeting with CMS to discuss project and what CMS would expect to see in a SPA request.
| 9/1/16 10/1/16 11/1/16 12/27/16 | P | P | P | State Plan Amendment sent to CMS DOB
| 2016-12-01 | P | P | P | Finalize contract with Vestracare
| 2017-08-31 | P | P | P | First Status Report due to the Department
| 2017-09-14 | P | P | P | State Plan Amendment approved by CMS
| 1/1/2017 10/1/17 11/15/17 6/30/18 8/31/18 | P | P | P | Develop Evaluation Plan
| 3/30/2017 1/19/17 | P | P | P | 1st Payment
| 3/30/2018 10/1/17 11/01/17 | P | P | P | 2nd Payment
| 2018-02-28 | 8 | 8 | 8 | Second Status Report due to the Department
| 3/30/2019 03/11/2018 03/31/18 | P | P | P | 3rd Payment
| 2018-08-31 | P | P | P | Third Status Report due to the Department
| 2018-09-30 | P | P | P | 4th Payment
| 3/15/2019 01/01/2019 | 8 | 8 | 8 | Submit a final summary of findings and recommendations
| 2019-03-30 | 8 | 8 | 8 | Post Evaluation Meeting with Rate Settings Group to determine future incorporation into rates
| 2019-03-31 | 8 | 8 | 8 | Final Payment Released
9108 |  |  |  |  | Project Name: Carve Out Transportation from NH Rate Division Lead: DFRS Team Lead: Jada Eberle Additional Staff: Mark Bertozzi, Ann Foster Description: |  | Completed - October 2018
| 2016-05-31 | P | P | P | Draft SPA and FPN.
| 2016-06-01 | P | P | P | Submit SPA and FPN for review
| 2016-06-05 | P | P | P | Create a survey for Nursing Homes to identify medical transportation
| 2016-06-08 | P | P | P | Meeting with the Associations to discuss how to identify the costs
| 2016-06-15 | P | P | P | Distribute the survey to facilities to collect data
| 2016-06-27 | P | P | P | Receive all surveys and review results compared to cost report data
| 7/5/16 8/26/16 9/30/16 | P | P | P | Meeting with the Associations to discuss survey results Notify NH Associaltions of the survey results
| 8/15/16 8/31/16 10/20/16 | P | P | P | Finalize and determine per diem for carve out and determine data needed to complete project
| 8/31/2016 10/20/16 | P | P | P | Review and approval by DOH executives. Revise SPA to include updates to reimbursement
| 8/31/2016 10/20/16 10/28/16 12/15/16 1/19/17 | P | P | P | Draft regulations for the new methodology (86-2.10 & 86-2.40)
| 11/1/15 10/18/16 11/15/16 1/19/17 | P | P | P | Finalize and submit regulations for review and approval
| 12/1/16 1/15/16 3/1/17 4/25/17 7/1/17 10/1/17 12/1/17 3/1/18 | P | P | P | Revise rates for the carve out of the transportation costs (effective 4/1/16 - depends on CMS approval Awaiting on Regulation approval, currently in DLA review) - Methodology has been revised to include the appropriate calculation. CMS approved a technical amendment to the approved SPA, preserving the effective date 4/1/16.
| 2018-03-01 | P | P | P | Finalize and determine per diem for carve out and determine data needed to complete project
| 2018-03-15 | P | P | P | Review and approval by DOH executives.
| 2018-03-15 | P | P | P | Revise SPA to include updates to reimbursement. Technical Amendment package sent to CMS 2/20/18 for review.
| 2018-09-01 | P | P | P | Submit revised SPA Pages to CMS
| 3/15/2018 5/10/2018 | P | P | P | Revise Draft regulations for the new methodology (86-2.10 & 86-2.40)
| 3/15/2018 5/10/2018 | P | P | P | Finalize and submit regulations for review and approval
| 8/1/2018 10/1/18 | P | P | P | Finalize rate package to include per diem reduction (Savings of $4 million annually)
| 8/1/2018 10/1/18 | P | P | P | Submit rate package for Executive review
| 10/1/2018 11/1/18 | P | P | P | Publish updated finalized rate package
9109 |  |  |  |  | Project Name: Reduce Managed Care Profit Cap Institute Medicaid MLR Division Lead: DFRS Team Lead: Mike Ogborn Additional Staff: Mike Dembrowsky Description: Tighten MC Profit Cap to 3.5% | $63.0M | Completed - February 2018
| 2016-10-01 | P | P | P | Work with Health Plan Associations to develop methodology to incorporate profit cap as an MLR.
| 3/31/2017 4/24/2017 5/29/17 6/26/17 8/30/17 9/30/17 10/30/17 11/30/17 1/29/18 | 8 | 8 | 8 | Finalize methodology
9110 |  |  |  |  | Project Name: OMIG/Plan MA Fiscal Integrity Division Lead: DFRS Team Lead: Dan Carmody Additional Staff: Mike Ogborn, Mike Dembrowsky, Connor Gemerek Description: | $15.0M | Completed December 2016
| 6/14/2016 8/8/2016 | P | P | P | Draft April 16 rates to plans
| 6/14/2016 8/8/2016 9/6/2016 10/3/2016 | P | P | P | April 16 rates sent to DOB
| 7/14/2016 9/5/2016 10/3/2016 | P | P | P | April 16 rates sent to CMS
| 7/14/2016 9/5/2016 10/31/16 12/31/16 11/21/16 | P | P | P | April 16 rates approved by DOB
| 7/19/2016 9/12/2016 11/10/2016 1/1/17 11/23/16 | P | P | P | April 16 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
9111 |  |  |  |  | Project Name: Office of the State Comptroller Audit Findings Division Lead: DFRS Team Lead: Mike Dembrowsky Additional Staff: Mike Ogborn, Connor Gemerek Description: OSC Audit Findings | $20.0M | Completed December 2016
| 6/14/2016 8/8/2016 | P | P | P | Draft April 16 rates to plans
| 6/14/2016 8/8/2016 9/6/2016 10/3/2016 | P | P | P | April 16 rates sent to DOB
| 7/14/2016 9/5/2016 10/3/2016 | P | P | P | April 16 rates sent to CMS
| 7/14/2016 9/5/2016 10/31/16 12/31/16 11/21/16 | P | P | P | April 16 rates approved by DOB.
| 7/19/2016 9/12/2016 11/10/2016 1/1/17 11/23/16 | P | P | P | April 16 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.
9112 |  |  |  |  | Project Name: Generic CPI Penalty Division Lead: DFRS Team Lead: Rebecca Corso, Janet Zachary-Elkind, Donna Cater Additional Staff: Michael Colabufo, Chris DeSorbo Description: Establishes a penalty for generic drugs that increase by more than 300%. This penalty will be captured through rebates |  | Merged June 2017 10215
| 6/1/2016 7/1/2016 8/15/16 | P | P | P | Develop Draft Methodology for Rebate Collections
| 6/1/2016 7/30/2016 9/15/16 10/7/16 10/24/16 | P | P | P | Engage Stakeholders
| 7/15/2016 8/15/2016 9/30/16 10/22/16 | P | P | P | Legal Review
| 8/1/2016 9/1/2016 10/15/16 11/1/16 11/15/16 | P | P | P | Finalize Methodology
| 8/30/2016 9/30/2016 11/15/16 12/1/16 12/31/16 3/15/17 4/1/17 5/15/17 5/30/17 7/15/17 | 8 | 8 | 8 | System Changes
| 10/1/2016 11/15/16 12/1/16 12/31/16 4/1/17 5/30/17 7/30/17 | 8 | 8 | 8 | Develop instructions for manufacturers on payment
| 12/31/2016 1/15/17 4/30/17 6/30/17 7/30/17 | 8 | 8 | 8 | Send out rebate invoices
9113 |  |  |  |  | Project Name: Accelerate RFP and Rebate Collections (FFS/MCO) Division Lead: DFRS Team Lead: Donna Cater Additional Staff: Michael Colabufo Description: Accelerate the collection of pharmacy rebates through improved management of encounter data and the consolidation and acceleration of rebate administration under a single contract. |  | Merged July 2018 with MRT #11105
ACCELERATE COLLECTION OF REBATES ASSOCIATED WITH OSC AUDITS
| 2016-05-15 | P | P | P | Conduct an analysis of uncollected rebates identified by OSC in their 2014 and 2015 audits and prioritize collection based on complexity involved in identifying and quantifying uncollected rebates.
| 6/1/16 6/30/16 8/1/2016 8/31/2016 9/15/2016 | P | P | P | Quantify rebates that can be collected in the "wave 3" invoice.
| 6/30/16 7/15/16 8/12/16 9/30/16 | P | P | P | Send out "wave 3" invoices.
| 10/1/2016 11/1/2016 12/31/16 3/31/2017 5/31/2017 9/30/2017 | P | P | P | Quantify rebates that can be collected in the "wave 4" invoice.
| 10/30/16 12/31/16 3/31/2017 6/30/2017 10/31/2017 | P | P | P | Send out "wave 4" invoices.
| 4/1/2017 7/1/2017 9/30/2017 3/31/2018 | 8 | 8 | 8 | Work with contractor to identify requirements necessary to collect remaining uncollected rebates.
| 8/1/2017 2/28/2018 | 8 | 8 | 8 | Complete any necessary systems changes.
| 10/1/2017 4/30/2018 | 8 | 8 | 8 | Quantify rebates that can be collected in a "wave 5 invoice".
| 11/1/2017 6/30/2018 | 8 | 8 | 8 | Send out "wave 5" invoices.
IMPROVED MANAGEMENT OF ENCOUNTER DATA
| 6/1/2016 9/1/16 12/1/2016 3/31/2017 4/30/2017 9/30/2017 | 8 | 8 | 8 | Through a demonstration with Fidelis, identify any unsubmitted or rejected pharmacy encounters that can be submitted/resubmitted.
| 9/1/2016 1/1/2017 5/31/2017 10/31/2017 | 8 | 8 | 8 | Conduct systems changes, if necessary.
| 9/1/2016 1/1/2017 5/31/2017 10/31/2017 | 8 | 8 | 8 | Conduct plan education, if necessary.
| 11/1/2016 3/31/2017 6/30/2017 11/30/2017 | 8 | 8 | 8 | Fidelis to submit/resubmit pharmacy encounters.
| 1/30/2017 5/7/2017 10/7/2017 | 8 | 8 | 8 | Quantify rebates associated with submitted/resubmitted pharmacy encounters.
| 2/28/2017 5/31/2017 10/31/2017 | 8 | 8 | 8 | Invoice pharmacy rebates.
| 4/1/2017 6/30/2017 11/30/2017 | 8 | 8 | 8 | Identify trends with other managed care plans based on the Fidelis demonstration and reach out to plans regarding submitting/resubmitting pharmacy encounters.
| 7/1/2017 12/1/2017 | 8 | 8 | 8 | Conduct systems changes, if necessary.
| 7/1/2017 12/1/2017 | 8 | 8 | 8 | Conduct plan education, if necessary.
| 9/1/2017 2/28/2018 | 8 | 8 | 8 | Managed Care Plans to submit/resubmit pharmacy encounters.
| 11/30/2017 4/30/2018 | 8 | 8 | 8 | Quantify rebates associated with submitted/resubmitted pharmacy encounters.
| 12/31/2017 5/31/2017 5/31/18 | 8 | 8 | 8 | Invoice pharmacy rebates.
9114 |  |  |  |  | Project Name: ACA Insurance Tax (MCO Tax) Division Lead: DFRS Team Lead: Mike Ogborn Additional Staff: Description: | $17.5M | Completed December 2017
| 2/28/2017 5/1/2017 7/3/2017 7/31/2017 8/31/2017 | P | P | P | Draft Jan 17 rates to plans
| 2/28/2017 5/1/2017 7/3/2017 7/31/2017 8/31/2017 10/2/2017 | P | P | P | Jan 17 rates sent to DOB
| 2/28/2017 5/1/2017 7/3/2017 7/31/2017 8/31/2017 | P | P | P | Jan 17 rates sent to CMS
| 3/30/2017 5/29/2017 7/31/2017 10/18/17 | P | P | P | Jan 17 rates approved by DOB
| 4/1/2017 6/5/2017 8/14/2017 10/18/2017 | P | P | P | Jan 17 rates loaded to the system. Assumes rates will be loaded once approval is secured from DOB.

## Ph 6 Long Term Care
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2016-2017 ($millions) | Status/Team Lead Information
Key |  |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
Division of Long Term Care
9201 |  |  |  |  | Project Name: Transition of TBI/NHTD Participants to CFCO Division Lead: DLTC Team Lead: Mark Kissinger Dave Hoffman Additional Staff: Margaret Willard, , Andrew Segal Description: Work with all parties to ensure successful transition for TBI/NHTD waiver participants from waiver services to CFCO. Review existing assessment tools to ensure continuity of care. |  | PROJECT ON HOLD UNTIL 9/1/21
| 2016-06-22 | P | P | P | Webinar NHTD/TBI Transition to Managed Care
| 6/9&29/16 | P | P | P | CFCO D&I Council Meetings
| 2016-09-04 | P | P | P | Continuation of Transition Workgroup Meetings
| 2016-06-27 | P | P | P | Webinar Introduction to CFCO
| 2015-08-24 | P | P | P | Crosswalk of waiver services to CFCO services
| 2016-06-22 | P | P | P | Webinar and Posting of waiver transition plan for public comment
| 2016-06-10 | P | P | P | Presentation Brain Injury Association of NYS Annual Conference
| 2016-08-24 | P | P | P | Public Comment submission of the draft transition plan
| 2016-09-14 | P | P | P | Phase two Stakeholder Meeting
| 10/1/2016 12/1/2016 3/1/17 6/1/17 1/1/19 ON HOLD | 8 | 8 | 8 | After comment period develop FAQs and amend plan
| 10/1/2016 12/1/2016 3/1/17 6/1/17 1/1/19 ON HOLD | 8 | 8 | 8 | Complete review of assessment tools
| 10/4/2016 12/1/2016 11/16/16 | P | P | P | Phase two Stakeholder Meeting
| 12/1/2016 1/1/18 6/1/18 TBD ON HOLD | 8 | 8 | 8 | Implementation of CFCO services
| 2/1/2017 10/1/17 7/1/18 TBD ON HOLD | 8 | 8 | 8 | Submit final transition plan for 1915c waiver to CMS
| 6/1/2017 1/1/19 ON HOLD | 8 | 8 | 8 | Upon approval by CMS submit 1115 waiver amendment
| 9/1/2017 7/1/18 TBD ON HOLD | 8 | 8 | 8 | CMS Approvals received
NHTD/TBI Waiver Transition Protections (effective 1/1/18)
| 6/22/2016 &1/1/18 | P | P | P | Continuity of Care Guarantees for participants and providers
| 6/22/2016 &1/1/18 | P | P | P | Enhanced Benefits available in managed care
| 10/1/2016 12/1/2016 3/1/17 6/1/17 1/1/19 ON HOLD | 8 | 8 | 8 | Begin Training Curriculum and Material Development
| 1/1/2018 12/1/18 ON HOLD | 8 | 8 | 8 | 60 day notice voluntary enrollment
| 2/1/2018 TBD ON HOLD | 8 | 8 | 8 | 30 day notice of enrollment
NHTD/TBI Waiver Transition Delay (delays transition to MC until 1/1/18)
| 2016-06-09 | P | P | P | Conference call with CMS to clarify CFCM and status of CFCO services in the 1915c Waivers
| 2016-06-28 | P | P | P | Letter to CMS seeking guidance regarding inclusion of CFCO services in 1915c waivers

## Ph 6 Prog Dev & Mgt
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2016-2017 ($millions) | Status/Team Lead Information
Key |  |  |  |  | P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
Division of Program Development and Management
9301 |  |  |  |  | Project Name: Waiver for Medicaid Services to Inmates Division Lead: DPDM Team Lead: Judith Arnold Additional Staff: Greg Allen, Lyn Karig Hohmann, Joann Susser, Tracie Gardner, Stephanie Fuertes, KIm Ciraulo Description: Seek a federal waiver to provide MA services to inmates in state facilities 30 days prior to release |  | Suspended
| 2016-04-01 | P | P | P | Legislative authority approved to seek waiver to reactivate Medicaid 30 days before release for specific services.
| 2016-04-13 | P | P | P | Meeting of team with Manatt to establish process and timeline
| 5/3/16 6/1/16 | P | P | P | First draft of concept paper prepared to review with CMS
| 5/13/16 6/1/16 6/6/16 | P | P | P | Review concept paper with CMS
| 5/13/16 6/10/16 7/15/16 8/15/16 8/31/16 9/30/16 10/13/16 | P | P | P | Finalize transitional services to be covered in the 30 days prior to release.
| 6/15/2016 7/12/16 | P | P | P | Prepare and submit public notice document for publication Post draft waiver amendment for input
| 6/15/2016 6/28/16 | P | P | P | Provide tribal notice
| 8/31/2016 9/30/16 10/13/16 | P | P | P | Submit waiver amendment
| TBD | 8 | 8 | 8 | CMS response on the waiver
| TBD | 8 | 8 | 8 | Implementation of of workflow pending CMS approval of the waiver
9302 |  |  |  |  | Project Name: Medicaid Update re: Medicare Part B Division Lead: DPDM Team Lead: Connie Donohue Additional Staff: Ronald Bass Description: Draft Medicaid Update re: Medicare Part B cost sharing proposal |  | Completed - May 2016
| 2016-03-31 | P | P | P | Budget letter (including clarification on Medicare Part B Cost-sharing)
| 2016-04-21 | P | P | P | System update to carve out physician administered drugs
| 2016-04-27 | P | P | P | Medicaid Update article published
9303 |  |  |  |  | Project Name: Health Homes for Children Start Up Costs Division Lead: DPDM Team Lead: Lana Earle Additional Staff: Description: Identify and address start-up costs for implementing Health Homes for children within available global cap resources for the HH program |  | Completed December 2016
|  | P | P | P | Identify resources within Global Cap ($7.2 mil - state only)
| 2016-05-23 | P | P | P | Determine legal authorization/appropriation and method for distributing funds(e.g. lump sum or contract, meeting with legal, GSC and FMG staff)
| 5/27/2016 6/20/16 | P | P | P | Develop draft formula for distributing funds to new HHSC and adult HH that have significanly expanded their regional service area to serve children
| 5/27/2016 6/20/16 | P | P | P | Identify permitted uses and reporting requirements for use of the funds (similar to HHDF)
| 6/1/2016 6/24/16 | P | P | P | Pending outcome of 5/23/16 meeting develop detailed work plan for distribution of the funds
| 6/24/2016 8/31/16 | P | P | P | Send notification of award and formula and process lump sum payments thru SFS | Letter at DOB for approval - July 5, 2016 | Complete
9304 |  |  |  |  | Project Name: Ambulance Transportation Rate Adequacy Review Division Lead: DPDM Team Lead: Mark Bertozzi Additional Staff: Description: Rate Review |  | Completed April 2017
| 2016-04-01 | P | P | P | Meet internally to discuss adequacy fee study and formulate implementation plan.
| 2016-05-05 | P | P | P | Develop Rate Adequacy Review Survey
| 2016-05-06 | P | P | P | Disseminate Rate Adequacy Review Survey to providers
| 5/15/16 5/20/16 | P | P | P | Meet internally with Bureau of EMS.
| 5/1/16 6/3/16 | P | P | P | Schedule meeting with stakeholders/ ambulance groups.
| 2016-07-01 | P | P | P | Solicit opinions from ambulance provider associations
| 2016-07-01 | 8 | 8 | 8 | Benchmark fees against Medicare, private pay ambulance and possibly other States
| 9/1/16 8/1/16 9/15/16 10/15/16 9/15/16 | P | P | P | Complete compilation of relevant data
| 10/1/16 9/1/16 10/15/16 11/10/16 11/15/16 | P | P | P | Develop draft report recommendations
| 10/7/16 9/8/16 11/15/16 11/20/16 12/31/16 | P | P | P | Meet with Div. of Fin. & rate Setting to discuss fiscal implications
| 11/1/16 9/15/16 11/1/16 11/20/16 12/1/16 12/31/16 | P | P | P | Approval from Division head.
| 9/22/2015 11/8/16 11/23/16 12/6/16 12/31/16 | P | P | P | Review Recommendations with DOB
| 12/1/2016 12/15/16 12/20/16 2/1/17 3/7/17 | P | P | P | Finalized completed report submitted and approved for release by DOB and submitted to the Legislature
9305 |  |  |  |  | Project Name: Opioids Hard CapDivision Lead: DPDMTeam Lead: Janet Zachary-Elkind Additional Staff: Monica Toohey Description: Implement Hard Cap on Opioids- Social Services Section 364-j, 26-a. Managed care providers shall require prior authorization of thirty-day period, provided, however, that this subdivision shall not apply if the patient is a recipient of hospice care, has a diagnosis of cancer or sickle cell disease, or any other condition or diagnosis for which the commissioner of health determines prior authorization is not required. | 2016-17 State Share 0.17M & 2017-18 0.3M | Completed December 2016
| 2016-04-05 | P | P | P | Notification to the MCO's via quarterly plan meeting legislative requirement effective 4/1/16 (implementaion date 10/1/16)
| 2016-04-26 | P | P | P | Share the legislation, FFS criteria (ICD-codes, inferred drugs etc.) with the MCO's
| 2016-07-05 | P | P | P | Verify MCO's are on track & troubleshoot any issues
| 2016-08-19 | P | P | P | Medicaid update submitted for August release
| 2016-09-01 | P | P | P | MCO's to notify their network providers
| 2016-10-01 | P | P | P | MCO's to implement
| 2016-11-01 | P | P | P | Follow up with MCO's to ensure compliance/ & address any concerns
9306 |  |  |  |  | Project Name: Cost-sharing Limits for Medicare Part C Claims Division Lead: DPDM Team Lead: Cristin Carter, Ron Bass, Connie Donohue, Monica Toohey Additional Staff: Ruth Rivera Description: Effective April 1, 2016 July 1, 2016, Medicaid will limit reimbursement of Medicare Part C to eighty-five percent of the co-payment/coinsurance liability. | $11.45 $8.59 | Completed August 2017
STATE PLAN AMENDMENT SPA #16-26
| 2016-03-30 | P | P | P | Federal Public Notice published
| 2016-05-10 | P | P | P | SPA drafted
| 2016-05-15 | P | P | P | SPA #16-26 reviewed/approved by DPDM
| 2016-05-16 | P | P | P | SPA #16-26 submitted to OHIP DFR Staff for processing/submission
| 5/31/2016 6/30/16 | P | P | P | SPA #16-26 transmitted to CMS (needs to be prior to 7/1/2016 to be effective 4/1/2016)
| 2016-07-29 | P | P | P | Received RAIs
| 2016-08-10 | P | P | P | Submitted resonses to RAIs
| 8/31/16 8/23/16 | P | P | P | SPA approved
SYSTEMS REQUIREMENTS
| 4/30/16 5/18/16 | P | P | P | Evolution Project drafted
| 5/10/16 6/1/16 7/1/16 7/14/16 | P | P | P | Evolution Project submitted
| 5/15/16 7/1/16 9/1/16 8/3/16 | P | P | P | Meet with eMedNY staff to review FRD
| 2017-01-12 | P | P | P | Review Project Design Document
| 9/30/2016 11/30/16 1/15/17 4/15/17 4/10/17 | P | P | P | Meet with eMedNY staff totesting of system changes
| 11/30/2016 10/6/16 | P | P | P | Review and Approval of Assessment of EP
| 12/15/2016 1/31/17 5/25/17 6/1/17 | P | P | P | Implementation of EP
| 1/1/16 1/1/17 2/15/17 8/1/17 8/7/2017 | P | P | P | Special input to reprocess claims retroactively to April 1, 2016 | 4-Cycle process | Total recovery: $8,183,037.73
NOTIFICATIONS
| 2016-05-01 | P | P | P | Draft of Medicaid Update article and/or eMedNY list serve e-blast completed
| 5/7/16 6/1/16 7/10/16 | P | P | P | Review Draft of Medicaid Update and/or eMedNY list serve e-blast
| 6/1/16 7/1/16 7/15/16 | P | P | P | Submit final Medicaid Update article for inclusion in Medicaid Update and/or eMedNY list serve e-blast
| 10/1/2016 11/30/16 1/15/17 3/30/17 4/19/17 | P | P | P | Medicaid Update article submitted for publication published to remind/notify providers of updcoming implementation and of 4/1/2016 7/1/2016 retro effective date
9307 |  |  |  |  | Project Name: Health Homes - Criminal Justice Division Lead: DPDM Team Lead: Lana Earle Additional Staff: Description: Health Homes Criminal Justice – authority to seek waiver of federal funding restrictions |  | Merged - #9301
9308 |  |  |  |  | Project Name: New Ambulette Ambulatory Fee Division Lead: DPDM Team Lead: Mark Bertozzi Additional Staff: Robert Schmit Description: Expansion of the Ambulette Ambulatory Fee to Other Counties |  | Completed December 2016
| 2015-10-13 | P | P | P | Meet with transportation managers and gather input needed for determining fee and estimate percentage applicable for ambulatory level.
| 2015-10-15 | P | P | P | Identify counties where ambulatory fee does not exist and calculated these fees.
| 2015-10-18 | P | P | P | Develop proposal for incusion of executive budget.
| 2015-12-01 | P | P | P | Submit proposal to Division Head for approval.
| 2016-04-01 | P | P | P | Executive budget passing. New fees effective 4/1 upstate.
| 2016-04-04 | P | P | P | Updated fee schedule/emedny for upstate counties.
| 7/15/16 8/12/16 9/7/16 | P | P | P | Develop implementation plan for ambulatory level in NYC and LI
| 2016-09-15 | P | P | P | Update fee schedule/emedny for NYC and LI counties.
| 2016-10-01 | P | P | P | New Fees Effective 10/1 in NYC and Long Island
9309 |  |  |  |  | Project Name: Comprehensive coverage/promotion of LARC Division Lead: DPDM Team Lead: Connie Donohue, Melissa Kinnicutt Additional Staff: Ruth Rivera, Ron Bass Description: Effective April 1, 2016, Medicaid will carve LARCs out of the FQHC PPS. |  | Completed December 2016
| 2016-04-06 | P | P | P | STATUATORY AUTHORITY - ARTICLE 7
SYSTEMS REQUIREMENTS
| 6/21/16 5/25/16 5/6/2016 | P | P | P | Assess existing eMedNY functionality to determine if EPR needed |  | EP not needed
STATE PLAN AMENDMENT SPA #16-0028
| 2016-03-30 | P | P | P | Federal Public Notice published
| 2016-04-04 | P | P | P | Obtain SPA pages to be amended
| 2016-04-22 | P | P | P | SPA drafted
| 2016-05-06 | P | P | P | SPA #16-0028 reviewed/approved by DPDM
| 5/20/16 5/13/2016 | P | P | P | SPA #16-0028 submitted to OHIP DFR Staff for processing/submission
| 6/30/16 5/30/2016 | P | P | P | SPA #16-0028 transmitted to CMS (needs to be prior to September 30, 2015 to be effective July 1, 2015)
| 8/1/16 8/4/16 | P | P | P | SPA approved
NOTIFICATIONS
| 7/1/16 6/1/2016 | P | P | P | Meet to discuss policy guidance to be included in a Medicaid Update article and/or an eMedNY list serve notification
| 7/15/20166/15/2016 | P | P | P | Draft of Medicaid Update article and/or eMedNY list serve e-blast completed
| 7/29/16 8/26/16 | P | P | P | Review Draft of Medicaid Update and/or eMedNY list serve e-blast
| 2016-09-15 | P | P | P | Submit final Medicaid Update article for inclusion in Medicaid Update and/or eMedNY list serve e-blast
| 2016-09-30 | P | P | P | Medicaid Update and/or eMedNY list serve e-blast published
9310 |  |  |  |  | Project Name: Increase Disallowance for Early Elective Deliveries Division Lead: DPDM Team Lead: Donna Urban, Joan Sicard Additional Staff: Connie Donohue Description: Increase Disallowance for Early Elective Deliveries less than 39 weeks without medical indication to 50% | 1.5 | Completed - July 2016
| 2016-01-01 | P | P | P | Complete compilation of relevant data - Continues MRT Project # 5402F initially implemented in 2013 with a ten percent penalty to both the practitioner and facility
| 2016-01-15 | P | P | P | Determine fiscal implications/savings
| 2016-02-01 | P | P | P | Write protocol description to increase disallowance for early elective deliveries without medical indication
SYSTEMS REQUIREMENTS
| 2016-02-01 | P | P | P | Assess existing eMedNY system capacity/functionality to determine if EPR needed | eMedNY not requiring EPR as reduction percentages are in table format.
| 2016-03-15 | P | P | P | E-mail appropriate eMedNY staff to notify of increase from 25% to 50% reduction in payment for non-medically indicated obstetrical deliveries
| 2016-04-01 | P | P | P | eMedNY system changes effective
NOTIFICATIONS
| 2016-02-15 | P | P | P | Meet to discuss increasing the penalty reduction for elective deliveries prior to 39 weeks, without medical indication, from 25% to 50%
| 2026-03-01 | P | P | P | Draft of Medicaid Update article completed
| 2016-03-15 | P | P | P | Inform Division of Health Plan Contractions and Oversight (Medicaid Managed Care) of increased reduction in payment for obstetrical claims
| 4/6/16 | P | P | P | Submit final Medicaid Update article for inclusion in Medicaid Update notifying providers of the April 12016 effective date for fee-for-service claims and the July 1 2016 effective date for Medicaid Managed Care
9311 |  |  |  |  | Project Name: Continued Medicaid Coverage Review Division Lead: DPDM Team Lead: Monica Toohey Additional Staff: Rich Brown, Jonathan Curtin; Melissa Kamal Description: Convene third party claims workgroup to discuss opportunities to ensure that third party coverage information is identified and accessed as appropriate; intial focus is on pharmacy claims |  | In Progress
| 2016-09-09 | P | P | P | Initial meeting to discuss options to ensure that TPHI is identified and accessed
| 2016-09-22 | P | P | P | Team meeting to further discuss options to identify other insurance on member files, including potential coding changes and use of system edits
| 2016-10-01 | P | P | P | eMedNY project EP2149 to make system changes which do not allow the use of Pharmacy Coverage Code 10 when policies are manually entered. To implement on 3/23/17
| 2016-10-04 | P | P | P | Medicare Part C policy load process updated to use Pharmacy Coverage Code 11 (previously used Coverage Code 10)
| 2016-10-20 | P | P | P | Team meeting to continue discussion of system changes; next steps include continued research and follow up with OMIG
| 11/10/16 12/1/16 | P | P | P | Team meeting on to further explore Medicare claims, billing for DME supplies, Part D opt out; discussion with OMIG on improving pharmacy claims data is scheduled
| 2016-12-05 | P | P | P | Meeting with OMIG to discuss improving pharmacy claims data; next steps: call with CSRA, evolution project TBD
| 2016-12-09 | P | P | P | GIS 16 MA/17 provided to local districts to no longer use Pharmacy Coverage Code 10 and use Coverage Code 11 or 12 as appropriate
| 2016-12-13 | P | P | P | New EP submitted to Capture Other Payor ID "BIN", HMS is a stakeholder (fiscal to be determined)
| 2016-12-15 | P | P | P | Update to edit #2004 to stop leakage of Part D claims on Medicare Advantage plans (fiscal to be determined
| 2017-01-05 | P | P | P | Team meeting
| 2017-01-18 | P | P | P | New EP submitted to "Tighten COB" (fiscal to be determined)
| 2/2/17 | P | P | P | Team meeting
| 2017-02-03 | P | P | P | Contact HMS & OMIG regarding reporting of recoupments
| 2017-03-01 | P | P | P | Incorporate DME/supplies to "Tighten COB" project
| 2017-03-01 | P | P | P | Submit new project to prevent duplicate crossover claims
| 2017-03-02 | P | P | P | Team meeting
| 2017-03-17 | P | P | P | In process – HMS reviewing population of clients with only prescription (Cov.Code 12) and no Major Med attempting to identify the Major Med policies. Follow up with HMS on progress..
| 2017-03-24 | P | P | P | Post ep2149 – Begin Development of a separate process to make changes to active policies for active Medicaid Cases which have Pharmacy Coverage Code 10 on the policy.
| 2017-04-06 | P | P | P | Team meeting- discussed options to develop a fiscal for different initiatives within the work plan & additional questions on TPL for OMIG/HMS
| 2017-05-04 | P | P | P | Team meeting
| 2017-05-05 | P | P | P | New EP 5471 "Tighten COB" , Phase 2 submitted (fiscal to be determined)
| 2017-06-06 | P | P | P | Team meeting (OMIG & HMS invited to discuss how tom measure savings/cost avoidance & other options)
| 2017-07-27 | P | P | P | EP 5471 was implemented Tighten COB Phase 1 was implemented
| 7/3/2017 9/14/17 12/20/17 3/1/18 12/5/18 | 8 | 8 | 8 | Possibly submit Phase 3 of Tighten COB, still in conversations to see if this. Review after Phase 2 is implemented.
| 11/1/2017 1/6/18 3/1/18 | P | P | P | Provide savings/cost avoidance of projects implemented to date. Needed more time to do a proper data analysis. We needed at a minimum a quarter’s worth of data to do a pre/post evaluation. Need to incorporate Phase 2 to do a comprehensive look at the data.
| 2018-01-22 | P | P | P | HMS cannot quantify the changes made by TPL (coverage codes 10, 11 & 12) in terms of cost avoidance/savings
| 2018-07-26 | P | P | P | Tighten COB Phase 2 implemented
| 2018-12-07 | 8 | 8 | 8 | Begin analysis for savings
9312 |  |  |  |  | Project Name: Claim Extra 1% FMAP for US Preventative Services Task Force Recommendations Division Lead: DPDM/MMC Team Lead: DPDM: Emily Steinbach Additional Staff: Connie Donohue, Doug Fish, Alda Osinaga, Ron Bass; MMC Description: CMS allows states to claim 1% additional FMAP for USPSTF A&B recommended preventive services when there is no cost-sharing. This initiative would collect the additional 1% FMAP for Managed Care. | $1.234 m | Completed - February 2018
| 2016-04-15 | P | P | P | Validate list of codes that represent the USPSTF A&B recommendations
| 6/14/16 8/31/16 | P | P | P | Meet with Medical Directors to discuss and approve coding list for USPSTF A&B recommendations
| 2016-06-21 | P | P | P | Meet with Managed Care and rate-setting staff to coordinate implementation
| 6/21/16 8/31/16 | P | P | P | Develop implementation plan to incorporate new A&B recommendations when published by USPSTF
| 9/1/16 7/19/16 | P | P | P | Determine Discuss methodology for pulling down extra 1% FMAP in managed care
| 9/16/2016 11/1/2016 1/1/17 3/1/17 5/1/17 9/1/17 10/1/17 | P | P | P | Develop CMS one pager with method for pulling down extra 1% FMAP.
| 10/1/2016 11/1/16 1/1/17 3/1/17 5/1/17 9/1/17 | P | P | P | Discuss Determine methodology for pulling down extra 1% FMAP in managed care
| 10/1/2016 11/1/17 1/1/17 3/1/17 5/1/17 9/1/17 | P | P | P | Determine implications for encounter reporting requirements
| 11/1/2016 12/1/16 1/15/17 4/1/17 6/1/17 10/1/17 12/1/2017 3/1/2018 | P | P | P | Request CMS approval of rate methodology for additional 1% FMAP (effective 4/1/16 1/1/2016)
9313 |  |  |  |  | Project Name: FUL Federal Revision Division Lead: DPDM Team Lead: Janet Zachary-Elkind Additional Staff: Dan McNamara, Monica Toohey Description: CMS finalized the recalibrated FUL to 175% of AMP. CMS published the new FUL late March 2016. Effective April 1, 2016. States had up to 30 days from the effective date to implement the FULs. The FULs will be published monthly thereafter. NYS Medicaid receives a weekly FUL file that reflects any changes made by CMS to the FUL file between the monthly published list. |  | Completed - June 2016
| 2016-02-01 | P | P | P | Evaluate the Federal Revision to the Final Rule with regards to FUL to understand requirements
| 2016-02-15 | P | P | P | Draft a system project
| 2015-03-15 | P | P | P | Obtain an implementation date for the project (CSRA/DOS)
| 2016-03-21 | P | P | P | Send out notication of the changes to the rule (effective 4/1/16, states have until 5/1/16 to comply)
| 2016-04-26 | P | P | P | Implement system project
| 2016-04-27 | P | P | P | Evaluate/trouble shoot issues
| 2016-06-27 | P | P | P | Access pre & post data to validate goals

## Boo Yah
Boo-Yah!